DIGITAL CONSTRUCTION OPERATING SYSTEM

Project Setup

Training Guide for Users & Clients

How a project is created, classified, configured, activated, controlled and closed

| Document | DCOS-PRJ-TRN-001 |
| --- | --- |
| Version | R2 — Enhanced with Project Categories & SOP Alignment |
| Module | 04-02 ¦ Foundation Phase |
| Based on | DCOS-SOP-PS-001 v2.0 |
| Audience | All DCOS users, clients & project teams |

Governing Principle A well-configured project creates a well-controlled project. A poorly configured project creates operational and commercial risk across every downstream module.

# 1. Why Project Setup Matters

Project Setup is the front door of the entire DCOS platform. Every task, drawing, purchase order, inspection, cost entry and payment must belong to a project created and activated here.

Get this module right and the rest of the system stays clean. Get it wrong and every downstream module inherits the mess.

| 1 | 11 | 10 | 4 |
| --- | --- | --- | --- |
| Entry Gate | Project Statuses | Working Days Target | Blocking Items |
| No WBS, task, document or PR can exist without a project | One controlled lifecycle from tender to archive | From Letter of Award to a fully active project | Must be complete before a project can go live |

Remember Replace spreadsheets and chat groups with one controlled registry. Project Setup is the cheapest risk control a construction company can buy.

# 2. Audience & Training Tracks

Four training tracks — take only what your role needs. Everyone starts with Exercise 0: open a sample project and read its status, phase, PM and contract value.

| Track | Audience | Focus | Duration |
| --- | --- | --- | --- |
| A | Company Admin & Project Director | Create projects, approve status changes, assign/change PMs, portfolio review | 2.5 hours |
| B | Project Manager & QS Engineer | Award conversion, contract header, roster, calendar, milestones, WBS | 3 hours |
| C | Tender Team | Register tenders, record bids & results, capture honest win/loss reasons | 1.5 hours |
| D | General Staff (view level) | Find projects, read status chip, understand on-hold and closed meaning | 45 min |

Clients usually need Track D only; contractor staff take Tracks A, B or C.

# 3. The Project Lifecycle

One project, one controlled lifecycle. Statuses are never skipped and never dragged — every move runs a rule check and is recorded with a reason.

## 3.1 Pre-Contract Phase

| DRAFT | Under setup. Editable; not visible to execution modules. |
| --- | --- |
| TENDER | Opportunity registered. Bid preparation in progress. |
| BID SUBMITTED | Tender submitted. Awaiting client decision. |
| AWARDED | Letter of Award received. Conversion checklist opens automatically. |

## 3.2 Delivery & Close-Out Phase

| ACTIVE | Live project. All modules operational. Tasks, drawings and PRs can be created. This is the only working state. |
| --- | --- |
| ON HOLD | Temporarily suspended. New tasks, documents and PRs blocked; approvals already in progress still finish. |
| COMPLETED | Work finished, pending closeout. Execution frozen; closeout activities allowed. |
| CLOSED | All prerequisites satisfied. Formal end of active operations. |
| ARCHIVED | Historical record. Read-only; no new records. Preserved for audit, claims and lessons learned. |
| LOST / CANCELLED | End of the story. Read-only records kept for audit and future tender pricing intelligence. |

Key Rule ACTIVE is the only working state. Tasks, drawings and purchase requisitions can only be created while a project is ACTIVE.

# 4. Project Categories & Classification

Every project is classified on multiple independent axes to support portfolio reporting, benchmarking, tender pricing intelligence and resource planning. Classification values come from controlled master lists maintained in Admin Configuration.

## 4.1 Project Sector Hierarchy

Projects are categorised by sector and sub-type. Select the most specific match available.

Residential

| Luxury Villa | Mansion / Estate | Private Residence |
| --- | --- | --- |
| Standard Villa | Townhouse | Apartment |
| Condominium | Residential Tower | Residential Development |

Commercial

| Showroom | Office Building | Shopping Mall |
| --- | --- | --- |
| Retail Building | Mixed-Use Building | Hotel |
| Restaurant |  |  |

Industrial

| Factory | Warehouse | Manufacturing Facility |
| --- | --- | --- |
| Logistics Center | Industrial Building |  |

Institutional

| School | University | Hospital |
| --- | --- | --- |
| Clinic | Government Building | Religious Building |

Infrastructure

| Road | Bridge | Drainage |
| --- | --- | --- |
| Water Supply | Utility | Other Infrastructure |

## 4.2 Classification Axes (from SOP)

In addition to Sector, each project is classified on three independent axes defined in the Project Setup SOP:

| Classification Axis | Permitted Values |
| --- | --- |
| By Business Type | Tender • Awarded • Internal |
| By Industry | Building • Infrastructure • Industrial • Energy • Water • Maintenance |
| By Contract Type | Lump Sum • Unit Rate • Design & Build • EPC • Turnkey |

Admin Note Adding a new classification value requires Admin authorization to preserve reporting consistency across the portfolio. Values are drawn from controlled master lists only.

# 5. Project Code Standard

Every project receives a unique, immutable code generated at creation. The code is the root identifier referenced by document numbering, WBS codes, cost codes and audit records.

PRJ-YYYY-XXX

| Segment | Meaning | Example |
| --- | --- | --- |
| PRJ | Fixed project prefix | PRJ |
| YYYY | Year of creation | 2026 |
| XXX | Sequential number within the year, zero-padded | 001 |

Examples: PRJ-2026-001, PRJ-2026-002, PRJ-2026-003

- Project codes are unique within the tenant and globally non-reusable.

- Project codes cannot be changed after generation — they are immutable.

- A retired or archived project code is never reissued to another project.

# 6. What You Will Use — Twelve Screens

Twelve screens cover the whole Project Setup module. Walk each screen as: what you see, what you do, what happens next.

| # | Screen | Purpose |
| --- | --- | --- |
| 01 | Portfolio List | All your projects, filters, saved views |
| 02 | Creation Wizard | Seven steps, each one saves on its own |
| 03 | Tender Board | Pipeline columns with deadline countdown |
| 04 | Project Overview | Status, setup ring, contract, milestones, category |
| 05 | Conversion Checklist | The mobilisation cockpit — four blocking items |
| 06 | Team Roster | Who is on the project, and from when |
| 07 | Contract Header | Original value, revisions, current value, currency |
| 08 | Milestones | Contractual dates with LD flags |
| 09 | Calendar Editor | Working pattern and site holidays |
| 10 | Numbering Rules | Document number patterns and locks |
| 11 | Project Settings | Defaults, workflow, notifications, category |
| 12 | Status Change | Reason, approver and consequences |

For clients, screens 01, 04 and 08 are usually sufficient. Do not demo all twelve in a client session.

# 7. The Critical Procedure — LOA to Live in 10 Working Days

Four blocking items must be complete before the Director can activate the project. Until then, no tasks, drawings or purchase orders can be created. A counter on screen shows working days used against the 10-day target. If it stalls, the Director is alerted automatically.

| # | Blocking Item | What Must Be Done | Owner |
| --- | --- | --- | --- |
| 1 | Contract Header | Type, value, currency, dates, DLP, retention | QS |
| 2 | Project Manager | Exactly one PM assigned at any time | Director |
| 3 | WBS Root | PM triggers creation of the project spine | PM |
| 4 | Numbering Rules | Drawing, RFI, PR and PO patterns set | Doc Controller |

Activation Flow PM requests activation → Director (or PMO) approves → project turns ACTIVE and every module unlocks.

# 8. Full Activation Checklist (SOP-Aligned)

Beyond the four critical blocking items, the full activation checklist (from DCOS-SOP-PS-001) must be satisfied. Activation is blocked until every item is confirmed.

| # | Checklist Item | Confirmed By |
| --- | --- | --- |
| 1 | Project information complete and validated (incl. category & classification) | PM |
| 2 | Stakeholders assigned (mandatory parties present) | PM |
| 3 | Internal team assigned with valid roles | PM / Dept Mgr |
| 4 | WBS configured and validated | PM |
| 5 | Project calendar configured | Planning Mgr |
| 6 | Approval workflows configured | SysAdmin |
| 7 | Notification rules configured | SysAdmin |
| 8 | Budget / CBS / currency configured | QS |
| 9 | Dashboards enabled and KPI ownership set | PM |
| 10 | Permissions assigned and reviewed | SysAdmin |

# 9. Golden Rules — Four Things the System Will Never Let You Undo

| # | Rule | Why It Exists |
| --- | --- | --- |
| 1 | Numbering locks on first use | Once the first drawing or RFI number is issued, its pattern is frozen forever. Confirm the preview with the PM before anything is issued. |
| 2 | Contract value is never edited | The original value is permanent. Every change is a revision with a reason and a reference. Current value = original + approved revisions. |
| 3 | One Project Manager, always | A project can never have zero or two PMs. Replacing a PM is a single swap action — never remove and re-add. |
| 4 | You cannot approve your own request | Whoever requests a status change or a contract revision cannot be the approver. This protects both the company and the individual. |

Framing These are protections, not restrictions — they are what makes the audit trail defensible in a claim.

# 10. Common Mistakes and How to Avoid Them

| What People Do | What It Costs | How to Avoid It |
| --- | --- | --- |
| Issuing a drawing before numbering is confirmed | The wrong pattern is locked permanently | PM confirms the preview in writing first |
| Removing a PM then adding a new one | Project left with no PM; approvals stall | Always use the Change PM action |
| Asking IT to “fix” a contract value | Impossible by design — and it hides the change | Raise a contract revision with a reason |
| Vague tender loss reasons | Estimating learns nothing for the next bid | Use the reason code plus one honest sentence |
| Leaving conversion items to day nine | 10-day target missed; Director alerted | PM checks the counter every day |
| Skipping category / classification at setup | Portfolio reports incomplete; benchmarking fails | Select sector + classification axes at registration |

# 11. Hands-On Practice — Tower A Story

Trainees follow a single real-shaped project — P014 Tower A for client Mekong Development, USD 12.4 million lump sum, Residential Tower category — from first opportunity to first issued drawing. Roles are swapped so everyone sees both sides of an approval.

| 06 Jan | Register the tender — Deadline 20 Feb, 14:00 (with time, not just date). Category: Residential → Residential Tower. |
| --- | --- |
| 20 Feb | Record the bid — USD 12.4M submitted, transmittal reference captured. |
| 18 Mar | Record the win — Letter of Award entered. Checklist opens automatically. |
| 19–24 Mar | Complete the four blocking items — Contract, PM, WBS root, numbering — in the correct roles. |
| 26 Mar | Activate — Director approves. 6 working days used, target met. Project becomes ACTIVE. |
| 02 Apr | First drawing issued — P014-STR-DWG-B01-L01-001-R00. Numbering now locked. |

# 12. Keep This on Your Desk — Eight Actions

| Action | How |
| --- | --- |
| Register a tender | Board → Register → client, value, deadline with time, sector/category |
| Record a win | Record Result → LOA reference → checklist opens |
| Convert an award | Contract → PM → WBS root → Numbering → Activate |
| Change the PM | Roster → Change PM → incoming person + effective time |
| Revise a contract | Header → New Revision → delta, reason, reference |
| Set numbering | Preview → PM confirms → then issue. It locks. |
| Put a project on hold | Status → reason citing the client letter → Director approves |
| Close a project | PC certificate → final account → handover → CLOSED |

# 13. Shared Language — Terms Every User Should Recognise

| Term | Definition |
| --- | --- |
| LOA | Letter of Award — the client's formal award notice |
| Mobilisation | The award-to-site-start period, measured here in working days |
| Practical Completion | Works complete for use — starts the defect liability period |
| DLP | Defect Liability Period — the post-completion defect obligation |
| Final Account | The agreed final contract value — the gate to closing a project |
| Retention | Percentage withheld from payments as performance security |
| LD | Liquidated Damages — contractual delay damages, flagged on milestones |
| WBS | Work Breakdown Structure — the spine every record hangs from |
| CBS | Cost Breakdown Structure — budget hierarchy and cost-code framework |
| IPC | Interim Payment Certificate — the monthly claim to the client |
| RBAC | Role-Based Access Control — permission model combining role, project and discipline scope |
| Separation of duties | The requester of a change can never be its approver |

# 14. Roles & Responsibilities (RACI Snapshot)

The following roles participate in Project Setup. Each role draws permissions from the RBAC model; no individual may perform a step for which their role is not authorized.

| Role | Primary Responsibilities in Project Setup |
| --- | --- |
| PMO Manager | Approves project creation; owns governance; approves change requests and closure. Final gate before activation. |
| Project Director | Reviews configuration; confirms commercial parameters; sponsors activation; assigns PM. |
| Project Manager | Performs setup; assigns team; verifies WBS, calendar and budget; submits for activation. |
| System Administrator | Technical configuration; access & permissions; system activation; integrations. |
| QS / Commercial Lead | Defines CBS, cost codes, currency, retention and procurement package structure. |
| Document Controller | Configures document numbering rules and document type master. |
| Planning Manager | Confirms calendar, working pattern and baseline schedule readiness. |

# 15. Change Control & Project Closure

## 15.1 Change-Controlled Items

Once a project is active, the following parameters require a formal change request approved by the PMO Manager:

- Project Manager (governance and accountability continuity)

- Contract Value (commercial baseline and reporting integrity)

- Project Duration (schedule baseline and contractual dates)

- WBS Structure (all linked records depend on WBS integrity)

- Major Stakeholders (approval routing and external relationships)

Workflow: Raise Change Request → Impact Assessment → PMO Approval → Apply Change → Audit & Notify

## 15.2 Closure Prerequisites

- All tasks closed

- All documents closed / issued / superseded as appropriate

- All claims resolved and closed

- All contracts (head and sub) closed

- Financial closeout complete (final account, retention released, payments settled)

Workflow: Request Closure → Review → Approval → Archive

# 16. Proving Competence — Assessment

Access to the live tenant is granted only after the practical assessment — this is a control, not a formality.

| 20 Quiz Questions | 5 Practical Criteria |
| --- | --- |
| Short written check covering statuses, locks, PM rules, categories, classifications and approvals. Answer key included in the guide. | Judged on the live sandbox, not on theory. |

Pass standard (practical):

- Tender registration — Deadline entered with time and timezone; category selected; alerts visible on the board

- Full award conversion — All four blocking items completed in the correct roles; project reaches ACTIVE

- Contract revision — Revision carries a reason and reference; current value verified

- Numbering discipline — Preview confirmed before issue; can explain the lock rule in own words

- Status discipline — Understands separation of duties; reasons cite letters or certificates

# 17. What Happens Next — Three Steps to Go Live

| 1 | Train | Run the four tracks in the sandbox tenant using the Tower A story (Residential Tower category). |
| --- | --- | --- |
| 2 | Assess | Quiz plus practical assessment; access granted on pass. |
| 3 | Adopt | First real project registered with the trainer present, then month-end portfolio review becomes routine. |

Closing Statement A clean project setup is the cheapest risk control a construction company can buy. Project Setup feeds WBS Management next — the same discipline carries forward.

Full SOP detail: DCOS-SOP-PS-001 v2.0  •  Training Code: DCOS-PRJ-TRN-001 R2  •  Module 04-02