## 00_Design_Notes
DCOS — Preliminaries Cost Library ¦ Revised Structure R1
Purpose: Link Project Categories → Prelim Profiles → Cost Library items with applicability & quantity rules
Design Principle
1 | Project Category (from Project Setup) maps to one or more Prelim Profiles.
2 | Each Preliminaries line item carries Applicable Profiles (which profiles can use it).
3 | Site Data parameters are profile-aware: Building params vs Infrastructure/Industrial params.
4 | When a project is created, the system loads the matching Profile → filters library → applies Qty rules.
5 | Common items (site office, security, PPE, welfare) appear in ALL profiles.
6 | Building-specific items (tower crane, facade scaffold, PT back-propping) only on Building profiles.
Sheets in this workbook
01_Prelim_Profiles | Master list of Prelim Profiles and their mapping to Project Categories / Sectors.
02_Category_Map | Explicit mapping: Project Category (from Project Categories.md) → default Prelim Profile.
03_Site_Data_Params | All Site Data parameters with profile applicability and unit.
04_Preliminaries_Library | Full cost library with Applicable Profiles column + Qty Rule guidance.
05_Qty_Rules | Optional lookup of how Qty is derived from Site Data per item / profile.
How the system should use this
Step 1 | User selects Project Category at Project Registration (e.g. Residential Tower).
Step 2 | System looks up 02_Category_Map → gets default Profile (e.g. PROF-BLD-HR).
Step 3 | System filters 04_Preliminaries_Library where Applicable Profiles contains that Profile.
Step 4 | System presents only relevant Site Data params from 03_Site_Data_Params for that Profile.
Step 5 | User (or auto-calc) fills Site Data → Qty rules populate quantities → rates produce amounts.
Version | R1 — Draft structure for review ¦ Date: 2026-10-21 ¦ Based on Prelim_Cost_Library_Default + Project Categories.md

## 01_Prelim_Profiles
Profile Code | Profile Name | Description | Typical Height / Scale | Primary Vertical Transport | Status
PROF-BLD-HR | Building – High Rise | Multi-storey buildings ≥ 6 storeys or ≥ 20 m height. Tower crane, hoist, facade scaffold, edge protection, PT back-propping typical. | ≥ 6 storeys / ≥ 20 m | Tower crane + Passenger hoist | Active
PROF-BLD-LR | Building – Low Rise | Buildings 1–5 storeys. Mobile crane or small tower possible; limited facade scaffold; simpler vertical transport. | 1–5 storeys / < 20 m | Mobile crane / small plant | Active
PROF-IND | Industrial | Factories, warehouses, logistics, manufacturing. Large footprint, often single storey, high eaves. Plant-heavy, less facade work. | Typically 1–2 storeys, large plan | Mobile crane / gantry / forklift | Active
PROF-INF | Infrastructure / Linear | Roads, bridges, drainage, water, utilities. Linear geometry, earthworks, temporary diversion, traffic management dominant. | Linear / area-based | Excavators, rollers, temporary bridges | Active
PROF-GEN | General / Default | Fallback when category is unmapped or internal projects. Contains only common/shared prelim items. | Any | As required | Active

## 02_Category_Map
Sector | Project Category | Default Profile Code | Default Profile Name | Notes / Override Guidance
Residential | Luxury Villa | PROF-BLD-LR | Building – Low Rise | Usually 1–3 storeys; villa-specific site works may be added later
Residential | Mansion / Estate | PROF-BLD-LR | Building – Low Rise | Large low-rise; may need extra landscape/temporary access
Residential | Private Residence | PROF-BLD-LR | Building – Low Rise
Residential | Standard Villa | PROF-BLD-LR | Building – Low Rise
Residential | Townhouse | PROF-BLD-LR | Building – Low Rise
Residential | Apartment | PROF-BLD-LR | Building – Low Rise | If ≤ 5 storeys; otherwise override to HR
Residential | Condominium | PROF-BLD-HR | Building – High Rise | Typically mid/high rise
Residential | Residential Tower | PROF-BLD-HR | Building – High Rise | Core high-rise profile
Residential | Residential Development | PROF-BLD-HR | Building – High Rise | Multi-block; may mix HR + LR — use dominant type or split packages
Commercial | Showroom | PROF-BLD-LR | Building – Low Rise
Commercial | Office Building | PROF-BLD-HR | Building – High Rise | If ≤ 5 storeys, override to LR
Commercial | Shopping Mall | PROF-BLD-LR | Building – Low Rise | Large plan, usually low/mid rise; complex temporary works
Commercial | Retail Building | PROF-BLD-LR | Building – Low Rise
Commercial | Mixed-Use Building | PROF-BLD-HR | Building – High Rise | Often tower + podium; use HR as default
Commercial | Hotel | PROF-BLD-HR | Building – High Rise
Commercial | Restaurant | PROF-BLD-LR | Building – Low Rise
Industrial | Factory | PROF-IND | Industrial
Industrial | Warehouse | PROF-IND | Industrial
Industrial | Manufacturing Facility | PROF-IND | Industrial
Industrial | Logistics Center | PROF-IND | Industrial
Industrial | Industrial Building | PROF-IND | Industrial
Institutional | School | PROF-BLD-LR | Building – Low Rise | Usually low-rise campus
Institutional | University | PROF-BLD-LR | Building – Low Rise | May contain mixed heights — dominant profile
Institutional | Hospital | PROF-BLD-HR | Building – High Rise | Often mid/high rise + complex MEP temporary works
Institutional | Clinic | PROF-BLD-LR | Building – Low Rise
Institutional | Government Building | PROF-BLD-LR | Building – Low Rise | Override to HR if multi-storey tower
Institutional | Religious Building | PROF-BLD-LR | Building – Low Rise
Infrastructure | Road | PROF-INF | Infrastructure / Linear
Infrastructure | Bridge | PROF-INF | Infrastructure / Linear | May need temporary works design emphasis
Infrastructure | Drainage | PROF-INF | Infrastructure / Linear
Infrastructure | Water Supply | PROF-INF | Infrastructure / Linear
Infrastructure | Utility | PROF-INF | Infrastructure / Linear
Infrastructure | Other Infrastructure | PROF-INF | Infrastructure / Linear

## 03_Site_Data_Params
Param Code | Parameter | Unit | Applicable Profiles | Typical Source | Used By (examples) | Mandatory for Profile
P01 | Site perimeter (hoarding line) | m | ALL | Survey / layout | Temporary fencing & hoarding | BLD-HR, BLD-LR, IND
P02 | Building footprint | m2 | BLD-HR, BLD-LR, IND | Architectural GA | Site preparation, some plant | BLD-HR, BLD-LR, IND
P03 | Building perimeter | m | BLD-HR, BLD-LR, IND | Architectural GA | Edge protection length check | BLD-HR, BLD-LR
P04 | Storeys above ground | no | BLD-HR, BLD-LR | Architectural | Edge protection floors, back-propping | BLD-HR, BLD-LR
P05 | Building height | m | BLD-HR, BLD-LR | Architectural | Crane selection, hoist | BLD-HR
P06 | Facade area | m2 | BLD-HR, BLD-LR | Elevation calc | External scaffolding | BLD-HR, BLD-LR
P07 | Programme duration | months | ALL | Master programme | Most monthly items | ALL
P08 | Structure phase duration | months | BLD-HR, BLD-LR, IND | Programme | Tower crane / major plant duration | BLD-HR
P09 | Scaffold rental duration | months | BLD-HR, BLD-LR | Programme | Scaffold hire period | BLD-HR, BLD-LR
P10 | Peak workforce | no | ALL | Resource plan | Welfare sizing, PPE, toilets | ALL
P11 | Floors incl. roof (edge protection) | no | BLD-HR, BLD-LR | Architectural | Edge protection & handrails | BLD-HR, BLD-LR
P12 | Gross floor area | m2 | BLD-HR, BLD-LR, IND | Architectural | Staff overhead drivers, cleaning | BLD-HR, BLD-LR, IND
P20 | Site area (plot) | m2 | IND, INF | Site plan | Hoarding alternative, security coverage | IND
P21 | Eaves / clear height | m | IND | Architectural | Plant selection, temporary works | IND
P22 | Number of crane / plant positions | no | IND, INF | Method statement | Mobile crane mobilisation | IND
P30 | Alignment / road length | m | INF | Civil design | Linear temporary works, traffic management | INF
P31 | Earthworks volume (cut + fill) | m3 | INF, IND | Civil design | Dewatering, temporary drainage scale | INF
P32 | Number of structures / crossings | no | INF | Civil design | Temporary bridges, diversions | INF
P33 | Working width / corridor | m | INF | Civil design | Hoarding / fencing length alternative | INF

## 04_Preliminaries_Library
Code | Description | Unit | Default Qty | Rate ($) | Amount ($) | Applicable Profiles | Qty Rule (guidance) | Level | Status
Z.00 | EARLY WORKS | Sum | 1 | 0 | 0 | ALL | Sum of children | 0 | Active
Z.00.01 | Topography Survey | Item | 1 | 0 | 0 | ALL | Usually Item 1; rate by project | 2 | Active
Z.00.02 | Soil Investigation | Item | 1 | 0 | 0 | ALL | Item 1 or by borehole count | 2 | Active
Z.00.03 | Mine / UXO Clearance | Item | 1 | 0 | 0 | ALL | Item 1 if required by site | 2 | Active
Z.00.04 | Soil Leveling | Item | 1 | 0 | 0 | ALL | Item or m2 of footprint | 2 | Active
Z.00.05 | Demolition | Item | 1 | 0 | 0 | ALL | Item or by volume/area of existing | 2 | Active
Z.00.06 | Cleaning | Item | 1 | 0 | 0 | ALL | Item 1 | 2 | Active
Z.00.07 | Repair existing services | Item | 1 | 0 | 0 | ALL | Item 1 if existing services on site | 2 | Active
Z.00.08 | Renovation | Item | 1 | 0 | 0 | ALL | Item 1 if renovation scope | 2 | Active
Z.01 | TEMPORARY WORKS | Sum | 1 | 344597.62 | 344597.62 | ALL | Sum of children | 0 | Active
Z.01.01 | Site Preparation | Sum | 1 | 35360 | 35360 | ALL | Sum of children | 1 | Active
Z.01.01.01 | Mobilization | Item | 1 | 10500 | 10500 | ALL | Item 1 | 2 | Active
Z.01.01.02 | Demobilization & site clearance | Item | 1 | 6460 | 6460 | ALL | Item 1 | 2 | Active
Z.01.01.03 | Temporary access & roads | Item | 1 | 7400 | 7400 | ALL | Item 1 or by length (INF: use P30) | 2 | Active
Z.01.01.04 | Setting out & ongoing survey works | Month | 18 | 400 | 7200 | ALL | P07 (Programme duration) | 2 | Active
Z.01.01.05 | Site signage & project board | Item | 1 | 800 | 800 | ALL | Item 1 | 2 | Active
Z.01.01.06 | Traffic management & road occupation | Item | 1 | 3000 | 3000 | ALL | Item 1; higher weight on INF | 2 | Active
Z.01.02 | General Protection | Sum | 1 | 50850 | 50850 | ALL | Sum of children | 1 | Active
Z.01.02.01 | Temporary fencing & hoarding | Item | 1 | 7950 | 7950 | ALL | Prefer: P01 × rate/m; or Item | 2 | Active
Z.01.02.02 | Temporary sheet pile, length 6m | m | 95 | 180 | 17100 | BLD-HR, BLD-LR, IND | By design length; often substructure related | 2 | Active
Z.01.02.03 | Safety net to building perimeter | Item | 1 | 6000 | 6000 | BLD-HR, BLD-LR | Item 1 or P03 based | 2 | Active
Z.01.02.04 | Edge protection & handrails | Floor | 11 | 700 | 7700 | BLD-HR, BLD-LR | P11 (Floors incl. roof) | 2 | Active
Z.01.02.05 | Protection of completed works | Item | 1 | 4000 | 4000 | ALL | Item 1 | 2 | Active
Z.01.02.06 | Monsoon protection & site drainage | Month | 18 | 250 | 4500 | ALL | P07 | 2 | Active
Z.01.02.07 | Dewatering during substructure | Month | 4 | 900 | 3600 | BLD-HR, BLD-LR, IND | Substructure duration or fixed months | 2 | Active
Z.01.03 | Temporary Building | Sum | 1 | 36800 | 36800 | ALL | Sum of children | 1 | Active
Z.01.03.01 | Site office, store & welfare facilities | Month | 18 | 1200 | 21600 | ALL | P07; scale by P10 if needed | 2 | Active
Z.01.03.02 | Temporary worker toilets & sanitation | Month | 18 | 200 | 3600 | ALL | P07; scale by P10 | 2 | Active
Z.01.03.03 | First aid room & facilities | Item | 1 | 1500 | 1500 | ALL | Item 1 | 2 | Active
Z.01.03.04 | Washing bay / wheel wash | Item | 1 | 10100 | 10100 | ALL | Item 1 (especially urban / INF) | 2 | Active
Z.01.04 | Temporary Site Labor | Sum | 1 | 14336 | 14336 | ALL | Sum of children | 1 | Active
Z.01.04.01 | Site cleaning & waste removal | Month | 18 | 602 | 10836 | ALL | P07 | 2 | Active
Z.01.04.02 | Final builder's clean at handover | Item | 1 | 3500 | 3500 | ALL | Item 1; scale by P12 optional | 2 | Active
Z.01.05 | Machinery & Vertical Transport | Sum | 1 | 134808 | 134808 | BLD-HR, BLD-LR, IND | Sum of children — profile sensitive | 1 | Active
Z.01.05.01 | Tower crane rental | Month | 16 | 3500 | 56000 | BLD-HR | P08 or structure duration; mainly HR | 2 | Active
Z.01.05.02 | Tower crane foundation, erection, dismantle & test | Item | 1 | 18000 | 18000 | BLD-HR | Item 1 per crane | 2 | Active
Z.01.05.03 | Passenger / material hoist rental | Month | 10 | 1500 | 15000 | BLD-HR | Typically structure + fit-out duration | 2 | Active
Z.01.05.04 | Hoist erection & dismantling | Item | 1 | 4000 | 4000 | BLD-HR | Item 1 | 2 | Active
Z.01.05.05 | Concrete pump provision | Item | 0 | 0 | 0 | BLD-HR, BLD-LR, IND | Item or by pour volume | 2 | Active
Z.01.05.06 | External scaffolding to facade | m2 | 4140 | 7.2 | 29808 | BLD-HR, BLD-LR | P06 (Facade area) | 2 | Active
Z.01.05.07 | Back-propping / falsework for PT slabs | Floor | 10 | 1200 | 12000 | BLD-HR, BLD-LR | P04 or structural floors | 2 | Active
Z.01.05.08 | Mobile crane / crawler crane (alternative) | Month | 0 | 0 | 0 | BLD-LR, IND, INF | For LR / IND / INF instead of tower crane | 2 | Active
Z.01.05.09 | Earthworks plant (excavator, roller, etc.) | Month | 0 | 0 | 0 | INF, IND | P07 or earthworks duration; key for INF | 2 | Active
Z.01.06 | Light Equipment & Hand Tools | Sum | 1 | 6300 | 6300 | ALL | Sum of children | 1 | Active
Z.01.06.01 | Small plant, light equipment & hand tools | Month | 18 | 350 | 6300 | ALL | P07 | 2 | Active
Z.01.07 | Temporary Electrical / Plumbing / Drainage | Sum | 1 | 32943.62 | 32943.62 | ALL | Sum of children | 1 | Active
Z.01.07.01 | Temporary electricity — installation, connection & removal | Item | 1 | 5500 | 5500 | ALL | Item 1 | 2 | Active
Z.01.07.02 | Temporary electricity — consumption & maintenance | Month | 18 | 1258.26 | 22648.68 | ALL | P07; scale by load if known | 2 | Active
Z.01.07.03 | Temporary water — installation, connection & removal | Item | 1 | 1900 | 1900 | ALL | Item 1 | 2 | Active
Z.01.07.04 | Temporary water — consumption & maintenance | Month | 18 | 160.83 | 2894.94 | ALL | P07 | 2 | Active
Z.01.08 | Safety & Environment Control | Sum | 1 | 33200 | 33200 | ALL | Sum of children | 1 | Active
Z.01.08.01 | Health, safety provisions & PPE | Month | 18 | 500 | 9000 | ALL | P07; scale by P10 | 2 | Active
Z.01.08.02 | Site security incl. guards & CCTV | Month | 18 | 900 | 16200 | ALL | P07 | 2 | Active
Z.01.08.03 | Material & concrete testing (QA/QC) | Item | 1 | 8000 | 8000 | ALL | Item 1 or by test regime | 2 | Active
Z.01.09 | Infrastructure Temporary Works (extra) | Sum | 1 | 0 | 0 | INF | Sum of children — activate for INF profile | 1 | Active
Z.01.09.01 | Temporary traffic diversion & signage | Item | 1 | 0 | 0 | INF | Item or by length (P30) | 2 | Active
Z.01.09.02 | Temporary access bridges / crossings | Item | 0 | 0 | 0 | INF | By P32 (number of crossings) | 2 | Active
Z.01.09.03 | Dust, noise & environmental monitoring | Month | 0 | 0 | 0 | INF, IND | P07 | 2 | Active
Z.30 | SITE STAFF & OVERHEADS | Sum | 1 | 243600 | 243600 | ALL | Sum of children | 0 | Active
Z.30.01 | Foreign country employees | Sum | 1 | 90000 | 90000 | ALL | Staffing plan driven | 1 | Active
Z.30.02 | Local country employees | Sum | 1 | 132000 | 132000 | ALL | Staffing plan driven | 1 | Active
Z.30.03 | Other personnel | Item | 0 | 0 | 0 | ALL | As required | 2 | Active
Z.30.04 | Welfare expense | Month | 18 | 300 | 5400 | ALL | P07 | 2 | Active
Z.30.05 | Office supplies expenses | Month | 18 | 200 | 3600 | ALL | P07 | 2 | Active
Z.30.06 | Communication & travel expense | Month | 18 | 250 | 4500 | ALL | P07 | 2 | Active
Z.30.07 | Social expense | Month | 18 | 150 | 2700 | ALL | P07 | 2 | Active
Z.30.08 | Taxes & public imposition | Item | 0 | 0 | 0 | ALL | As applicable | 2 | Active
Z.30.09 | Meeting expense | Month | 18 | 100 | 1800 | ALL | P07 | 2 | Active
Z.30.10 | Miscellaneous expense | Month | 18 | 200 | 3600 | ALL | P07 | 2 | Active
Z.50 | DESIGN EXPENSES | Sum | 1 | 21000 | 21000 | ALL | Sum of children | 0 | Active
Z.50.01 | Shop drawings | Item | 1 | 10000 | 10000 | ALL | Item 1 or by package | 2 | Active
Z.50.02 | As-built drawings | Item | 1 | 6000 | 6000 | ALL | Item 1 | 2 | Active
Z.50.03 | Temporary works design | Item | 1 | 5000 | 5000 | ALL | Item 1; higher for INF/Bridge | 2 | Active
Z.70 | RISKS AND OPPORTUNITIES | Sum | 1 | 0 | 0 | ALL | Sum of children | 0 | Active
Z.70.01 | Risk allowance | Item | 0 | 0 | 0 | ALL | % of prelims or fixed sum | 2 | Active
| TOTAL PRELIMINARIES (default Building HR values) |  |  |  | 609197.62

## 05_Qty_Rules
Code | Description | Unit | Primary Qty Driver | Formula / Rule | Profiles where active
Z.01.01.04 | Setting out & ongoing survey works | Month | P07 | Qty = P07 | ALL
Z.01.02.01 | Temporary fencing & hoarding | Item / m | P01 | Prefer Qty = P01 (m); or Item lump sum | ALL
Z.01.02.04 | Edge protection & handrails | Floor | P11 | Qty = P11 | BLD-HR, BLD-LR
Z.01.02.06 | Monsoon protection & site drainage | Month | P07 | Qty = P07 | ALL
Z.01.03.01 | Site office, store & welfare | Month | P07 | Qty = P07 (optionally scale rate by P10) | ALL
Z.01.03.02 | Temporary worker toilets | Month | P07 / P10 | Qty = P07; rate may vary with P10 | ALL
Z.01.04.01 | Site cleaning & waste removal | Month | P07 | Qty = P07 | ALL
Z.01.05.01 | Tower crane rental | Month | P08 | Qty ≈ P08 (or structure + buffer) | BLD-HR
Z.01.05.03 | Passenger / material hoist rental | Month | Programme | Typically structure + fit-out months | BLD-HR
Z.01.05.06 | External scaffolding to facade | m2 | P06 | Qty = P06 | BLD-HR, BLD-LR
Z.01.05.07 | Back-propping / falsework for PT slabs | Floor | P04 | Qty = P04 (or structural floors) | BLD-HR, BLD-LR
Z.01.05.08 | Mobile crane / crawler crane | Month | Method | User / method statement driven | BLD-LR, IND, INF
Z.01.05.09 | Earthworks plant | Month | P07 / earthworks duration | User or derived from P31 programme | INF, IND
Z.01.06.01 | Small plant, light equipment | Month | P07 | Qty = P07 | ALL
Z.01.07.02 | Temporary electricity — consumption | Month | P07 | Qty = P07 | ALL
Z.01.07.04 | Temporary water — consumption | Month | P07 | Qty = P07 | ALL
Z.01.08.01 | Health, safety provisions & PPE | Month | P07 / P10 | Qty = P07; rate scales with P10 | ALL
Z.01.08.02 | Site security incl. guards & CCTV | Month | P07 | Qty = P07 | ALL
Z.01.09.01 | Temporary traffic diversion | Item / m | P30 | Item or Qty related to P30 | INF
Z.01.09.02 | Temporary access bridges / crossings | Item | P32 | Qty ≈ P32 | INF
Z.30.04–10 | Monthly staff overhead items | Month | P07 | Qty = P07 | ALL

## 99_Legend
Legend & Colour Key
Profile colours (used in 02_Category_Map)
Residential | Blue tint
Commercial | Green tint
Industrial | Amber tint
Institutional | Purple tint
Infrastructure | Pink tint
Library Level
Level 0 | Section header (dark navy) — Sum of children
Level 1 | Subsection (teal tint) — Sum of children
Level 2 | Measurable item — carries rate & qty
Applicable Profiles values
ALL | Item appears in every profile
BLD-HR | Building – High Rise only
BLD-LR | Building – Low Rise only
IND | Industrial only
INF | Infrastructure / Linear only
Comma list | Item appears in the listed profiles only
Next design steps (optional)
1 | Add rate libraries per country / currency if multi-tenant
2 | Add 'Default Rate Source' column (internal rate / subcontract quote)
3 | Link Z.30 staff costs to a resource/role library later
4 | Consider package-level prelims for multi-block Residential Development