## Slide 1
DIGITAL CONSTRUCTION OPERATING SYSTEM
Project Setup
Training Summary for Users & Clients
How a project is created, awarded, controlled and closed inside one platform — and what each role must do.
Module 04-02
Foundation Phase
Document R1
Notes: Opening slide. Frame Project Setup as the entry gate of the whole platform: nothing exists in DCOS without a project created here.

## Slide 2
WHY IT MATTERS
Project Setup is the front door of the platform
Every task, drawing, purchase order, inspection and payment in DCOS must belong to a project created here. Get this module right and the rest of the system stays clean; get it wrong and every downstream module inherits the mess.
1
entry gate
No WBS, task, document or PR can exist without a project
11
project statuses
One controlled lifecycle from tender to archive
10
working days
Target from Letter of Award to a fully active project
4
blocking items
Must be complete before a project can go live
“Replace spreadsheets and chat groups with one controlled registry.”
DCOS-PRJ-TRN-001 | R1
2
Notes: Anchor the business case before any screen is shown. The four numbers are the ones people remember.

## Slide 3
AUDIENCE
Four training tracks — take only what your role needs
A
Company Admin & Project Director
Create projects, approve status changes, assign and change PMs, run the month-end portfolio review.
2.5 hours
B
Project Manager & QS Engineer
Drive award conversion, maintain contract header, roster, calendar and milestones.
3 hours
C
Tender Team
Register tenders, record bids and results, capture honest win/loss reasons.
1.5 hours
D
General Staff (view level)
Find your projects, read the status chip, know what on-hold and closed mean for daily work.
45 minutes
Chart: Training time (hours)
| Track A | Track B | Track C | Track D
Hours | 2.5 | 3 | 1.5 | 0.75
Everyone starts with Exercise 0: open project P014 and read its status, phase, PM and contract value.
DCOS-PRJ-TRN-001 | R1
3
Notes: Clients usually need Track D only; contractor staff take A, B or C.

## Slide 4
THE JOURNEY
One project, one controlled lifecycle
PRE-CONTRACT
DRAFT
→
TENDER
→
BID SUBMITTED
→
AWARDED
DELIVERY & CLOSE-OUT
ACTIVE
⇄
ON HOLD
pause & resume
→
COMPLETED
→
CLOSED
→
ARCHIVED
ACTIVE is the only working state
Tasks, drawings and purchase requisitions can only be created while a project is ACTIVE.
ON HOLD freezes new work
New tasks, documents and PRs are blocked; approvals already in progress still finish.
LOST & CANCELLED end the story
Both are read-only records kept for audit and for future tender pricing.
DCOS-PRJ-TRN-001 | R1
4
Notes: Statuses are never skipped and never dragged — every move runs a rule check and is recorded with a reason.

## Slide 5
WHAT YOU WILL USE
Twelve screens cover the whole module
01
Portfolio List
All your projects, filters, saved views
02
Creation Wizard
Seven steps, each one saves on its own
03
Tender Board
Pipeline columns with deadline countdown
04
Project Overview
Status, setup ring, contract, milestones
05
Conversion Checklist
The mobilisation cockpit
06
Team Roster
Who is on the project, and from when
07
Contract Header
Original value, revisions, current value
08
Milestones
Contractual dates with LD flags
09
Calendar Editor
Working pattern and site holidays
10
Numbering Rules
Document number patterns and locks
11
Project Settings
Defaults, workflow and notifications
12
Status Change
Reason, approver and consequences
DCOS-PRJ-TRN-001 | R1
5
Notes: Walk each screen as: what you see, what you do, what happens next. Do not demo all twelve to clients — screens 01, 04 and 08 are enough.

## Slide 6
THE CRITICAL PROCEDURE
From Letter of Award to live project in 10 working days
Four blocking items must be complete before the Director can activate the project. Until then, no tasks, drawings or purchase orders can be created.
1
Contract header
QS enters type, value, currency, dates, DLP, retention
QS
2
Project Manager
Director assigns the PM — exactly one at any time
Director
3
WBS root
PM triggers creation of the project spine
PM
4
Numbering rules
Document Controller sets drawing, RFI, PR and PO patterns
Doc Controller
Then: PM requests activation → Director approves → project turns ACTIVE and every module unlocks.
A counter on screen shows working days used against the 10-day target. If it stalls, the Director is alerted automatically.
DCOS-PRJ-TRN-001 | R1
6
Notes: This is the single most important slide for a contractor audience. The four items are the same four every time, regardless of project size.

## Slide 7
GOLDEN RULES
Four things the system will never let you undo
1
Numbering locks on first use
Once the first drawing or RFI number is issued, its pattern is frozen forever. Confirm the preview with the PM before anything is issued.
2
Contract value is never edited
The original value is permanent. Every change is a revision with a reason and a reference. Current value = original + approved revisions.
3
One Project Manager, always
A project can never have zero or two PMs. Replacing a PM is a single swap action — never remove and re-add.
4
You cannot approve your own request
Whoever requests a status change or a contract revision cannot be the approver. This protects both the company and the individual.
DCOS-PRJ-TRN-001 | R1
7
Notes: Frame these as protections, not restrictions — they are what makes the audit trail defensible in a claim.

## Slide 8
LEARN FROM OTHERS
Common mistakes and how to avoid them
What people do
What it costs
How to avoid it
Issuing a drawing before numbering is confirmed
The wrong pattern is locked permanently
PM confirms the preview in writing first
Removing a PM then adding a new one
The project is left with no PM and approvals stall
Always use the Change PM action
Asking IT to “fix” a contract value
Impossible by design — and it hides the change
Raise a contract revision with a reason
Vague tender loss reasons
Estimating learns nothing for the next bid
Use the reason code plus one honest sentence
Leaving conversion items to day nine
The 10-day target is missed and the Director is alerted
The PM checks the counter every day
DCOS-PRJ-TRN-001 | R1
8
Notes: Run this slide as a discussion — ask the room which mistake they have already made on paper systems.

## Slide 9
HANDS-ON PRACTICE
One story runs through the whole training: Tower A
Trainees follow a single real-shaped project — P014 Tower A for client Mekong Development, USD 12.4 million lump sum — from first opportunity to first issued drawing. Roles are swapped so everyone sees both sides of an approval.
06 Jan
Register the tender
Deadline 20 Feb, 14:00 — with the time, not just the date
20 Feb
Record the bid
USD 12.4M submitted, transmittal reference captured
18 Mar
Record the win
Letter of Award entered — checklist opens automatically
19–24 Mar
Complete the four items
Contract, PM, WBS root, numbering — in the correct roles
26 Mar
Activate
Director approves — 6 working days used, target met
02 Apr
First drawing issued
P014-STR-DWG-B01-L01-001-R00 — numbering now locked
DCOS-PRJ-TRN-001 | R1
9
Notes: Cambodian project context on purpose — trainees recognise the client type, the currency and the timezone handling.

## Slide 10
KEEP THIS ON YOUR DESK
Eight actions, one line each
Register a tender
Board → Register → client, value, deadline with time
Record a win
Record Result → LOA reference → checklist opens
Convert an award
Contract → PM → WBS root → Numbering → Activate
Change the PM
Roster → Change PM → incoming person + effective time
Revise a contract
Header → New Revision → delta, reason, reference
Set numbering
Preview → PM confirms → then issue. It locks.
Put a project on hold
Status → reason citing the client letter → Director approves
Close a project
PC certificate → final account → handover → CLOSED
DCOS-PRJ-TRN-001 | R1
10
Notes: Print this slide as an A5 card for site offices.

## Slide 11
PROVING COMPETENCE
Assessment before system access is granted
20
quiz questions
Short written check covering statuses, locks, PM rules and approvals. Answer key included in the guide.
5
practical criteria
Judged on the live sandbox, not on theory.
Pass standard
Tender registration
Deadline entered with time and timezone; alerts visible on the board
Full award conversion
All four blocking items completed in the correct roles; project reaches ACTIVE
Contract revision
Revision carries a reason and reference; current value verified
Numbering discipline
Preview confirmed before issue; can explain the lock rule in own words
Status discipline
Understands separation of duties; reasons cite letters or certificates
DCOS-PRJ-TRN-001 | R1
11
Notes: Access to the live tenant is granted only after the practical assessment — this is a control, not a formality.

## Slide 12
SHARED LANGUAGE
Terms every user should recognise
LOA
Letter of Award — the client's formal award notice
Mobilisation
The award-to-site-start period, measured here in working days
Practical Completion
Works complete for use — starts the defect liability period
DLP
Defect Liability Period — the post-completion defect obligation
Final Account
The agreed final contract value — the gate to closing a project
Retention
Percentage withheld from payments as performance security
LD
Liquidated Damages — contractual delay damages, flagged on milestones
WBS
Work Breakdown Structure — the spine every record hangs from
IPC
Interim Payment Certificate — the monthly claim to the client
Separation of duties
The requester of a change can never be its approver
DCOS-PRJ-TRN-001 | R1
12
Notes: Clients often use these terms loosely — agreeing definitions early prevents disputes later.

## Slide 13
WHAT HAPPENS NEXT
Three steps to go live
1
Train
Run the four tracks in the sandbox tenant using the Tower A story.
2
Assess
Quiz plus practical assessment; access granted on pass.
3
Adopt
First real project registered with the trainer present, then month-end portfolio review becomes routine.
A clean project setup is the cheapest risk control a construction company can buy.
Full detail: 12-Training-Guide.md · DCOS-PRJ-TRN-001 · Module 04-02 Project Setup
Notes: Close by reminding the room that Project Setup feeds WBS Management next — the same discipline carries forward.