## Slide 1
DCOS · DIGITAL CONSTRUCTION OPERATING SYSTEM
WBS Management
How the project breakdown structure works —
and why it protects your programme, your cost report, and your claim.
Training & orientation · For project teams and clients
Module 04-03 · Foundation Phase · Version R1 · August 2026
P001 Tower A
PH2 Superstructure
B01 Tower A
L05 Level 05
Z03 Zone 03
STR Slab
Notes: Opening: this session is about one thing — the addressing system that every other part of DCOS depends on. Keep it practical; the audience includes clients.

## Slide 2
One building, four versions of the truth
How work is broken down today — and what it costs every month
The Planner
Keeps the breakdown in Primavera, organised by activity.
The QS
Keeps it in the BOQ, organised by trade and bill section.
The Document Controller
Keeps it hidden inside drawing numbers.
The Site Team
Keeps it on a whiteboard, floor by floor.
4
answers to one question
“How is Level 05 doing?” produces four different numbers, computed against four different definitions of Level 05.
The cost: 2–4 staff-days per project every month spent reconciling reports — and contradictory numbers presented to the client.
Source: DCOS Business Requirement, pain points PP-01 to PP-12
Notes: Ask the room: how many versions of the floor list exist on your current project? Usually the answer is more than four.

## Slide 3
What this session covers
Five ideas, one skill, and the rules you will meet in daily use
1
The five core ideas
What a WBS is here, why one structure, and why tasks sit outside the tree.
2
Reading a WBS code
The single skill that makes the whole system navigable.
3
How progress is calculated
Roll-up, weighting, and why you cannot type a summary figure.
4
The three safeguards
Delete guard, baseline lock, override flag — what they look like.
5
The screens and the rhythm
What you use daily, monthly, and at each milestone.
6
Your training track
Six role-based paths, with hands-on exercises.
Core concepts: 60 minutes for everyone · Role tracks: 1.5 to 4 hours

## Slide 4
Idea 1 — The WBS is your addressing system
Not a folder tree. Every record in DCOS has a location in it.
Every task, drawing, cost line, material batch, inspection, photo, and payment valuation attaches to a location in this structure.
That is why DCOS can answer “how is Level 05 doing?” — Level 05 is a real object with real records attached to it.
Every node answers five questions: which project, which location, which discipline, who is responsible, what status.
The five questions
Project? · Location? · Discipline? · Responsible? · Status?
P001 Tower A Mixed-Use Development
PH2 Superstructure
B01 Tower A
L05 Level 05
Z03 Zone 03 (East Wing)
STR Structural
SLAB Slab to L05 — work package
Notes: Point at the amber node: this is a work package — the lowest structural level, and the thing a QS can measure and a supervisor can report against.

## Slide 5
Idea 2 — One structure means one answer
The same spine serves planning, cost, documents, QA, and site
Without a shared spine
Four departments, four breakdowns of the same building
Progress reconciled by hand in Excel every month
Cost answerable by code, never by location
Document numbers orphaned when a level is renamed
Subcontractors see everything — or nothing at all
With DCOS
One definition of “Level 05” across every department
Progress rolls up automatically from the work face
Cost aggregated by zone, level, building, and phase
Old document numbers still resolve after a change
Each party sees exactly the area assigned to them
The departments work in different rooms — but the building is one building.

## Slide 6
Idea 3 — Tasks attach to the tree, not into it
You still see them under the location. The screen joins them — the structure does not carry them.
P001-PH2-B01-L05-Z03-STR-SLAB
Slab to L05
One work package —
one location in the structure
WORK PACKAGE
12 tasks
34 drawings
BOQ cost lines
Inspection requests
Site photos
Material batches
Why it matters
A 20-storey tower has roughly 5,000 locations and 80,000 tasks. Keeping tasks out of the structure is what keeps the tree fast, stable, and capable of being baselined — so last month's valuation can still be reconciled to this month's.

## Slide 7
Idea 4 — Progress is calculated, never typed
This is the one that changes behaviour. You cannot type “Level 05 is 60%”.
Child
Its progress
Weight (budget)
Contribution
Structural
70.0%
$180,000
63.0%
MEP
30.0%
$20,000
3.0%
Zone 03 — cost-weighted
$200,000
66.0%
Weighted equally instead of by cost, the same children would read 50%.
66.0%
Derived, not declared
If the number looks wrong, the fix is in the work packages — not in the summary.
There is an override — and it is deliberately uncomfortable
Project Managers and Directors only · a reason code is compulsory · the node is flagged in every report and export · it appears on a report the Project Director reads.
Notes: Emphasise: the override exists for genuine data lag, not for making a report look better before a client meeting.

## Slide 8
The five weighting methods, one line each
Set per branch — the QS decides which one is honest for the work
1
Equal weight
Simple average of the children.
Early planning only, before cost data exists.
2
Cost weighted
Weighted by each child's budget.
The default once the BOQ is loaded — and the commercially honest one.
3
Duration weighted
Weighted by planned days.
Programme-driven reporting before cost loading.
4
Quantity weighted
Weighted by measured quantities.
Repetitive work — piling, slabs, blockwork, cladding.
5
Manual override
A typed value, flagged and reason-coded.
Exception only, cleared within days.
Change the method and the number changes — that is expected, and the contribution table always shows how the figure was produced.

## Slide 9
How to read a WBS code
Read it left to right for “where”. Read it right to left for “what”.
P001
Project
Tower A
PH2
Phase
Superstructure
B01
Building
Tower A
L05
Level
Level 05
Z03
Zone
East Wing
STR
Discipline
Structural
SLAB
Work package
The slab
Where you meet it
Every document number on the project carries the middle segments:
P001-STR-DWG-B01-L05-001-R02
That is exactly why codes cannot be changed casually — and why an old number still resolves after an approved change.
Practical tip
On a 5,000-node project, stop expanding the tree and start searching. Search is scoped to what you are allowed to see, and it returns results in under a third of a second.
Competent = finds any node in under 20 seconds.

## Slide 10
Idea 5 — The structure locks at baseline
Because the QS values the work against it every single month
1
Build freely
Create, move, re-code, import, delete. Nothing is locked while the structure is being designed.
2
Four-party sign-off
Planner, QS, Document Controller and PM each confirm the structure serves their needs.
3
Baseline R0
A frozen snapshot. Set before the first payment application at the latest.
4
Change control
From here, moving or re-coding needs an approved change request — with a reason.
The question this answers
“Prove the structure you valued this month's application against is the same structure you valued last month's against.” — the baseline comparison answers it in one export.

## Slide 11
Three safeguards you will meet
Each one blocks something — and each one offers the legitimate route instead
1
Delete guard
WHAT HAPPENS
You try to delete a location that has 34 drawings and 12 tasks attached.
WHAT YOU SEE
Blocked. The system offers Archive, or reassigning the records first.
Records are evidence. Never delete records in order to free a location.
2
Baseline lock
WHAT HAPPENS
You try to move a zone after the structure has been baselined.
WHAT YOU SEE
Blocked. A “Raise change request” button appears, pre-filled.
It is never “just a small change” once a valuation exists.
3
Override flag
WHAT HAPPENS
A progress figure is typed rather than derived.
WHAT YOU SEE
Allowed for PM/Director only — flagged everywhere until cleared.
Fix the underlying data within five working days.

## Slide 12
The approved route: a change request
Five steps, one paper trail, and the change is applied by the system
1
Raise
Change type, affected nodes, target, justification, and the contractual reference (instruction or variation).
2
Preview
Read the impact: how many locations, how many attached records, which codes change.
3
Route
Goes to the Project Manager. If the PM raised it, it goes to the Project Director.
4
Decide
Approve with comment, or reject with a mandatory comment saying what would make it acceptable.
5
Apply & verify
The system applies the change and stamps the reference into the audit record. You then verify.
Two rules that never bend: the person who raises a request cannot approve it · no decision within 48 hours escalates automatically to the Project Director.

## Slide 13
Always read the impact preview
It appears before every move, delete, cascade, cancel, and import commit
Move “Zone 03 (East Wing)” to “Level 06”
This affects
9 locations will move · 46 attached records follow
34 drawings · 12 tasks · 3 responsibility assignments
Codes will change
…-B01-L05-Z03-STR-SLAB → …-B01-L06-Z03-STR-SLAB
Old codes remain searchable for document retrieval.
Roll-up recalculates
Level 05 chain and Level 06 chain
Notifications
PM, Discipline Manager, Document Controller, area engineer
Cancel
Confirm
Why it earns its place
Nothing runs until you confirm.
The counts are live, not estimated.
If a count surprises you, that surprise is the point — cancel and investigate.
After the move, verify: three codes, the record count, and one old drawing number.

## Slide 14
Node statuses at a glance
What each one means for the work — and for the numbers
Draft
Being built. Not yet available to other modules.
Active
Live. Tasks, documents and cost can be attached.
On hold
Suspended — but still in scope, so still counted.
Completed
Physically finished, awaiting closure checks.
Closed
Gates passed, locked. No new records.
Cancelled
Descoped by variation. Removed from the calculation.
Archived
History. Out of active views, fully reportable.
The pair people get wrong: On hold stays IN the calculation — suspended work is still scope. Cancelled comes OUT entirely — that scope no longer exists.

## Slide 15
Six training tracks, one core session
Core concepts: 60 minutes, all attendees. Then your role track.
Project Manager / Director
3 h
Governance, baselines, approving change, override discipline, closure gates
Planner / Scheduler
4 h
Breakdown design, coding, templates, import, duplication, move and verification
QS / Cost Engineer
3 h
Cost containers, all five roll-up methods, baseline diff, monthly verification
Document Controller
2 h
Code segments, numbering integration, immutability, historical resolution
Site Engineer / Supervisor
1.5 h
Navigation, reading codes, reporting by location, mobile and offline use
Company Admin
3 h
Node types, structure rules, templates, integrity report, access scoping
Delivery: classroom for core concepts · hands-on in the “Tower A Training” sandbox · supervised live use for the first two weeks

## Slide 16
Practise in a sandbox first
Fifteen exercises on the “Tower A Training” project — six shown here
1
Build it
Apply the tower template and detail Level 05 with zones, disciplines and work packages.
2
Import it
Load 40 rooms from a file — then load a deliberately corrupted one and explain both errors.
3
Repeat it
Duplicate Level 05 to Levels 06–10 and confirm the codes generated correctly.
4
Calculate it
Work out Zone 03 on paper as cost-weighted, then check the system agrees at 66%.
5
Get blocked
Try to delete a location with records attached, and choose the right alternative.
6
Change it
Set a baseline, get a move blocked, raise a change request, approve it, verify the result.
Assessment: a 20-question quiz (pass mark 16) plus a practical rubric covering navigation, code reading, roll-up understanding and change control.

## Slide 17
The mistakes that cost the most
Every one of these has happened on a real project
!
Building the tree for one department
Run the structure workshop; four parties sign off before baseline.
!
Work packages too coarse to measure
Ask the QS: can you measure this monthly? If not, split it.
!
Deleting instead of archiving
Records are evidence. Archive keeps them locatable.
!
Overriding instead of fixing
Fix the work-package data; clear the override within five days.
!
Restructuring after baseline without a request
It is never “just a small change” once a valuation exists.
!
Committing an import without reading the dry run
400 wrong locations take 30 seconds to create and a day to unpick.

## Slide 18
The rhythm: what happens, and when
Fourteen written procedures sit behind this — these are the moments that matter
At award
Structure workshop, apply a template, agree the coding convention
Before the first application
Four-party review and sign-off, then set Baseline R0
Weekly
Structure changes reviewed in the progress meeting; unassigned areas checked
Monthly, 3 days before cut-off
Roll-up verification before the payment application is prepared
Month end
Integrity review; overrides older than 14 days reviewed by the Director
At each milestone
Close the branch once inspections and open items are cleared
At handover
Export, archive, and retain for the defects period plus five years
Full detail in the module SOPs — the pre-baseline sign-off is the single control that prevents six months of rework.

## Slide 19
When someone asks hard questions
Client, consultant, auditor — every question has one place to look
“Is the structure controlled?”
Baseline register and the signed structure sheet
“Did it change since the last valuation?”
Baseline comparison export — one page
“Who authorised this change?”
The change request and its approval record
“How was this progress figure derived?”
The contribution table, child by child
“Why is this drawing number not in the tree?”
Historical code resolution — old codes still resolve
“Was anything deleted?”
Nothing is. Locations are archived, never purged.
Every structural action is recorded permanently — who did it, when, what changed, and why.

## Slide 20
Five things to take away
1
The WBS is the address of everything
If a record has no location, it cannot be reported, costed, or found.
2
Summary progress is earned, not typed
Fix the work face, not the summary. Overrides are visible to everyone.
3
Blocked never means stuck
Every block offers the legitimate route — archive, or a change request.
4
Read the impact preview
It is the last moment before nine locations and forty-six records move.
5
The structure is a commercial document
It is what your monthly application is valued against. Treat it that way.
Questions — and then into the sandbox.
Notes: Close by handing out the quick reference cards: reading a code, before you move a node, blocked deletion, monthly check, raising a change request, roll-up methods, status meanings.