## Site Data
SITE DATA — Common Parameters (feeds all build-up sheets)
Yellow = input. Items marked TO VERIFY must be checked against drawings before tender submission.
Ref | Parameter | Value | Unit | Status
P01 | Site perimeter (hoarding line) | 130 | m | TO VERIFY
P02 | Building footprint | 800 | m2 | Given
P03 | Building perimeter | 115 | m | TO VERIFY
P04 | Storeys above ground | 10 | no | Given
P05 | Building height | 36 | m | TO VERIFY
P06 | Facade area (P03 x P05) | 4140 | m2 | Calculated
P07 | Programme duration | 18 | months | Assumed
P08 | Structure phase duration | 10 | months | Assumed
P09 | Scaffold rental duration | 12 | months | Assumed
P10 | Peak workforce | 80 | no | Assumed
P11 | Floors incl. roof (edge protection) | 11 | no | Given
P12 | Gross floor area (P02 x P04) | 8000 | m2 | Calculated

## Preliminaries
PRELIMINARIES & GENERAL (Z) — Fully Built-Up
10-Storey School, Phnom Penh ¦ USD ¦ 18-month programme ¦ Yellow = input ¦ Green = linked from build-up / Site Data sheets
Code | Description | Unit | Qty | Rate ($) | Amount ($) | Remarks
Z.01 | TEMPORARY WORKS
Z.01.01 | Site Preparation — build-ups in sheet "BU Z.01.01"
Z.01.01.01 | Mobilization | Item | 1 | 10500 | 10500 | Trips + setup labor + yard
Z.01.01.02 | Demobilization & site clearance | Item | 1 | 6460 | 6460 | Trips out + reinstatement
Z.01.01.03 | Temporary access & roads | Item | 1 | 7400 | 7400 | Road + hardstand areas
Z.01.01.04 | Setting out & ongoing survey works | Month | 18 | 400 | 7200 | Instrument + consumables + checks
Z.01.01.05 | Site signage & project board | Item | 1 | 800 | 800 | Board + safety signage
Z.01.01.06 | Traffic management & road occupation | Item | 1 | 3000 | 3000 | Flagmen + permits + equipment
Z.01.02 | General Protection — build-ups in sheet "BU Z.01.02"
Z.01.02.01 | Temporary fencing & hoarding | Item | 1 | 7950 | 7950 | Site perimeter x rate/m + gates
Z.01.02.02 | Temporary sheet pile, length 6m | m | 95 | 180 | 17100 | Rate/m = drive/extract + rental. DELETE from CS BoQ (double count)
Z.01.02.03 | Safety net to building perimeter | Item | 1 | 6000 | 6000 | Net area x rate + labor
Z.01.02.04 | Edge protection & handrails | Floor | 11 | 700 | 7700 | Rate/floor = perimeter x rail rate
Z.01.02.05 | Protection of completed works | Item | 1 | 4000 | 4000 | Sheeting area + sundries
Z.01.02.06 | Monsoon protection & site drainage | Month | 18 | 250 | 4500 | Pumps + channels + labor
Z.01.02.07 | Dewatering during substructure | Month | 4 | 900 | 3600 | Pumps + fuel + attendance
Z.01.03 | Temporary Building — build-ups in sheet "BU Z.01.03"
Z.01.03.01 | Site office, store & welfare facilities | Month | 18 | 1200 | 21600 | Containers + furniture + shelter
Z.01.03.02 | Temporary worker toilets & sanitation | Month | 18 | 200 | 3600 | Units + servicing
Z.01.03.03 | First aid room & facilities | Item | 1 | 1500 | 1500 | Fit-out + supplies
Z.01.03.04 | Washing bay / wheel wash | Item | 1 | 10100 | 10100 | Pad + pump + maintenance
Z.01.04 | Temporary Site Labor — build-ups in sheet "BU Z.01.04"
Z.01.04.01 | Site cleaning & waste removal | Month | 18 | 602 | 10836 | Crew + skips + tipping
Z.01.04.02 | Final builder's clean at handover | Item | 1 | 3500 | 3500 | GFA x rate + facade clean
Z.01.05 | Machinery & Vertical Transport — build-ups in sheet "BU Z.01.05"
Z.01.05.01 | Tower crane rental | Month | 16 | 3500 | 56000 | Rental + operator + maintenance
Z.01.05.02 | Tower crane foundation, erection, dismantle & test | Item | 1 | 18000 | 18000 | Base + erect + dismantle + test
Z.01.05.03 | Passenger / material hoist rental | Month | 12 | 1500 | 18000 | Rental + operator
Z.01.05.04 | Hoist erection & dismantling | Item | 1 | 4000 | 4000 | Erect + dismantle + cert
Z.01.05.05 | Concrete pump provision | Item |  |  | 0 | DECISION: included in concrete unit rates — do NOT price here
Z.01.05.06 | External scaffolding to facade | m2 | 4140 | 7.2 | 29808 | Qty = facade area (Site Data). Rate/m2 = E&D + rental
Z.01.05.07 | Back-propping / falsework for PT slabs | Floor | 10 | 1200 | 12000 | Props rental + labor per floor
Z.01.06 | Light Equipment & Hand Tools — build-up in sheet "BU Z.01.06"
Z.01.06.01 | Small plant, light equipment & hand tools | Month | 18 | 350 | 6300 | Mixers + tools + consumables
Z.01.07 | Temporary Electrical / Plumbing / Drainage — build-ups in sheet "Temp Utilities"
Z.01.07.01 | Temporary electricity — installation, connection & removal | Item | 1 | 5500 | 5500 | One-time — Temp Utilities A3
Z.01.07.02 | Temporary electricity — consumption & maintenance | Month | 18 | 1258.2624 | 22648.7232 | Load schedule — Temp Utilities A1/A2
Z.01.07.03 | Temporary water — installation, connection & removal | Item | 1 | 1900 | 1900 | One-time — Temp Utilities B1
Z.01.07.04 | Temporary water — consumption & maintenance | Month | 18 | 160.83 | 2894.94 | Demand calc — Temp Utilities B2
Z.01.08 | Safety & Environment Control — build-ups in sheet "BU Z.01.08"
Z.01.08.01 | Health, safety provisions & PPE | Month | 18 | 500 | 9000 | PPE x workforce + training
Z.01.08.02 | Site security incl. guards & CCTV | Month | 18 | 900 | 16200 | Guards + CCTV + lighting
Z.01.08.03 | Material & concrete testing (QA/QC) | Item | 1 | 8000 | 8000 | Cubes + rebar + soil tests
Z.30 | SITE STAFF & OVERHEADS — build-up in sheet "Staff Schedule"
Z.30.01 | Foreign country employees (per Staff Schedule) | Sum |  |  | 63000 | Position x months x rate
Z.30.02 | Local country employees (per Staff Schedule) | Sum |  |  | 132000 | Position x months x rate
Z.30.03 | Other personnel | Item |  |  | 0 | Allow if client requires (e.g. clerk of works support)
Z.30.04 | Welfare expense | Month | 18 | 300 | 5400 | Monthly allowance — input
Z.30.05 | Office supplies expenses | Month | 18 | 200 | 3600 | Monthly allowance — input
Z.30.06 | Communication & travel expense | Month | 18 | 250 | 4500 | Monthly allowance — input
Z.30.07 | Social expense | Month | 18 | 150 | 2700 | Monthly allowance — input
Z.30.08 | Taxes & public imposition | Item |  |  | 0 | Carried in Tender Cost Summary (tax line) — do NOT price here
Z.30.09 | Meeting expense | Month | 18 | 100 | 1800 | Monthly allowance — input
Z.30.10 | Miscellaneous expense | Month | 18 | 200 | 3600 | Monthly allowance — input
Z.50 | DESIGN EXPENSES — build-ups in sheet "BU Z.50"
Z.50.01 | Shop drawings | Item | 1 | 10000 | 10000 | Draftsmen man-months + printing
Z.50.02 | As-built drawings | Item | 1 | 6000 | 6000 | Draftsman man-months + printing
Z.50.03 | Temporary works design | Item | 1 | 5000 | 5000 | Crane base + shoring + back-prop design
Z.70 | RISKS AND OPPORTUNITIES
Z.70.01 | Risk allowance | Item |  |  | 0 | Carried in Tender Cost Summary risk line — do NOT price here
| Subtotal Z.01 — TEMPORARY WORKS |  |  |  | 347597.6632
| Subtotal Z.30 — SITE STAFF & OVERHEADS |  |  |  | 216600
| Subtotal Z.50 — DESIGN EXPENSES |  |  |  | 21000
| Subtotal Z.70 — RISKS AND OPPORTUNITIES |  |  |  | 0
| TOTAL PRELIMINARIES & GENERAL (Z) |  |  |  | 585197.6632
ITEMS RELOCATED OUT OF PRELIMINARIES (now under Section X — Authority / Insurance)
X.02 | Insurance (CAR / third party) — was Z.11 |  |  |  | 12000 | Price under Budget Code Section X, not Z
X.02 | Performance bond / guarantees — was Z.12 |  |  |  | 6000 | Price under Budget Code Section X, not Z
ASSUMPTION REGISTER NOTES:
1. Every rate is now formula-linked to a build-up sheet (BU Z.xx.xx / Staff Schedule / Temp Utilities) — no typed lump sums remain.
2. All build-up input rates are Phnom Penh benchmarks — replace yellow cells with actual quotations before submission.
3. Site Data parameters marked TO VERIFY (perimeters, height) must be measured from drawings; facade & GFA recalculate automatically.
4. Temporary sheet piles priced ONCE (Z.01.02.02) — remove "Temperary Protection" lines from CS BoQ measured works (double count).
5. Concrete pump is included in concrete unit rates; taxes & risk are carried in the Tender Cost Summary.
6. Utility rates split fixed vs monthly for prolongation claims; crane 16 months, hoist 12 months, scaffold rental 12 months.

## Staff Schedule
SITE STAFF SCHEDULE — Feeds Z.30.01 / Z.30.02 in Preliminaries
10-Storey School Building, Phnom Penh — 18-month programme. Yellow = input.
No. | Position | Origin | Persons | Months | Monthly Rate ($) | Total ($)
1 | Project Manager | Foreign | 1 | 18 | 3500 | 63000
2 | Site Engineer | Local | 2 | 18 | 1200 | 43200
3 | Quantity Surveyor | Local | 1 | 18 | 1000 | 18000
4 | Safety Officer | Local | 1 | 18 | 800 | 14400
5 | Surveyor (incl. assistant) | Local | 1 | 18 | 900 | 16200
6 | General Foreman | Local | 2 | 18 | 700 | 25200
7 | Site Admin / Storekeeper | Local | 1 | 18 | 500 | 9000
8 | Document Controller | Local | 1 | 12 | 500 | 6000
| Subtotal — Foreign staff (→ Z.30.01) |  |  |  |  | 63000
| Subtotal — Local staff (→ Z.30.02) |  |  |  |  | 132000
| TOTAL SITE STAFF |  |  |  |  | 195000

## Temp Utilities
TEMPORARY UTILITIES BUILD-UP — Feeds Z.01.07 in Preliminaries
Yellow = input. Change any input and the Preliminaries rates update automatically.
A. TEMPORARY ELECTRICITY
A1. Monthly Load Schedule (peak structure months)
Equipment | kW | Hrs/day | Days/month | kWh/month
Tower crane | 30 | 6 | 26 | 4680
Passenger / material hoist | 15 | 5 | 26 | 1950
Bar bender & cutter | 6 | 5 | 26 | 780
Concrete vibrators (4 no.) | 6 | 3 | 20 | 360
Welding sets (2 no.) | 10 | 3 | 20 | 600
Water pumps | 3 | 4 | 26 | 312
Site office (AC, IT, lighting) | 5 | 9 | 26 | 1170
Site & tower lighting | 4 | 11 | 30 | 1320
Total peak consumption |  |  |  | 11172
A2. Monthly Cost Calculation
EDC tariff ($/kWh) | 0.16
Peak monthly cost | 1787.52
Diversity factor (programme average / peak) | 0.62
Average monthly consumption cost | 1108.2624
Electrician maintenance ($/month) | 150
MONTHLY RATE → Z.01.07.02 | 1258.2624
A3. One-Time Installation & Removal
Description | Amount ($)
EDC connection fee & deposit | 1500
Main distribution board (MDB) & meter | 800
Sub-distribution boards (1 per 2 floors × 5) | 750
Cabling & rising mains distribution | 1200
Earthing & protection | 400
Site lighting installation | 600
Removal at completion | 250
ONE-TIME TOTAL → Z.01.07.01 | 5500
B. TEMPORARY WATER
B1. One-Time Installation & Removal
Description | Amount ($)
PPWSA connection & meter | 600
Storage tanks 2 × 5 m³ | 500
Booster pump & piping to floors | 700
Removal at completion | 100
ONE-TIME TOTAL → Z.01.07.03 | 1900
B2. Monthly Demand & Cost
Workers on site (no.) | 80
Liters per worker per day | 40
Working days per month | 26
Domestic use (m³/month) | 83.2
Curing water (m³/month, structure phase) | 40
Blockwork & plaster mixing (m³/month) | 25
Washing bay & dust control (m³/month) | 30
Total demand (m³/month) | 178.2
PPWSA tariff ($/m³) | 0.65
Consumption cost ($/month) | 115.83
Pump running & maintenance ($/month) | 45
MONTHLY RATE → Z.01.07.04 | 160.83

## BU Z.01.01
Z.01.01 SITE PREPARATION — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.01.01 | Mobilization (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Low-bed & truck transport trips (plant in) | 12 | trip | 400 | 4800
Crane lifts for site establishment | 4 | lift | 300 | 1200
Site setup labor | 100 | man-day | 12 | 1200
Utility applications & administration | 1 | lot | 1000 | 1000
Storage yard & hardstand setup | 1 | lot | 1500 | 1500
Survey control points establishment | 1 | lot | 800 | 800
| Build-up total → Z.01.01.01 |  |  | 10500
Z.01.01.02 | Demobilization & site clearance (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Transport trips out (plant removal) | 10 | trip | 400 | 4000
Dismantling labor | 80 | man-day | 12 | 960
Site reinstatement & final clearance | 1 | lot | 1500 | 1500
| Build-up total → Z.01.01.02 |  |  | 6460
Z.01.01.03 | Temporary access & roads (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Laterite/gravel access road | 300 | m2 | 18 | 5400
Hardstand at loading/unloading area | 100 | m2 | 20 | 2000
| Build-up total → Z.01.01.03 |  |  | 7400
Z.01.01.04 | Setting out & ongoing survey works (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Total station & level rental | 1 | mo | 250 | 250
Pegs, paint, consumables | 1 | mo | 60 | 60
Periodic verification survey | 1 | mo | 90 | 90
| Build-up total → Z.01.01.04 |  |  | 400
Z.01.01.05 | Site signage & project board (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Project board 3m x 2m incl. frame | 1 | no | 500 | 500
Safety & directional signage | 1 | lot | 300 | 300
| Build-up total → Z.01.01.05 |  |  | 800
Z.01.01.06 | Traffic management & road occupation (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Flagmen during concrete pours | 60 | man-day | 15 | 900
Road occupation permits | 6 | no | 250 | 1500
Cones, barriers, warning lights | 1 | lot | 600 | 600
| Build-up total → Z.01.01.06 |  |  | 3000

## BU Z.01.02
Z.01.02 GENERAL PROTECTION — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.02.01 | Temporary fencing & hoarding (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Corrugated hoarding 2.4m high on site perimeter | 130 | m | 55 | 7150
Double gates | 2 | no | 400 | 800
| Build-up total → Z.01.02.01 |  |  | 7950
Z.01.02.02 | Temporary sheet pile, length 6m (rate per m)
Component | Qty | Unit | Rate ($) | Amount ($)
Drive & extract (subcontract) | 1 | m | 140 | 140
Rental during excavation (4 months) | 4 | m-mo | 10 | 40
| Build-up total → Z.01.02.02 |  |  | 180
Z.01.02.03 | Safety net to building perimeter (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Net band, 2 lifts rotating up building | 1400 | m2 | 4 | 5600
Installation & shifting labor | 1 | lot | 400 | 400
| Build-up total → Z.01.02.03 |  |  | 6000
Z.01.02.04 | Edge protection & handrails (rate per Floor)
Component | Qty | Unit | Rate ($) | Amount ($)
Guardrail to slab edge (building perimeter) | 115 | m | 5 | 575
Posts, fixing & shifting labor | 1 | floor | 125 | 125
| Build-up total → Z.01.02.04 |  |  | 700
Z.01.02.05 | Protection of completed works (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Floor/lobby/stair protection sheeting | 600 | m2 | 5 | 3000
Corner guards, tapes, miscellaneous | 1 | lot | 1000 | 1000
| Build-up total → Z.01.02.05 |  |  | 4000
Z.01.02.06 | Monsoon protection & site drainage (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Submersible pumps rental | 2 | no | 60 | 120
Sandbags & drainage channels | 1 | mo | 80 | 80
Attendance labor | 1 | mo | 50 | 50
| Build-up total → Z.01.02.06 |  |  | 250
Z.01.02.07 | Dewatering during substructure (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Dewatering pumps rental | 2 | no | 150 | 300
Fuel / power | 1 | mo | 300 | 300
Standby attendance | 1 | mo | 300 | 300
| Build-up total → Z.01.02.07 |  |  | 900

## BU Z.01.03
Z.01.03 TEMPORARY BUILDING — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.03.01 | Site office, store & welfare (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Office containers | 3 | no | 250 | 750
Store container | 1 | no | 150 | 150
Furniture, AC, IT (amortized) | 1 | mo | 200 | 200
Workers shelter / canteen | 1 | mo | 100 | 100
| Build-up total → Z.01.03.01 |  |  | 1200
Z.01.03.02 | Temporary worker toilets (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Portable toilet units | 4 | no | 35 | 140
Servicing & consumables | 1 | mo | 60 | 60
| Build-up total → Z.01.03.02 |  |  | 200
Z.01.03.03 | First aid room & facilities (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Room fit-out | 1 | lot | 800 | 800
Equipment & initial supplies | 1 | lot | 700 | 700
| Build-up total → Z.01.03.03 |  |  | 1500
Z.01.03.04 | Washing bay / wheel wash (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
RC pad & sediment pit | 1 | lot | 4500 | 4500
Pump & water recycling system | 1 | lot | 1500 | 1500
Hoses & equipment | 1 | lot | 500 | 500
Maintenance & desilting over programme | 18 | mo | 200 | 3600
| Build-up total → Z.01.03.04 |  |  | 10100

## BU Z.01.04
Z.01.04 TEMPORARY SITE LABOR — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.04.01 | Site cleaning & waste removal (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Cleaning laborers | 26 | man-day | 12 | 312
Waste skip hire | 2 | no | 120 | 240
Tipping fees | 1 | mo | 50 | 50
| Build-up total → Z.01.04.01 |  |  | 602
Z.01.04.02 | Final builder's clean at handover (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Builder's clean on GFA | 8000 | m2 | 0.35 | 2800
Glass & facade cleaning | 1 | lot | 700 | 700
| Build-up total → Z.01.04.02 |  |  | 3500

## BU Z.01.05
Z.01.05 MACHINERY & VERTICAL TRANSPORT — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.05.01 | Tower crane rental (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Tower crane rental | 1 | mo | 2800 | 2800
Operator & rigger | 1 | mo | 600 | 600
Maintenance & spares | 1 | mo | 100 | 100
| Build-up total → Z.01.05.01 |  |  | 3500
Z.01.05.02 | Tower crane foundation, erection, dismantle & test (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
RC foundation base | 25 | m3 | 220 | 5500
Erection incl. mobile crane hire | 1 | lot | 6000 | 6000
Dismantling | 1 | lot | 4500 | 4500
Load test & certification | 1 | lot | 2000 | 2000
| Build-up total → Z.01.05.02 |  |  | 18000
Z.01.05.03 | Passenger / material hoist rental (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Hoist rental | 1 | mo | 1200 | 1200
Operator | 1 | mo | 300 | 300
| Build-up total → Z.01.05.03 |  |  | 1500
Z.01.05.04 | Hoist erection & dismantling (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Erection & base | 1 | lot | 2200 | 2200
Dismantling | 1 | lot | 1300 | 1300
Test & certification | 1 | lot | 500 | 500
| Build-up total → Z.01.05.04 |  |  | 4000
Z.01.05.06 | External scaffolding to facade (rate per m2)
Component | Qty | Unit | Rate ($) | Amount ($)
Erection & dismantling | 1 | m2 | 3 | 3
Rental over scaffold duration (P09 months) | 12 | m2-mo | 0.35 | 4.2
| Build-up total → Z.01.05.06 |  |  | 7.2
Z.01.05.07 | Back-propping / falsework for PT slabs (rate per Floor)
Component | Qty | Unit | Rate ($) | Amount ($)
Adjustable props rental (400 no x 2-month cycle) | 800 | prop-mo | 1.2 | 960
Install & strike labor | 20 | man-day | 12 | 240
| Build-up total → Z.01.05.07 |  |  | 1200

## BU Z.01.06
Z.01.06 LIGHT EQUIPMENT & HAND TOOLS — Build-Up
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.06.01 | Small plant, light equipment & hand tools (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Concrete mixers | 2 | no | 50 | 100
Cutting & grinding equipment | 1 | mo | 80 | 80
Power tools replacement allowance | 1 | mo | 100 | 100
Consumables (discs, bits, blades) | 1 | mo | 70 | 70
| Build-up total → Z.01.06.01 |  |  | 350

## BU Z.01.08
Z.01.08 SAFETY & ENVIRONMENT CONTROL — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.01.08.01 | Health, safety provisions & PPE (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
PPE issue & replacement (per peak workforce) | 80 | worker | 4 | 320
First-aid consumables | 1 | mo | 30 | 30
Toolbox training & safety officer support | 1 | mo | 100 | 100
Safety signage & miscellaneous | 1 | mo | 50 | 50
| Build-up total → Z.01.08.01 |  |  | 500
Z.01.08.02 | Site security incl. guards & CCTV (rate per Month)
Component | Qty | Unit | Rate ($) | Amount ($)
Security guards (day/night rotation) | 3 | no | 250 | 750
CCTV system (amortized) | 1 | mo | 100 | 100
Security lighting power | 1 | mo | 50 | 50
| Build-up total → Z.01.08.02 |  |  | 900
Z.01.08.03 | Material & concrete testing (QA/QC) (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Concrete cube test sets | 300 | set | 15 | 4500
Rebar tensile tests | 40 | no | 30 | 1200
Soil / compaction tests | 1 | lot | 800 | 800
Other / miscellaneous tests | 1 | lot | 1500 | 1500
| Build-up total → Z.01.08.03 |  |  | 8000

## BU Z.50
Z.50 DESIGN EXPENSES — Build-Ups
Yellow = input (Phnom Penh benchmarks — replace with quotations). Green = linked from Site Data.
Z.50.01 | Shop drawings (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Draftsmen (2 no. x 10 months) | 20 | man-mo | 450 | 9000
Plotting & printing | 1 | lot | 1000 | 1000
| Build-up total → Z.50.01 |  |  | 10000
Z.50.02 | As-built drawings (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Draftsman (1 no. x 10 months) | 10 | man-mo | 500 | 5000
Printing & binding | 1 | lot | 1000 | 1000
| Build-up total → Z.50.02 |  |  | 6000
Z.50.03 | Temporary works design (total per Item)
Component | Qty | Unit | Rate ($) | Amount ($)
Crane base design & check | 1 | lot | 1500 | 1500
Sheet pile / shoring design | 1 | lot | 1500 | 1500
Back-propping & formwork scheme | 1 | lot | 1500 | 1500
Documentation & submissions | 1 | lot | 500 | 500
| Build-up total → Z.50.03 |  |  | 5000

## Budget Code
BUDGET CODE
Section | Code |  | Description
Early Work | A.00 | A.Early Work
Topography Survey | A.01 | A.01.Topography Survey
Soil Investigation | A.02 | A.02.Soil Investigation
Mine / UXO Clearance | A.03 | A.03.Mine / UXO Clearance
Soil Leveling | A.04 | A.04.Soil Leveling
Demolition | A.05 | A.05.Demolition
Cleaning | A.06 | A.06.Cleaning
Repair exiting services | A.07 | A.07.Repair exiting services
Renovation | A.08 | A.08.Renovation
Sub Structure | B.00 | B.0.Sub Structure
Piling Work | B.01 | B.01.Piling Work
Basement | B.02 | B.02.Basement
Ground Floor | B.03 | B.03.Ground Floor
Super structure | B.04 | B.04.Super structure
Architecture | C.00 | C.0.Architecture
Exterior Wall and Partition | C.01 | C.01.Exterior Wall and Partition | Masonry Wall, Dry Wall, Glass partition
Exterior Wall Finishes | C.02 | C.02.Exterior Wall Finishes | Plastering, painting, cladding, molding
Exterior Door | C.03 | C.03.Exterior Door | Wooden door, Glass door, Steel door
Exterior Window and Louver | C.04 | C.04.Exterior Window and Louver | Glass window, window fence, steel louver
Exterior floor | C.05 | C.05.Exterior floor | Screeding, floor tiling, hardening, Waterproofing
Exterior soffit | C.06 | C.06.Exterior soffit | Soffit slab finish
Exterior Stair Ramp | C.07 | C.07.Exterior Stair Ramp | Barrier, ramp
Roofing | C.08 | C.08.Roofing
Interior Wall and Partition | C.09 | C.09.Interior Wall Partition | Masonry Wall, Dry Wall, Glass partition
Interior Doors | C.10 | C.10.Interior Door /Windows and Louvers | Steel door, wooden door, glass door
Special installation | C.11 | C.11.Special installation | LPG Gas
Exterior Finishes | C.12 | C.12.Exterior Finishes | Plastering, painting, cladding, molding
Interior Finish | D.00 | D.0.Interior Finish
Interior Wall Finishes | D.01 | D.01.Interior Wall Finishes | Wall tiling, Plastering, Painting, Skirting, Wall Marble
Interior Floor Finishes | D.02 | D.02.Interior Floor Finishes | Screeding, floor tiling, Wooden Flooring, Marble flooring, Carpet Flooring, Epoxy Flooring, waterproofing, Floor strip divider
Ceiling Finishes | D.03 | D.03.Ceiling Finish | Suspended Ceiling
Fittings, furnishings and equipment | E.00 | E.0.Fitting, furnishings and equipment
General Fitting | E.01 | E.01.General Fitting
Domestic Kitchen Fitting | E.02 | E.02.Domestic Kitchen Fitting
Special purpose Fitting | E.03 | E.03.Special purpose Fitting
Signage | E.04 | E.04.Signage
Art | E.05 | E.05.Art
Non-Mechanical and Non Electrical Equipement | E.06 | E.06.Non-Mechanical and Non Electrical Equipement
Internal Planting | E.07 | E.07.Internal Planting
Bird and Vermin Control | E.08 | E.08.Bird and Vermin Control
Services | F.00 | F.0.Services
Sanitary Installations | F.01 | F.01.Sanitary Installations
AIR-CONDITIONAL SYSTEM | F.02 | F.02.AC SYSTEM
MECHANICAL VENTILATION SYSTEM | F.03 | F.03.MECHANICAL VENTILATION SYSTEM (MV)
MV DISTRIBUTION SYSTEM | F.04 | F.04.MV DISTRIBUTION SYSTEM
ELECTRICAL SYSTEM | F.05 | F.05.ELECTRICAL SYSTEM
ELV INSTALLATION | F.06 | F.06.ELV INSTALLATION
PLUMBING SYSTEM | F.07 | F.07.PLUMBING SYSTEM
FIRE FIGHTING SYSTEM | F.08 | F.08.FIRE FIGHTING SYSTEM
Specialist Installations | F.09 | F.09.Specialist Installations
VERTICAL TRANSPORTATION SYSTEM | F.10 | F.10.VERTICAL TRANSPORTATION SYSTEM
External Work | G.00 | G.External Work
Site preparation | G.01 | G.01.Site preparation
Roads, path, paveing Surfacing | G.02 | G.02.Roads, path, paveing Surfacing
Land scape | G.03 | G.03.Land scape
Fence Railing wall | G.04 | G.04.Fence Railing wall
Exteranal Fixture | G.05 | G.05.Exteranal Fixture
AUTHORITY RELATED , INSURANCE | X.00 | X.0.AUTHORITY RELATED , INSURANCE
CONSTRUCTION PERMIT, OPEN SITE AND CLOSE SITE PERMITS | X.01 | X.01.CONSTRUCTION PERMIT, OPEN SITE AND CLOSE SITE PERMITS
CAR Insurance + DLP Insurance | X.02 | X.02.CAR Insurance + DLP Insurance
DLP 24 Month Budget | X.03 | X.03.DLP 24 Month Budget
E.I.A | X.04 | X.04.E.I.A
Z.0.CONTRACTOR'S PRELIMINARIES / DESIGN / OTHERS | Z.00 | Z.0.CONTRACTOR'S PRELIMINARIES / DESIGN / OTHERS
Temporary Works | Z.01 | Z.01.Temporary Works
Site Preparation | Z.01.01 | Z.01.01.Site Preparation
General Protection | Z.01.02 | Z.01.02.General Protection
Temporary Building | Z.01.03 | Z.01.03.Temporary Building
Temporary site labor | Z.01.04 | Z.01.04.Temporary site labor
Machinery | Z.01.05 | Z.01.05.Machinery
Light equiment hand tools | Z.01.06 | Z.01.06.Light equiment hand tools
Temporary Elecrical Plumbing Drainage | Z.01.07 | Z.01.07.Temporary Elecrical Plumbing Drainage
Safe and environment control | Z.01.08 | Z.01.08.Safe and environment control
Foreign Country Employee | Z.30.01 | Z.30.01.Foreign Country Employee
Local Country employee | Z.30.02 | Z.30.02.Local Country employee
Other personnel | Z.30.03 | Z.30.03.Other personnel
Welfare expense | Z.30.04 | Z.30.04.Welfare expense
office supplies expenses | Z.30.05 | Z.30.05.office supplies expenses
Communication & Travel expense | Z.30.06 | Z.30.06.Communication & Travel expense
Social expense | Z.30.07 | Z.30.07.Social expense
Taxes & Public imposition | Z.30.08 | Z.30.08.Taxes & Public imposition
Meeting expense | Z.30.09 | Z.30.09.Meeting expense
Miscellaneous expense | Z.30.10 | Z.30.10.Miscellaneous expense
Design expenses | Z.50 | Z.50.Design expenses
Risks and Opportunities | Z.70 | Z.70.Risks and Opportunities