DCOS

Digital Construction Operating System

GFA, Site Area & Cost per m²

Measurement & Reporting Guideline for Quantity Surveyors

| Document Ref | DCOS-QS-GDL-001 |
| --- | --- |
| Version | V1.0 — Initial Issue |
| Related Documents | SOP-QS-001 R3; DCOS-QS-DDS-001 V2.0; DCOS-QS-RPT-001; Measurement Rules (Ch.1 = this convention) |
| Issue Date | 2026-07-16 |
| Owner | QS Manager (convention authority) / Commercial Director (approval) |
| Applies To | All QS Engineers, Estimators, and anyone producing a cost/m² figure in DCOS |
| Classification | Internal — Controlled Document |

# Table of Contents

Table of Contents	2

1. Purpose & Rule of Use	3

2. Definitions	3

3. GFA Measurement Convention (House Rules)	4

4. Site Area Convention	4

5. Cost Allocation Rules — What Divides by What	4

6. Case A — Building WITHOUT Basement	6

7. Case B — Building WITH Basement	6

8. Case C — External Works	7

9. Case D — Combined Project & the Standard Final Cost Summary	8

10. Common Mistakes & Validation Checklist	8

11. Entering the Data in DCOS	9

12. Approval & Revision	9

# 1. Purpose & Rule of Use

Cost per square metre ($/m²) is the most-used benchmark in construction: it sanity-checks a tender, compares projects, and is the number every client and director asks for first. But $/m² is only meaningful if everyone measures the same way. Two QS engineers using different area conventions will report different $/m² for the same building — and both will look wrong.

This guideline fixes ONE house convention for measuring Gross Floor Area (GFA) and Site Area, and ONE standard method for allocating cost to each, so every DCOS cost summary is comparable across projects, years, and staff.

The Governing Principle GFA measures FLOOR PLATES, not cost items. Piles have cost but no floor — they divide by the building's GFA. A roof has area but no floor — its cost also divides by GFA. External works have neither building cost nor building floor — they divide by SITE AREA and never enter the building $/m².

Rule of use: no cost/m² figure may be issued in a tender review, management report, or client document unless it is calculated per this guideline. Deviations require QS Manager approval recorded in writing.

# 2. Definitions

| Term | Definition |
| --- | --- |
| GFA (Gross Floor Area) | Total area of all counted floor plates, measured to the OUTSIDE face of external walls, per the convention in Section 3. Includes internal walls, columns, circulation, and shafts. |
| GFA above ground | GFA of all floors at or above ground level, including counted roof-level rooms. |
| GFA basement | GFA of all floors below ground level. Always recorded separately from above-ground GFA. |
| GFA total | GFA above ground + GFA basement. |
| Site Area | Total land area of the project site within the legal boundary, per title/survey plan. |
| Building footprint | Ground-level area covered by the building. Used for site coverage checks — NOT a cost denominator. |
| Building cost | Contract cost of the building works only — excludes external works and land. |
| External works cost | Cost of works outside the building line: roads, boundary, drainage, landscape, guard house, site utilities. |
| Elemental cost/m² | Cost of one trade/element (substructure, frame, finishes, MEP...) ÷ GFA total. |
| Blended $/m² | Total building cost ÷ GFA total (basement mixed in). |
| Split $/m² | Above-ground cost ÷ above-ground GFA reported separately from basement cost ÷ basement GFA. |

# 3. GFA Measurement Convention (House Rules)

Measure each floor plate from the architectural floor plans to the OUTSIDE face of external walls. Then apply the inclusion table:

| Element | Count in GFA | Rule |
| --- | --- | --- |
| Typical enclosed floor | 100% | Full plate to outside face of external walls |
| Basement floor | 100% | Full plate — recorded as GFA basement, never mixed silently into above-ground |
| Covered balcony / open-sided corridor / covered walkway / canopy over entrance | 50% | Half area — covered but not enclosed |
| Uncovered terrace, open roof deck, open parking on grade | 0% | No enclosure — excluded |
| Lift shafts, stair cores, service risers | 100% | Counted at EVERY floor they pass through |
| Double-height void (lobby, atrium, auditorium airspace) | Once | Counted once at the lowest floor; the void opening above counts 0% |
| Enclosed roof-level rooms (lift motor room, tank room, plant room, stair bulkhead) | 100% | They are floor plates — count them in above-ground GFA |
| Roof structure, waterproofing, parapets | 0% | Not a floor — cost divides by GFA total |
| Piles, pile caps, footings, ground beams | 0% | Not a floor — cost shows as the Substructure elemental line ÷ GFA total |
| External works, boundary walls, site roads | 0% | Different denominator — Site Area (Section 4) |

Three Non-Negotiable Rules 1. GFA is ENTERED from drawings, never derived. Do not sum it from BOQ items or room areas — room-by-room totals miss walls, circulation, and shafts. 2. GFA is entered per LEVEL in DCOS and rolls up to building and project (Section 11). Parents are read-only. 3. When the design changes (added floor, changed footprint), the GFA is revised with a reason and the change is audit-logged. Historical $/m² snapshots keep the GFA that was current at their time.

# 4. Site Area Convention

- Site Area = legal land area from the title deed / survey plan, entered once at the PROJECT node.

- If the contract covers only part of a larger site, use the defined works-area boundary from the contract drawings and note the source.

- Site Area is the denominator for external works $/m² ONLY. It never divides building cost.

- Building footprint may be recorded for site-coverage ratio (footprint ÷ site area) but is not a cost denominator.

# 5. Cost Allocation Rules — What Divides by What

| Cost | Denominator | Shown as |
| --- | --- | --- |
| Building works total (incl. piling, roof, prelims share) | GFA total | Building $/m² (blended) |
| Above-ground building works | GFA above ground | Split reporting line 1 |
| Basement works (excavation, retaining, waterproofing, basement structure) | GFA basement | Split reporting line 2 |
| Substructure (piling, pile caps, ground beams) | GFA total | Elemental line inside building $/m² |
| Each trade/element (frame, finishes, MEP, prelims) | GFA total | Elemental $/m² table |
| External works | SITE AREA | External $/m² site — SEPARATE line, never inside building $/m² |

Building $/m2 = Building cost ÷ GFA_total Elemental $/m2 = Element cost ÷ GFA_total Basement $/m2 = Basement cost ÷ GFA_basement External $/m2 (site) = External cost ÷ Site_Area NEVER: (Building + External) ÷ GFA as the headline building benchmark

A deep-piled project shows a HIGH substructure elemental line — that is the correct, visible signal. Hiding foundation cost by inflating area is the classic mistake this guideline exists to stop.

# 6. Case A — Building WITHOUT Basement

Project: 10-storey school building. Contract for building works only = $3,595,200 (external works excluded, handled in Case C).

### Step 1 — Measure GFA per level

| Level | Plate area | Rule applied | Counted |
| --- | --- | --- | --- |
| Ground floor | 850 m² | 100% | 850 |
| Levels 2–10 (9 floors) | 9 × 850 m² | 100% | 7,650 |
| Roof: lift motor room + tank room | 60 m² | Enclosed roof rooms 100% | 60 |
| Roof: open deck | 400 m² | Uncovered 0% | 0 |
| GFA above ground = GFA total |  |  | 8,560 m² |

### Step 2 — Compute the benchmark

Building $/m2 = 3,595,200 ÷ 8,560 = $420.00 /m2

### Step 3 — Elemental breakdown (÷ GFA total 8,560)

| Element | Cost (USD) | $/m² |
| --- | --- | --- |
| Substructure (piling, pile caps, ground beams) | 428,000 | 50.00 |
| Superstructure (concrete frame) | 1,112,800 | 130.00 |
| Architectural works & finishes | 1,027,200 | 120.00 |
| MEP services | 856,000 | 100.00 |
| Preliminaries | 171,200 | 20.00 |
| Building total | 3,595,200 | 420.00 |

Note how the piling cost is fully visible as the $50/m² substructure line — divided by the whole GFA, contributing zero area of its own.

# 7. Case B — Building WITH Basement

Same school, now with one basement level of 850 m² (parking + plant). Basement works (excavation, retaining, waterproofing, basement structure) = $722,500. Illustrative — in reality substructure design also changes; this example isolates the area logic.

### Step 1 — GFA split

| Component | Area |
| --- | --- |
| GFA above ground (Case A) | 8,560 m² |
| GFA basement (1 × 850) | 850 m² |
| GFA total | 9,410 m² |

### Step 2 — Report BOTH ways (mandatory)

| Reporting line | Calculation | Result |
| --- | --- | --- |
| Above-ground $/m² | 3,595,200 ÷ 8,560 | 420.00 |
| Basement $/m² | 722,500 ÷ 850 | 850.00 |
| Blended building $/m² | (3,595,200 + 722,500) ÷ 9,410 = 4,317,700 ÷ 9,410 | 458.84 |

Why split reporting is mandatory The basement costs 850 $/m² — roughly double a typical floor. If you publish only the blended 458.84, this project looks 9% more expensive than the no-basement school at 420.00, and someone will wrongly conclude the building got costlier. Split reporting shows the truth: the above-ground building is IDENTICAL at 420.00; the basement is a separate, expensive component. Blended is for portfolio comparison; split is for understanding.

# 8. Case C — External Works

Site area 4,500 m² (title deed). External works: boundary wall, internal road & parking, storm drainage, landscaping, guard house = $180,000.

External works $/m2 (site) = 180,000 ÷ 4,500 = $40.00 /m2 of site WRONG: adding 180,000 into the building numerator (4,317,700 + 180,000) ÷ 9,410 = 477.97 ← NOT the building benchmark

- External works relate to the land, not the floor plates. A small building on a large site would be unfairly penalized if external cost divided by GFA.

- The 477.97 all-in figure MAY be shown as a memo line labelled “whole project ÷ GFA” — but never as “building $/m²”, and never used to benchmark against building-only figures.

# 9. Case D — Combined Project & the Standard Final Cost Summary

The full project = Case B building + Case C external works. Total contract $4,497,700. Every project cost summary issued from DCOS must follow this exact format:

### STANDARD FINAL COST SUMMARY (mandatory format)

| No. | Description | Cost (USD) | Denominator | $/m² |
| --- | --- | --- | --- | --- |
| 1 | Building works — above ground | 3,595,200 | 8,560 m² GFA | 420.00 |
| 2 | Building works — basement | 722,500 | 850 m² GFA | 850.00 |
| A | Building subtotal (blended) | 4,317,700 | 9,410 m² GFA | 458.84 |
| 3 | External works | 180,000 | 4,500 m² site | 40.00 |
| B | TOTAL CONTRACT | 4,497,700 | — | — |
| memo | Whole project ÷ GFA (memo only — not a benchmark) | 4,497,700 | 9,410 m² GFA | 477.97 |

Below the summary, attach the elemental table (Section 6 Step 3 format) computed on GFA total, and state the GFA convention reference: “Areas per DCOS-QS-GDL-001 V1.0”. Client-facing versions show sell-side costs only, per the firewall rule (SOP-QS-05A / RPT-001 G7).

### Reading the summary — what each line answers

| Line | Question it answers |
| --- | --- |
| Line 1 (420.00) | Is this building's construction economical? Compare with other above-ground buildings of the same type. |
| Line 2 (850.00) | What did going underground cost us? Compare basement decisions across projects. |
| Line A (458.84) | Portfolio blended rate — for company-wide $/m² statistics. |
| Line 3 (40.00) | Site development intensity — compare against site area, not building size. |
| Memo (477.97) | Answering a director who asks “total divided by area” — labelled so it is never mistaken for the building benchmark. |

# 10. Common Mistakes & Validation Checklist

### The five classic mistakes

- Counting foundations or roof structure as area. They are cost, not floor plate — 0% area, full cost ÷ GFA total.

- Blending the basement silently. Always report split + blended; a blended-only figure misleads every comparison.

- Dividing external works by GFA. External works ÷ Site Area, always.

- Deriving GFA from BOQ or room areas. GFA is measured from floor plans to the outside face — room sums miss walls, shafts, circulation.

- Changing GFA without revision control. A GFA edit silently changes every historical-looking benchmark. Revise with reason; snapshots keep their original GFA.

### Checklist before issuing any $/m² figure

- GFA entered per level, from the current drawing revision, convention table applied and noted.

- Basement levels flagged; above/below split available.

- Site area entered at project node with source (title deed / survey ref).

- External works WBS branch excluded from building numerator.

- No level has cost > 0 with GFA = 0 (DCOS warns — do not ignore the warning).

- Summary follows the Section 9 mandatory format; convention reference cited.

- Client version contains sell-side figures only (firewall check).

# 11. Entering the Data in DCOS

- Open the WBS tree → select each Level node → Quantities panel → add metric GFA with value (m²), source = drawing revision reference.

- Basement levels: ensure the node is typed/flagged as below-ground so the split reports automatically.

- Roof-level enclosed rooms: enter their 60 m² (etc.) as GFA on the roof level node — the open deck is simply not entered.

- Select the Project node → add metric SITE_AREA with the title-deed area and source reference.

- Building and project GFA totals roll up automatically — parent values are read-only.

- Design change: edit the level GFA → the system requires a reason and logs the change; existing S-curve/EVM snapshots retain their original GFA.

- The QS Dashboard “Cost/m²” card and the Final Cost Summary report (RPT series) read ONLY these entered values — if the card shows “no area data”, the input above is missing.

System reference: metrics are stored in wbs_node_quantities (metric_code GFA / SITE_AREA); feature specification FS-QS-012 in DDS-001 V2.0.

# 12. Approval & Revision

The 50% balcony treatment, void rules, and split-reporting mandate are HOUSE DECISIONS. They bind all staff once approved below. Amendments follow document control (new version, reason, re-approval).

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| QS Manager (convention authority) |  |  |  |
| Commercial Director (approver) |  |  |  |

| Version | Date | Description | Author |
| --- | --- | --- | --- |
| V1.0 | 2026-07-16 | Initial issue — GFA/site conventions, cost allocation rules, worked Cases A–D, standard final cost summary format, DCOS entry procedure | DCOS Commercial Team |

End of Document — DCOS-QS-GDL-001 V1.0