## Slide 1
DCOS · TRAINING GUIDE SUMMARY
Quantity Surveying Module
How the commercial chain works, what each role does, and the habits that keep
the numbers right — from tender price to final account.
Doc 12 — DCOS-QS-12-TRN · R1
Notes: Welcome. This deck summarises the training guide. Full detail is in doc 12; the SOP set always governs where they differ.

## Slide 2
The commercial chain
Every figure in the module comes from the step before it — nothing is typed twice.
Price list
what we buy
›
Unit rate
what one unit costs
›
BOQ
qty × rate
›
Budget
locked baseline
›
Cost + VO
what we spend
›
IPC
what we bill
›
Final account
what we settle
Change a price while the tender is draft and everything downstream recalculates. Lock the BOQ at award and the chain becomes the contract baseline.
71.87
net unit rate per m³
40,661.70
payment due this claim
+1,248.75
net buy-out to date
The same worked figures follow you through every module of this course.
Notes: Emphasise: the chain is one-directional and automatic. The most common user error is typing a number that the system would have computed.

## Slide 3
Six training paths
Attend the path for your role — not everything applies to everyone.
A
Estimator
1 day · T1 · T2 · T3
B
Project QS
2 days · T1 · T4–T7
C
QS Manager
2.5 days · All + T10
D
Procurement
0.5 day · T1 · T8
E
Management
0.5 day · T1 · T9
F
Site requester
2 hours · T1 · T8 (PR)
Notes: Paths are cumulative in difficulty. Site requesters only need two hours; QS Managers need everything plus the approvals module.

## Slide 4
T1
Foundations — the three habits
45 minutes · everyone
1
Check the status badge first
Draft, approved, locked, certified — status decides what you can edit. The system disables rather than fails.
2
Read the computed field
Net rate, variance, payment due are calculated. If you are retyping a number the system produced, stop.
3
Use the override, not a workaround
If a control blocks you there is a documented path with a reason field. Never route around it.
Notes: These three habits prevent the majority of support tickets. Repeat them at the end of every module.

## Slide 5
T2
Price list and unit rates
Build rates from resources — never type a rate.
UR-CON-001 · C25 concrete, per m³
Cement 7.0 bags @ 4.20 +5% wastage
30.87
Sand 0.45 m³ @ 12.00 +5%
5.67
Aggregate 0.90 m³ @ 14.00 +5%
13.23
Labor 0.80 h @ 22.00
17.60
Plant 0.30 h @ 15.00
4.50
Net unit rate
71.87
What to remember
Wastage sits on material lines only.
Productivity divides labor and plant only.
Price is read-only here — edit it in the price list.
Change cement 4.20 → 4.60 and the rate becomes 74.81, with blockwork and plaster moving too.
Exercise: build this rate, confirm 71.87, then change the cement price and watch the cascade.
Notes: Exercise: build this rate from seed data and confirm 71.87, then change the cement price and observe the cascade.

## Slide 6
T3
Tender pricing and revisions
Draft is working space. Finalize freezes everything.
Draft
Edit inputs freely. No revision is created by editing.
›
Final
All input tabs freeze and are snapshotted.
›
New revision
Requires a reason, clones the last, unlocks editing again.
The bid summary chain
Direct + Subcon + Prelims → overhead % → profit % → contingency → risk → VAT = bid price
Risk items are priced individually. Contingency covers the unknown. Never cover the same risk twice.
Notes: Exercise: price a ten-item tender, finalize Revision 1, then handle an addendum as Revision 2 and confirm Revision 1 is untouched.

## Slide 7
T4
Baseline and the margin firewall
Two rates per item. Only one leaves the company.
Internal — QS Manager and above
Cost rate 85.00
Markup: labor 18% · material 8% · plant 12%
Expected margin per item
Buy-out gain and loss
Client-facing — everyone
Sell rate 94.69
Contract value and section totals
Certified amounts and retention
No cost. No markup. No margin.
Client exports do not hide the cost columns — they do not contain them.
Notes: Stress that this is structural, not a permission toggle. There is an automated test that scans client output for restricted fields.

## Slide 8
T5
Cost recording and budget control
Three statuses, one rule about deleting.
Pending
Recorded. Editable. Deletable.
Approved
Verified against documents. Locked.
Paid
Settled. Permanent audit record.
Made a mistake after approval? Post a contra entry referencing the original. Never delete, never edit.
Variance colours — the same bands everywhere
Green
at or under budget
Amber
0 – 5% over
Red
over 5% — act this cycle
Notes: Every cost must carry a BOQ link, otherwise it never appears in variance and the project looks better than it is.

## Slide 9
T6
Variation orders
The approval chain is decided by value and cannot be shortened.
under $5,000
Project Manager
1 step
$5,000 – $50,000
PM → QS Manager
2 steps
$50,000 and above
PM → QS Manager → Director
3 steps
You cannot approve a variation you raised.
Rejection always needs a reason — it goes back to draft.
Approved variations add to the contract sum; they never rewrite locked BOQ lines.
Notes: Exercise: raise VOs of 3,200 / 25,000 / 80,000 and confirm the three chains.

## Slide 10
T7
Interim payment certificate
The most important two hours of the course.
G702 summary — worked example
Original contract sum
280,572.00
Net approved variations
12,400.00
Contract sum to date
292,972.00
Completed and stored
146,486.00
Less retention 5%
7,324.30
Less previous certificates
98,500.00
Current payment due
40,661.70
Rules you cannot break
Over-claiming beyond scheduled value is blocked.
Add approved variations before you submit.
Retention is created by certification — never entered by hand.
Certified value governs. The difference is kept for the final account.
Submit on the contractual date. A late claim is cash you do not recover.
Notes: Exercise: produce IPC 3 and match these figures exactly, then certify and confirm the retention ledger entry appears automatically.

## Slide 11
Retention — deducted automatically, released deliberately
5% held from every certificate, returned in two halves.
Every certificate
5% deducted
created by the system at certification
Practical completion
50% released
on the PC certificate
End of DLP
Balance released
usually 12 months later
A release request must cite the trigger certificate and cannot exceed the outstanding balance.
Notes: Retention is real money and a frequent source of dispute. The ledger is the single record.

## Slide 12
T8
Buying against the baseline
Three checks run on every requisition line.
1
Budget
Is there money left on this BOQ item?
1,740 ≤ 6,120 remaining
Pass
2
Quantity
Have we already bought enough for the scope?
3,580 of 3,675 allowable
97.4%
3
Price
How does it compare to the tender price?
4.35 against baseline 4.20
+3.6%
A red result is not a dead end — request the override with a reason. Every override is reviewed monthly.
Notes: Requesters see the variance chip, not the baseline value itself. Overrides go to the QS Manager.

## Slide 13
T9
Reading the health numbers
Two indices tell management everything about cost and time.
CPI
Cost performance — below 1.00 means we are spending more than we are earning.
SPI
Schedule performance — below 1.00 means we are behind the programme.
1.00 and above
On track — monitor
0.95 – 0.99
Review with the PM
Below 0.85
Escalate to the Director
Cost per m² always includes preliminaries and margin; it excludes VAT, land, fees, loose furniture, and external works.
Notes: If CPI or SPI is above 1.10, treat it as a data-quality flag and verify before reporting.

## Slide 14
The month-end sequence
The one week where the whole module comes together.
Day 1–2
Cut off costs; confirm deliveries and timesheets posted
Day 2–3
Measure completed work; update progress for earned value
Day 3–4
Prepare claim items; check over-claim; add approved variations
Day 4
Internal review, then submit the claim to the client
Day 5
S-curve snapshot; refresh EVM; run the buy-out report
Day 5–7
Client review and certification; retention created automatically
Day 7
Management review — variance, health, cash flow, overrides
Notes: Day 4 is the hard deadline. Submit on the contractual date even if internal review is imperfect — adjust in the next claim.

## Slide 15
Quick reference
Print this for your desk
Never
Edit a locked BOQ
Enter retention by hand
Delete an approved cost record
Send cost or margin figures to a client
Approve something you raised yourself
Always
Link every cost and PR line to a BOQ item
Give a reason on every rejection and override
Add approved variations before claiming
Submit the claim on the contract date
Check the status badge before editing
VO routing <5k PM · 5k-50k PM + QSM · 50k+ PM + QSM + Director
Retention 5% · 50% at PC · 50% at DLP
Notes: Hand out the printed card at the end of every session.

## Slide 16
COMPETENCY AND SUPPORT
You are signed off when you can
do it without the trainer.
Floor support during go-live · a named super-user in every project team ·
quarterly refreshers on the month-end sequence.
Where the truth lives: the SOP set governs whenever training material and procedure disagree.
Notes: Close by naming the super-user for each team and the date of the first refresher.