DCOS

Digital Construction Operating System

Cost Control → Procurement Integration

Standard Operating Procedure — BOQ Baseline to PR / RFQ / PO

| Document Ref | SOP-QSP-001 |
| --- | --- |
| Version | R1 — Initial Issue |
| Base Documents | SOP-QS-001 R3 (QS Module SOP); FS-QS-001; DCOS Architecture R0 §13 (Procurement); DDS-001 V2.0 |
| Issue Date | 2026-07-16 |
| Owner | Commercial Manager (QS side) / Procurement Manager (procurement side) |
| Applies To | QS, Procurement, Site, Store, and Finance staff on all DCOS projects |
| Classification | Internal — Controlled Document |

# Table of Contents

Table of Contents	2

1. Purpose & Scope	3

2. Definitions	3

3. Integration Golden Rules	3

4. Roles	4

5. SOP-QSP-01 — Procurement Baseline Activation	5

6. SOP-QSP-02 — Purchase Requisition with Baseline Checks	7

6.1 The Three Baseline Checks (per PR line)	7

6.2 Approval Routing Matrix	7

7. SOP-QSP-03 — RFQ & Quotation Comparison vs Baseline	10

8. SOP-QSP-04 — Purchase Order & Budget Commitment	12

9. SOP-QSP-05 — Delivery, Matching & Committed-to-Actual (summary)	14

10. SOP-QSP-06 — Buy-out Reporting & Baseline Maintenance	14

11. Data Linkage Reference	16

12. KPIs & Reports	16

13. RACI	16

14. Document Control	17

Revision History	17

# 1. Purpose & Scope

This SOP defines how the QS Cost Control baseline (the locked BOQ, its price basis, and its derived quantities) controls the procurement chain — Purchase Requisition (PR), Request for Quotation (RFQ), and Purchase Order (PO) — so that every riel of committed spend is checked against the contract cost baseline BEFORE the money is committed, not discovered after.

It covers: activation of the Procurement Baseline at contract award; the three baseline checks applied to every PR line (budget, quantity, price); RFQ quotation comparison against baseline prices; PO issue and budget commitment; the hand-off from committed cost to actual cost at delivery and invoice; and the buy-out gain/loss reporting that closes the loop back to QS.

Out of scope: supplier prequalification, inventory/stock operations after receipt, and subcontract procurement (subcontracts follow SOP-QS-15/16 in SOP-QS-001 R3). Payment processing follows SOP-QS-07.

The Integration Principle The tender told us what everything SHOULD cost (baseline prices), how much of everything we SHOULD need (allowable quantities), and how much money each work item HAS (locked BOQ budget). Procurement's job is to buy within all three. This SOP makes the three limits computable, visible on every PR line, and enforceable by workflow — with a controlled override path, because sites cannot stop for a budget technicality, but every override must leave evidence.

# 2. Definitions

| Term | Definition |
| --- | --- |
| Procurement Baseline | The frozen trio created at contract award: (a) locked BOQ budget per item, (b) baseline unit price per resource (tender Price List snapshot), (c) allowable quantity per resource (BOQ qty × composition × wastage) |
| Allowable Quantity | Maximum quantity of a resource justified by the contract scope: BOQ quantity × unit-rate composition qty_per_unit × (1 + wastage %) |
| Baseline Price | The unit price assumed at tender for a resource — copied read-only onto each PR line at creation |
| Committed Cost | Value of approved, open POs not yet invoiced — reduces remaining budget immediately at PO approval |
| Remaining Budget | BOQ item budget − committed − actual − pending PR value |
| Buy-out Gain/(Loss) | (Baseline price − PO price) × PO quantity, summed per resource/trade/project |
| Three-way Match | PO + Goods Receipt Note (GRN) + Invoice agreement before payment (SOP-QS-07 / SOP-QS-001 R3) |
| Red Route | Override approval path for over-budget or over-variance requests — QS Manager approval with mandatory reason, audit-logged |
| Unbenchmarked Line | A PR line with a budget link but no price-list ancestor (consumables, small tools) — checks 2–3 skipped, flagged in buy-out reporting |

# 3. Integration Golden Rules

1. The Procurement Baseline is frozen at award and READ-ONLY to procurement. An approved Variation Order is the only door that adds budget, items, or quantities. 2. Every PR line must carry a budget link (BOQ item / budget code). No budget link, no submission. 3. Baseline price is copied onto the PR line at creation (snapshot). Later edits anywhere cannot rewrite the benchmark a decision was made against. 4. Budget is consumed in this order: pending PR (soft) → committed at PO approval (hard) → actual at invoice. The same dollar is never counted twice. 5. PO quantity and value may not exceed the approved PR (per line, cumulatively) without re-approval. 6. Blocks always have a controlled override (red route) — never a dead end, never a silent bypass. 7. Every check result, override, and approval is audit-logged with identity, timestamp, and reason.

# 4. Roles

| Role | Responsibility in this SOP |
| --- | --- |
| Requester (Site Engineer / Storekeeper) | Raises PR with budget link; responds to check flags |
| Procurement Officer | Validates PR, runs RFQ, prepares comparison, drafts PO |
| Procurement Manager | Approves PR (procurement side), approves supplier selection, issues PO |
| QS Engineer | Maintains BOQ links, monitors pending/committed against budget |
| QS Manager | Red-route approvals (over-budget, price variance > threshold), buy-out review |
| Project Manager | PR approval per threshold; escalation recipient |
| Finance Officer | Three-way match, invoice recording, payment (per SOP-QS-07) |
| Commercial Manager | Owns the baseline; monthly buy-out and commitment review |

# 5. SOP-QSP-01 — Procurement Baseline Activation

| Who | QS Manager (prepare), Commercial Manager (approve) |
| --- | --- |
| When | Once, at contract award — immediately after BOQ lock (SOP-QS-05) |
| System Path | /dashboard/qs → Procurement Baseline (new) |

### Procedure Steps

- Confirm the BOQ is locked (SOP-QS-05) and the markup set is locked (SOP-QS-05A).

- Click “Activate Procurement Baseline” — the system snapshots three data sets:

- (

- (

- (

- R

- C

- F

### Worked Allowable-Quantity Example (from FS-QS-001 seed)

BOQ: 500 m3 C25 concrete; composition: 7.0 bags cement /m3; wastage 5% Allowable cement = 500 × 7.0 × 1.05 = 3,675 bags

### Workflow Control

Process status flow:

draft (auto-generated) → reviewed → approved (Commercial Manager) → active — revised only via approved VO

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Prerequisites | Activation blocked unless BOQ status = locked and markup set locked | System rule |
| G2 — Snapshot integrity | All three data sets are immutable copies; source edits after activation do not alter the baseline | System rule |
| G3 — Approval | Commercial Manager approval required; identity and timestamp recorded | RBAC + audit |
| G4 — VO-only revision | Approved VO items append to the baseline (budget + allowable qty at then-current prices); nothing else changes it | System rule + audit |

| Entry criteria | Contract awarded; BOQ locked; price list frozen at final bid revision |
| --- | --- |
| Exit criteria | Baseline active with reference number; PR checks live |

Exception and rejection handling:

- Tender priced without compositions (flat rates only): baseline activates with budget + price checks; quantity check runs only for composed items — flag the gap to estimating for next tender.

- Post-award re-pricing of the BOQ (client-agreed): treat as a budget revision per SOP-QS-05 G4, then re-issue the baseline as revision BL-…-R2 with comparison retained.

# 6. SOP-QSP-02 — Purchase Requisition with Baseline Checks

| Who | Requester (raise), Procurement Officer (validate), PM / Procurement Manager / QS Manager (approve per routing) |
| --- | --- |
| When | Whenever site, store, or design needs material, plant hire, or services |
| System Path | /dashboard/procurement/pr |

### Procedure Steps

- Create PR: project, required date, delivery location, justification.

- Add lines. EVERY line must select a Budget code / BOQ item (mandatory) and, where the material exists in the baseline, the Price List resource (auto-suggested by item code/description match).

- O

- E

- Resolve any red flags or prepare override justification, then Submit.

- T

- Approved PR → available to RFQ (SOP-QSP-03). Rejected PR returns to draft with mandatory reason.

## 6.1 The Three Baseline Checks (per PR line)

| Check | Formula | Result Handling |
| --- | --- | --- |
| 1 — Budget (money) | PR line value ≤ Remaining budget = BOQ budget − committed − actual − pending PRs | Exceeds → BLOCK with red-route override option (QS Manager + reason) |
| 2 — Quantity (over-order) | Ordered-to-date + PR qty ≤ Allowable qty (= BOQ qty × composition × (1+wastage%)) | Exceeds → amber at ≤105%, red > 105% (config) — red requires QS Manager |
| 3 — Price (benchmark) | Variance % = (expected − baseline) ÷ baseline × 100 | ≤0% green; 0–5% amber (visible to approver); >5% red → extra QS Manager step + reason |

### Worked example (cement line)

Requested 400 bags @ 4.35; baseline 4.20; ordered-to-date 3,180; allowable 3,675 Check 1: 400 × 4.35 = 1,740 ≤ remaining 6,120 → PASS Check 2: 3,180 + 400 = 3,580 ≤ 3,675 (97.4%) → PASS Check 3: (4.35 − 4.20) ÷ 4.20 = +3.6% → AMBER (visible, no extra step)

## 6.2 Approval Routing Matrix

| Condition | Routing |
| --- | --- |
| All checks green/amber, PR value < $5,000 | Procurement Manager (1 step) |
| All checks green/amber, PR value ≥ $5,000 | Procurement Manager → Project Manager |
| Any RED check (over-budget, qty >105%, price >5%) | Standard chain + QS Manager step with mandatory reason (red route) |
| No baseline link (unbenchmarked line) | Standard chain; line flagged “no baseline” to approver and in buy-out report |
| Urgent / emergency (safety, stoppage risk) | PM verbal + system “urgent” flag → approvals completed within 24h retrospectively — never skipped |

### Workflow Control

Process status flow:

draft → submitted → checks evaluated → [routing per 6.2] → approved → to RFQ / direct PO └── rejected (reason mandatory) → draft red flag path: blocked → override requested → QS Manager approve/deny → continue / return

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Budget link | Line without BOQ item / budget code cannot be saved for submission | System validation |
| G2 — Snapshot | baseline_price copied to the line at creation; recomputation prohibited | System rule |
| G3 — Live checks | All three checks recompute on submission (not only on entry) — stale pending amounts are re-read | System rule |
| G4 — Red route | Any red check inserts the QS Manager step; approval without it is impossible; reason mandatory | System rule + RBAC + audit |
| G5 — Pending reservation | Submitted PR value reserves budget as pending; released on rejection or PO conversion | System automation |

| Entry criteria | Procurement baseline active (SOP-QSP-01); requester has project access |
| --- | --- |
| Exit criteria | PR approved with all check outcomes recorded per line |

Exception and rejection handling:

- Material not in BOQ scope at all: raise the need to QS — either a VO (client scope) or a budget transfer per project rules; do not force it onto an unrelated budget code.

- Baseline price obviously stale (market moved): the check still runs against the tender price — that variance IS the information; note market movement in the justification, and QS records it for the next tender's rate library.

- Split orders to dodge thresholds: cumulative same-resource PRs within 30 days are summed for routing — detected and flagged automatically.

# 7. SOP-QSP-03 — RFQ & Quotation Comparison vs Baseline

| Who | Procurement Officer (run), Procurement Manager (approve selection) |
| --- | --- |
| When | After PR approval, for lines above the direct-purchase limit (config, e.g. $500) |
| System Path | /dashboard/procurement/rfq |

### Procedure Steps

- Create RFQ from one or more approved PRs (system carries the lines, budget links, and baseline prices).

- S

- R

- Open the Comparison Sheet — one row per line, one column per supplier, plus the BASELINE column always shown last for reference.

- N

- S

- P

### Comparison Sheet Layout (mandatory columns)

| Column | Content |
| --- | --- |
| Line / resource | PR line reference, resource code, quantity |
| Supplier A…N | Normalized unit price and total per supplier |
| Baseline | Tender baseline price — read-only reference |
| Variance vs baseline | Selected quote vs baseline % — colour-coded per 6.1 check 3 bands |
| Selection + reason | Chosen supplier; mandatory reason when not lowest normalized price |

### Workflow Control

Process status flow:

draft RFQ → issued → quotations received → comparison → selection approved → to PO (no responsive quotes → re-issue / direct negotiation with reason)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Source | RFQ lines derive only from approved PRs; quantities cannot exceed PR quantities | System rule |
| G2 — Baseline visibility | The baseline column cannot be hidden or removed from the comparison sheet | System rule |
| G3 — Non-lowest selection | Selecting other than the lowest normalized quote requires a recorded reason | System validation + audit |
| G4 — Deadline | Quotes recorded after closing require Procurement Manager override with reason | System rule + audit |
| G5 — Re-check | If the selected price pushes the line into a red band that the PR passed at, the red route re-triggers before PO | System rule |

| Entry criteria | Approved PR; approved supplier register available |
| --- | --- |
| Exit criteria | Supplier selection approved per line; variance vs baseline recorded |

Exception and rejection handling:

- All quotes above baseline by >5%: proceed via red route with market-condition note; QS logs the systematic variance for tender rate-library feedback.

- Single-source item (no comparison possible): record single-source justification; Procurement Manager approval mandatory regardless of value.

# 8. SOP-QSP-04 — Purchase Order & Budget Commitment

| Who | Procurement Officer (draft), Procurement Manager (approve & issue) |
| --- | --- |
| When | After supplier selection (or direct purchase under limit) |
| System Path | /dashboard/procurement/po |

### Procedure Steps

- C

- T

- Approve → PO issued to supplier. At this moment the system: (a) writes a commitment against each BOQ item for the PO line value; (b) releases the corresponding PR pending reservation; (c) records buy-out gain/(loss) = (baseline − PO price) × qty per line.

- C

- Delivery: store receives against the PO (GRN). Invoice: Finance performs the three-way match and records the cost transaction (SOP-QS-07) — the value moves committed → actual for the matched quantity.

- C

### Commitment Lifecycle

PR submitted → budget PENDING (soft reservation) PO approved → budget COMMITTED (pending released) GRN + invoice → COMMITTED → ACTUAL (per matched qty) PO closed/cancelled → residual commitment released back to budget

### Workflow Control

Process status flow:

draft → approved → issued → partially delivered → delivered → invoiced/matched → closed (cancelled: any pre-delivery status → cancelled, commitment released, reason mandatory)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — PR ceiling | PO qty and value ≤ approved PR per line, cumulatively across split POs; excess requires PR revision/re-approval | System rule |
| G2 — Final re-check | Checks 1–3 re-run at PO prices; a new red band triggers the red route before issue | System rule |
| G3 — Commitment atomicity | Commitment write + pending release + buy-out record occur in one transaction at issue | System automation |
| G4 — Amendment control | PO amendments (qty/price/terms) re-approve at the original routing level; version history retained | System rule + audit |
| G5 — Three-way match | Invoice cannot post above matched GRN qty × PO price without Finance + QS Manager override | System rule (SOP-QS-07 link) |

| Entry criteria | Approved selection (or approved PR within direct-purchase limit) |
| --- | --- |
| Exit criteria | PO issued; commitment live in Budget & Variance; buy-out recorded |

Exception and rejection handling:

- Supplier withdraws after PO: cancel with reason → commitment released → return to next-ranked quotation (RFQ record retained for exactly this moment).

- Price increase at delivery (supplier unilateral): do NOT receive at the new price — treat as PO amendment (G4) or reject delivery; escalate to Procurement Manager.

- Partial delivery long-outstanding: monthly commitment review (Section 10) flags POs > 60 days with undelivered balance for close/cancel decision.

# 9. SOP-QSP-05 — Delivery, Matching & Committed-to-Actual (summary)

Full detail lives in SOP-QS-07 (Cost Transactions) and the Inventory module SOP; this section defines only the integration hand-off:

- GRN quantity received against a PO line is the only basis for invoice matching — no PO/GRN, no payment.

- On matched invoice recording (SOP-QS-07 status approved), the system moves value committed → actual for the matched quantity, at PO price.

- Price difference on invoice vs PO beyond tolerance (config, e.g. 1%) blocks posting → Finance + Procurement resolve via PO amendment or supplier credit note.

- Stock issues to WBS locations consume against the same BOQ item, keeping quantity check 2 accurate for future PRs.

# 10. SOP-QSP-06 — Buy-out Reporting & Baseline Maintenance

| Who | QS Manager (prepare), Commercial Manager (review) |
| --- | --- |
| When | Monthly, with the Budget & Variance cycle (SOP-QS-06) |
| System Path | /dashboard/qs → Buy-out Report (new) |

### The Buy-out Report

| Column | Content |
| --- | --- |
| Resource / trade | Grouped by resource, subtotaled by trade and project |
| Baseline price | Tender assumption |
| Weighted PO price | Committed value ÷ committed qty |
| Committed qty / value | All issued POs |
| Buy-out gain/(loss) | (baseline − PO price) × qty — green gains, red losses |
| Unbenchmarked spend | Committed value on lines without baseline links — visibility line |
| Coverage % | Committed qty ÷ allowable qty — how much of the scope is bought |

### Worked example

Cement: baseline 4.20; PO 4.35; 3,675 bags → (551.25) loss Rebar: baseline 0.72; PO 0.68; 45,000 kg → 1,800.00 gain Net buy-out to date: +1,248.75 (0.5% of trade budget)

### Monthly review agenda

- N

- R

- C

- S

- S

### Workflow Control

Process status flow:

monthly: generate report → review meeting → actions assigned → minuted → next cycle

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Source integrity | Report computes only from baseline snapshot + PO commitments + matched actuals — no manual adjustment | System rule |
| G2 — Override register | Every red-route approval of the month appears; none may be omitted | System rule + audit |
| G3 — Feedback loop | Systematic variances (> 5% on > 3 resources in a trade) must be logged to the rate-library feedback list | Procedure |

| Entry criteria | At least one issued PO on the project |
| --- | --- |
| Exit criteria | Monthly buy-out position minuted; actions assigned |

Exception and rejection handling:

- Baseline missing for a heavily-bought resource: add it to the next baseline revision via the VO/budget-revision door — never edit the active baseline directly.

# 11. Data Linkage Reference

| Object | Key fields added by this SOP |
| --- | --- |
| procurement_baselines | project_id, reference, status, approved_by/at; child snapshots: baseline_budgets, baseline_prices, baseline_allowables |
| pr_items | boq_item_id (mandatory), price_list_item_id (nullable), baseline_price (snapshot), expected_price, variance_pct, check1/2/3_result, override_ref |
| rfq_lines / quotes | pr_item_id, supplier quotes, normalized_price, baseline_price (carried), selection_reason |
| po_items | pr_item_id, final_price, commitment_id, buyout_amount |
| cost_commitments | boq_item_id, po_id, amount, status (open/partial/closed), released_at |
| qs_cost_transactions | existing (SOP-QS-07) — gains po_id + grn_ref for the committed→actual move |

Configuration parameters (Config Spec): price variance bands (default 0/5%), quantity tolerance (default 105%), direct-purchase limit (default $500), PR routing threshold (default $5,000), invoice price tolerance (default 1%), stale-commitment age (default 60 days).

# 12. KPIs & Reports

- Net buy-out gain/(loss) — project and portfolio, monthly trend.

- % PR lines with baseline link (target > 85% of value).

- Red-route count and value per month (rising trend = baseline or market problem).

- Commitment coverage per critical resource vs programme need.

- PR cycle time (raise → approve) and PO cycle time (approve → issue).

- Unbenchmarked spend % of committed value.

# 13. RACI

| Activity | Requester | Proc. Officer | Proc. Manager | QS Manager | PM | Commercial Mgr |
| --- | --- | --- | --- | --- | --- | --- |
| Baseline activation | — | I | C | R | I | A |
| Raise PR | R | C | A | I | C | — |
| Red-route override | C | C | C | A/R | I | I |
| RFQ & comparison | — | R | A | C | I | — |
| PO issue | I | R | A | I | I | — |
| Buy-out review | — | C | C | R | C | A |

R = Responsible,  A = Accountable,  C = Consulted,  I = Informed

# 14. Document Control

| Field | Value |
| --- | --- |
| Document Number | SOP-QSP-001 |
| Title | Cost Control → Procurement Integration SOP (BOQ Baseline to PR / RFQ / PO) |
| Revision | R1 |
| Prepared By | DCOS Commercial Team |
| Reviewed By | QS Manager / Procurement Manager |
| Approved By | Commercial Director |
| Issue Date | 2026-07-16 |
| Next Review | 2027-01-16 |

## Revision History

| Revision | Date | Description | Author |
| --- | --- | --- | --- |
| R1 | 2026-07-16 | Initial issue — baseline activation, three PR checks with routing, RFQ baseline comparison, PO commitment lifecycle, GRN/matching hand-off, buy-out reporting, data linkage, KPIs, RACI | DCOS Commercial Team |

End of Document — SOP-QSP-001 R1