DCOS

Digital Construction Operating System

Quantity Surveying Module

Standard Operating Procedure (SOP)

| Document Ref | SOP-QS-001 |
| --- | --- |
| Revision | R3 — Margin Application, Time-Phased Budget Forecast & Final QS Cost Report |
| Base Document | SOP-QS-001 R2; SOP-QS-Module R1 (2026-06-06); DCOS System Architecture R0; Gap Analysis R1 |
| Issue Date | 2026-07-12 |
| Owner | Commercial Manager / QS Manager |
| Classification | Internal — Controlled Document |

# Table of Contents

# 1. Purpose & Scope

This Standard Operating Procedure governs the complete commercial lifecycle of a construction project within the DCOS platform — from pre-contract cost estimation through to financial close-out. It defines the standard process, the workflow control applied at every stage, the responsible roles, and the system controls that enforce commercial governance.

The SOP covers the following processes:

- Cost Library management (rate build-up and maintenance)

- Tender BOQ creation, tender management, and bid evaluation (in development)

- Bill of Quantities (BOQ) creation and contract baseline control

- Rate build-up and margin application — dual cost/sell rates (NEW in R3)

- Budget monitoring and variance analysis

- Time-phased budget baseline and monthly cash flow forecast (NEW in R3)

- Cost transaction recording (invoices, POs, timesheets, deliveries)

- Variation Order (VO / Change Order) management with threshold-based approval

- Earned Value Management (EVM) and Cost S-Curve monitoring

- Interim Payment Certificates (IPC / Progress Claims) in G702 format

- Retention deduction and release management

- Portfolio-level commercial reporting

- Final Account and close-out (in development)

- Final QS Cost Report — internal full-cost version and client sell-side version (NEW in R3)

- Subcontractor Sub-IPC and back charges (in development)

- Contract Administration — Employer Instructions (in development)

Applies To QS Engineers, QS Managers, Project Managers, Commercial Managers, Contract Administrators, Finance Officers, and Directors on any project managed in DCOS.

Workflow Control Principle Every commercial record in this module moves through a controlled status lifecycle. No record may skip a status, and every approval, rejection, and post-lock change is recorded in the audit trail. The locked BOQ is the single contract baseline: all financial movement after lock must flow through a Variation Order, and all payment must flow through a certified IPC.

# 2. Definitions & Abbreviations

| Term | Definition |
| --- | --- |
| BOQ | Bill of Quantities — priced list of measured work items forming the contract cost baseline |
| VO | Variation Order (Change Order) — formal instrument for scope, price, or programme change |
| IPC | Interim Payment Certificate — monthly progress claim submitted to the client for certification |
| G702 | Standard application-and-certificate-for-payment summary format used for IPC claims |
| EVM | Earned Value Management — integrated cost and schedule performance measurement |
| BAC / EAC / VAC | Budget at Completion / Estimate at Completion / Variance at Completion |
| CPI / SPI | Cost Performance Index / Schedule Performance Index |
| Retention | Percentage withheld from each certified payment as performance security (typically 5%) |
| PC | Practical Completion — contractual milestone triggering first retention release |
| DLP | Defects Liability Period — post-completion period; end of DLP triggers final retention release |
| Sub-IPC | Subcontractor interim payment certificate assessed against the subcontract BOQ |
| EI | Employer's Instruction — formal client instruction with potential time/cost entitlement |
| WBS | Work Breakdown Structure — the location/spine hierarchy of DCOS to which cost is allocated |
| Cost Rate | Net direct cost per unit from the cost library — contains no margin. Internal only |
| Sell Rate | Client-facing unit rate = cost components marked up per approved project markup settings. Basis of contract value, IPC claims, and all client documents |
| Markup / Margin | Markup is the % applied on cost to produce the sell rate; Margin = (Sell − Cost) ÷ Sell. Expected Margin (item) = (Sell Rate − Cost Rate) × Quantity |
| Time-Phased Baseline | The locked BOQ distributed across calendar months — the source of the planned S-curve and EVM Planned Value (PV) |
| Cash Flow Forecast | Monthly cash in (certified IPCs net of retention, retention releases) versus cash out (supplier/subcontractor payments per payment terms) |
| RACI | Responsible, Accountable, Consulted, Informed |

# 3. Module Navigation

| Feature | Path | Access Level |
| --- | --- | --- |
| BOQ & Budget Hub | /dashboard/qs | QS Engineer+ |
| Cost Library | /dashboard/qs/cost-library | QS Manager+ |
| Variation Orders | /dashboard/qs/variations | QS Engineer+ |
| Progress Claims (IPC) | /dashboard/qs/claims | QS Engineer+ |
| Retention Register | /dashboard/qs/retention | QS Manager+ |
| Tendering (TBD) | /dashboard/qs/tendering | QS Manager+ |

The sidebar groups all QS features under “Quantity Surveying” with the following sub-sections:

- QS & Cost — BOQ, Cost Library, Variation Orders, Claims, Retention

- Tendering — Cost Estimation, Tender Management, Bid Evaluation

- Contract Admin — Notices, Employer Instructions, Correspondence, Entitlements

- Subcontractors — Sub-IPCs, Back Charges, Performance Notices

# 4. Database Tables Reference

| Table | Purpose |
| --- | --- |
| qs_cost_divisions | Cost library — top-level divisions |
| qs_cost_sections | Cost library — mid-level sections |
| qs_cost_items | Cost library — rate items with cost breakdowns |
| qs_boq_sections | Project BOQ groupings (baseline status) |
| qs_boq_items | BOQ line items linked to WBS nodes and cost codes — holds dual cost/sell rates (R3) |
| qs_budget_revisions | Audit trail of post-lock BOQ changes |
| qs_cost_transactions | Actual cost entries (invoices, POs, timesheets) |
| qs_variation_orders | Change order register |
| qs_vo_items | Line items within each VO |
| qs_vo_approvals | Multi-step VO approval trail |
| qs_progress_claims | Monthly IPC claims (G702 format) |
| qs_claim_items | Line items per IPC |
| qs_retention_ledger | Retention deductions and release transactions |
| qs_project_markups | Project default markup % per cost component — approval-controlled (NEW R3) |
| qs_monthly_budget_baseline | Time-phased distribution of the locked BOQ by month, with baseline revisions (NEW R3) |
| qs_cashflow_forecasts | Monthly cash in/out forecast derived from the baseline and payment terms (NEW R3) |

# 5. QS Process Overview & Master Workflow Map

The QS module follows the commercial lifecycle of a construction contract. Each phase hands a controlled baseline to the next:

PRE-CONTRACT POST-CONTRACT CLOSE-OUT ───────────── ────────────────────── ────────────── Cost Library ──→ BOQ Baseline ──→ Final Account Tender BOQ ──→ Budget Monitoring ──→ Retention Release Bid Evaluation ──→ Cost Transactions ──→ Final Certificate Variation Orders Progress Claims (IPC) EVM Reporting

Master status lifecycles controlled by this SOP:

| Record Type | Status Lifecycle | SOP Ref |
| --- | --- | --- |
| BOQ Baseline | draft → approved → locked → revised | SOP-QS-05 |
| Cost Transaction | pending → approved → paid | SOP-QS-07 |
| Variation Order | draft → submitted → approved/rejected → implemented | SOP-QS-08 |
| Progress Claim (IPC) | draft → submitted → client_reviewed → certified → paid | SOP-QS-11 |
| Retention Release | pending → approved / rejected | SOP-QS-12 |
| Markup Settings | draft → approved → locked (with BOQ) | SOP-QS-05A |
| Monthly Budget Baseline | auto-generated → adjusted → approved → locked (Rev 0) | SOP-QS-10A |
| Final QS Cost Report | draft → approved → client version issued → signed | SOP-QS-14A |
| Tender | draft → published → evaluation → awarded / cancelled | SOP-QS-03 |
| Sub-IPC | draft → submitted → certified → paid | SOP-QS-15 |
| Employer Instruction | open → responded → closed | SOP-QS-17 |

Golden Rules of Workflow Control 1. The locked BOQ is the contract baseline. It is never edited directly — every post-lock change flows through a Variation Order. 2. Approved VOs accumulate on top of the baseline (Contract Sum to Date = Original Contract Sum + Net Approved VOs); they never rewrite locked line items. 3. Certified IPCs automatically create retention ledger deductions — retention is never calculated manually. 4. Cost transactions may only be deleted while status = pending. Approved and paid transactions are permanent audit records. 5. Every approval and rejection requires an identified approver, timestamp, and (for rejection) a mandatory reason — all written to the audit trail. 6. Dual-rate firewall: the cost library and BOQ hold net cost rates; margin is applied at pricing to produce sell rates. All client-facing outputs (BOQ export, IPC, Final Statement) render sell rates only — internal cost and margin are never exposed externally. 7. Planned Value (EVM) and the planned S-curve derive only from the approved time-phased budget baseline — never from manual snapshots.

# 6. Phase 1 — Pre-Contract

## SOP-QS-01: Cost Library Management

| Who | QS Manager, Senior QS Engineer |
| --- | --- |
| When | Project setup or periodic library maintenance |
| System Path | /dashboard/qs/cost-library |

### Procedure Steps

- Navigate to QS → Cost Library.

- The library is organised in 3 levels: Divisions → Sections → Items.

- S

- To add a Division: click “Add Division” → enter Code, Name, Sequence.

- To add a Section: expand a division → click “Add Section”.

- To add a Cost Item: expand a section → click “Add Item” → fill in Code, Description, Unit, Base Rate, and the cost breakdown (Labor %, Material %, Equipment % — must sum ≤ 100%).

- Items with is_active = false are hidden from BOQ library lookups.

- C

### Validation Rules

| Rule | Detail |
| --- | --- |
| Item code | Must be unique within its section |
| Base rate | Must be > 0 |
| Component percentages | Labor% + Material% + Equipment% ≤ 100% |
| Sequence | Determines display order; auto-assigned if left blank |

### Workflow Control

Process status flow:

create item (active) ⇄ deactivate (is_active = false) — no delete once referenced by any BOQ

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Create/Edit | Only QS Manager+ may create or edit library divisions, sections, and items | RBAC |
| G2 — Rate integrity | Base rate > 0; component % sum ≤ 100%; code unique within section | System validation |
| G3 — Referential lock | An item referenced by any BOQ line cannot be deleted — deactivate instead | System rule |
| G4 — Rate change | Editing a base rate never re-prices existing BOQ items; rates are copied at time of BOQ item creation | System rule |

| Entry criteria | QS Manager role assigned MasterFormat divisions seeded |
| --- | --- |
| Exit criteria | Library items active and searchable in BOQ Builder |

Exception and rejection handling:

- Obsolete rate found: deactivate the item and create a replacement — never overwrite the old rate history.

- Duplicate code rejected by the system: correct the code or place the item under the appropriate section.

## SOP-QS-02: Tender BOQ Creation (in development)

| Who | Estimator, QS Engineer |
| --- | --- |
| When | Responding to a tender invitation |
| System Path | /dashboard/qs/tendering/cost-estimation (TBD) |

### Procedure Steps

- Navigate to QS → Tendering → Cost Estimation.

- Create or open the linked tender from Tender Management.

- In the Tender BOQ tab, add sections and items from the rate library.

- F

- Add subcontractor quotes under the Sub-Quotes tab (compare quotes per trade).

- In the Risk Register, add risk items with likelihood, impact, and priced amount.

- Compile the Bid Summary: Direct Cost + Preliminaries + Overhead % + Profit % + Contingency + Risk Allowance = Total Bid Price.

- Set status to final and submit.

### Bid Summary Calculation

| Component | Description |
| --- | --- |
| Direct Cost | Sum of all tender BOQ items |
| Preliminaries | Site setup, temporary works, insurances |
| Subcontract Cost | Sum of preferred sub-quotes |
| Overhead % | Company overhead applied to direct cost |
| Profit % | Commercial margin |
| Contingency | Risk buffer for known unknowns |
| Risk Allowance | Priced risk items from risk register |
| Total Bid Price | Auto-calculated generated column |

### Workflow Control

Process status flow:

draft → final → submitted (with linked tender) — final estimate is frozen at submission

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Tender link | Tender BOQ must be linked to an existing tender record before it can be finalised | System rule |
| G2 — Completeness | Bid summary must contain direct cost, preliminaries, overhead %, and profit % before status = final | System validation |
| G3 — Freeze on final | Estimate items become read-only at final; re-pricing requires reverting to draft with reason logged | System rule + audit |
| G4 — Submission sign-off | Only QS Manager+ may submit the final bid price | RBAC |

| Entry criteria | Tender registered in Tender Management Cost library rates current |
| --- | --- |
| Exit criteria | Bid Summary at status final; total bid price submitted against the tender |

Exception and rejection handling:

- Addendum received after finalisation: revert to draft, record the addendum reference, re-price affected items, re-finalise.

- Sub-quote withdrawn: replace with next preferred quote and record the change in the sub-quotes comparison.

## SOP-QS-03: Tender Management (in development)

| Who | Commercial Manager, QS Manager |
| --- | --- |
| When | Running an invitation-to-tender process |
| System Path | /dashboard/qs/tendering (TBD) |

### Tender Types

| Type | Description |
| --- | --- |
| Open | Public advertisement, any bidder |
| Selective | Invited list only |
| Negotiated | Direct negotiation with single party |
| Restricted | Limited, pre-qualified suppliers |

### Procedure Steps

- Navigate to QS → Tendering → Tender Management.

- C

- F

- Issue Addenda as required (addendum number, title, attachment URL).

- Manage the Queries log: record questions and published answers; mark confidential where required.

- Record Submissions: bidder name, submitted date, bid amount, responsiveness status.

- Evaluate bids under Bid Evaluation: shortlist, score, and recommend award.

- Award tender: set winning submission → status → awarded.

### Workflow Control

Process status flow:

draft → published → (queries / addenda) → submissions closed → evaluation → awarded / cancelled

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Publication | Tender number, type, and submission deadline mandatory before publishing | System validation |
| G2 — Deadline lock | Submissions cannot be recorded after the deadline without a Commercial Manager override (reason logged) | System rule + audit |
| G3 — Addendum trace | Every addendum is numbered sequentially and notified to all invited bidders | System rule |
| G4 — Award authority | Only Commercial Manager or Director may set status = awarded | RBAC |

| Entry criteria | Tender opportunity approved for bidding (go/no-go decision) |
| --- | --- |
| Exit criteria | Tender awarded with winning submission recorded, or formally cancelled with reason |

Exception and rejection handling:

- No responsive bids received: record outcome, cancel or re-issue the tender as a new revision.

- Confidential query: mark confidential — the answer is issued only to the querying bidder and flagged in the log.

## SOP-QS-04: Bid Evaluation (in development)

| Who | Commercial Manager, QS Manager, Director |
| --- | --- |
| When | After tender submission deadline |
| System Path | /dashboard/qs/tendering/bid-evaluation (TBD) |

### Procedure Steps

- Open the tender and navigate to the Submissions tab.

- Mark each submission as responsive or non_responsive.

- F

- Set preferred submissions to shortlisted.

- P

- Award to the selected bidder → tender status → awarded.

### Workflow Control

Process status flow:

submission → responsiveness check → scoring → shortlisted → recommendation → award approval

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Responsiveness first | Scores can only be entered against submissions marked responsive | System rule |
| G2 — Scoring integrity | Evaluation criteria and weights are fixed before scoring begins; scores are attributable per evaluator | System rule + audit |
| G3 — Recommendation | A recommendation report is required before award can be triggered | Procedure |
| G4 — Award approval | Director approval required for award; decision recorded with timestamp | RBAC + audit |

| Entry criteria | Submission deadline passed; all submissions logged |
| --- | --- |
| Exit criteria | Award decision approved and tender status = awarded |

Exception and rejection handling:

- Tied scores: Commercial Manager applies documented tie-break criteria (price, programme, HSE record) and records the rationale.

- Preferred bidder withdraws: escalate to next shortlisted bidder; re-issue recommendation for approval.

# 7. Phase 2 — Post-Contract: Budget Establishment

## SOP-QS-05: BOQ Creation (Bill of Quantities)

| Who | QS Manager, QS Engineer |
| --- | --- |
| When | After contract award, before work commences |
| System Path | /dashboard/qs → Bill of Quantities tab |

### Procedure Steps

- Navigate to QS → BOQ & Budget → Bill of Quantities tab.

- S

- Click “Add Section” to create BOQ divisions (e.g., “Substructure”, “Superstructure”, “Finishes”).

- Within each section, click “Add Item”: search the cost library by code or description (auto-populates unit and rate) or enter a free-form description; set Unit, Quantity, Unit Rate → Total Amount auto-calculates; optionally link a WBS Node for WBS-level cost tracking; mark provisional items with the “Provisional” toggle; set Contingency % for risk allowance items.

- R

- When the BOQ is ready for contract sign-off: click “Approve BOQ” → draft → approved.

- Once the contract is executed: click “Lock BOQ” → approved → locked. The locked BOQ is the contract baseline — no direct editing permitted. All post-lock changes must go through a Variation Order (see SOP-QS-08).

- Post-lock revisions create an entry in qs_budget_revisions and set status to revised.

### Baseline Status Rules

| Status | Meaning | Who Can Transition |
| --- | --- | --- |
| draft | Being built, editable | QS Engineer |
| approved | Reviewed and agreed, awaiting execution | QS Manager |
| locked | Contract baseline frozen | QS Manager |
| revised | Post-lock amendment approved via VO | QS Manager + Director |

### BOQ Item Fields

| Field | Description |
| --- | --- |
| Description | Item narrative |
| Unit | Measurement unit (m², m³, m, nr, t, etc.) |
| Quantity | Contract quantity |
| Unit Rate | Rate from cost library or manually entered |
| Total Amount | Auto-calculated: Quantity × Unit Rate |
| WBS Node | Optional link for WBS-level cost roll-up |
| Cost Item | Optional link to rate library for cost breakdown |
| Contingency % | Risk allowance on this item |
| Is Provisional | Mark for items with uncertain scope |

### Workflow Control

Process status flow:

draft → approved → locked → revised (post-lock, via VO/budget-revision only)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Build control | Only QS Engineer+ may create/edit draft BOQ; items require unit, quantity, and rate before section totals validate | RBAC + validation |
| G2 — Approval | QS Manager reviews totals against contract sum before setting approved; approval identity and timestamp recorded | RBAC + audit |
| G3 — Lock | Lock is one-way; after lock, item edit controls are disabled in the UI and blocked by the API | System rule |
| G4 — Post-lock change | Any revision requires an approved VO or a budget revision record; direct edits rejected. Revision entry written to qs_budget_revisions | System rule + audit |
| G5 — Provisional items | Provisional items are flagged for re-measurement and reported separately in budget analysis | System rule |

| Entry criteria | Contract awarded; contract sum and payment terms known Cost library available |
| --- | --- |
| Exit criteria | BOQ locked — contract baseline established and feeding Budget, EVM, and IPC modules |

Exception and rejection handling:

- Error discovered after lock: raise a budget revision (with Director approval) or a VO depending on whether the error is internal or contractual.

- Client-supplied BOQ differs from measured quantities: mark affected items provisional and resolve through re-measurement at Final Account.

## SOP-QS-05A: Rate Build-Up & Margin Application (NEW in R3)

| Who | QS Manager (set markups), Commercial Director (approve) |
| --- | --- |
| When | After contract award, before BOQ pricing; locked together with the BOQ |
| System Path | /dashboard/qs → Markup Settings tab (new) |

Core Pricing Principle The cost library base rate is always the NET DIRECT COST — no margin. The Labor/Material/Equipment percentages classify that cost; they do not add margin. Margin is applied at pricing time through approved project markup settings, producing a SELL RATE per BOQ item. The BOQ therefore carries dual rates: the Cost Rate (internal budget) and the Sell Rate (contract value the client sees and pays against).

### Procedure Steps

- Navigate to QS → BOQ & Budget → Markup Settings and select the project.

- E

- Submit for approval → Commercial Director reviews and approves the markup set → status approved.

- I

- Item-level exception: enter a markup_pct_override with a mandatory reason (e.g., loss-leader pricing, provisional item) — the override replaces the component build-up for that item.

- Total Amount = Quantity × Sell Rate — this is the contract value shown on the BOQ, claimed in IPCs, and reported to the client.

- E

- Markup settings lock automatically when the BOQ locks (SOP-QS-05) → status locked.

### Sell Rate Formula

Sell Rate = Σ [ Cost Rate × Component% × (1 + Component Markup%) ] Expected Margin (item) = (Sell Rate − Cost Rate) × Quantity Margin % = (Sell − Cost) ÷ Sell × 100

### Worked Example — C25 Concrete, Slab (Cost Rate $85.00/m³)

| Component | Split | Net Cost | Markup | Sell |
| --- | --- | --- | --- | --- |
| Labor | 30% | $25.50 | +18% | $30.09 |
| Material | 60% | $51.00 | +8% | $55.08 |
| Equipment | 10% | $8.50 | +12% | $9.52 |
| Unit Rate | 100% | $85.00 | — | $94.69 |

Quantity 500 m³ → Contract value $47,345 (sell), estimated cost $42,500, expected margin $4,845 (10.2%).

### Data Model Additions

| Table / Field | Description |
| --- | --- |
| qs_project_markups | project_id; labor_markup_pct; material_markup_pct; equipment_markup_pct; subcontract_markup_pct; status (draft/approved/locked); approved_by; approved_at |
| qs_boq_items.cost_rate | Net unit cost copied from library at item creation (immutable snapshot) |
| qs_boq_items.sell_rate | Computed client-facing rate; frozen at BOQ lock |
| qs_boq_items.markup_pct_override | Nullable item-level markup exception, with reason |
| qs_boq_items.expected_margin | (sell_rate − cost_rate) × quantity — computed |

### Workflow Control

Process status flow:

markup set: draft → approved (Commercial Director) → locked (automatically with BOQ lock)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Breakdown integrity | Component build-up pricing requires the library item's Labor+Material+Equipment split to equal exactly 100%; otherwise the item falls back to item-level margin override | System validation |
| G2 — Approval authority | Markup settings must be approved by Commercial Director before the BOQ can be approved (SOP-QS-05 G2 dependency) | RBAC + system rule |
| G3 — Negative margin | Any item priced with sell rate below cost rate requires Commercial Director approval with a mandatory reason | System validation + audit |
| G4 — Visibility firewall | Cost rates, markup %, and margin figures are visible to QS Manager+ only. All client-facing outputs (BOQ export, IPC documents, Final Statement) render sell rates only — enforced by the report generator, never by manual editing | RBAC + system rule |
| G5 — Post-lock change | Markup changes after BOQ lock are prohibited; new pricing applies only to new VO items, priced at then-current approved markups | System rule |

| Entry criteria | Contract awarded; cost library rates current; BOQ in draft |
| --- | --- |
| Exit criteria | Markup set approved; every BOQ item carries cost rate, sell rate, and expected margin; contract value totals from sell rates |

Exception and rejection handling:

- Mid-project markup policy change: applies to pricing of new VOs only — the locked baseline sell rates never change.

- Library item without a 100% component split: price via item-level margin override with reason, and flag the library item for correction (SOP-QS-01).

- Client requests rate breakdown: only the sell rate build-up may be shared in the contractual format; internal cost/markup structure requires Commercial Director approval and a contractual open-book basis.

## SOP-QS-06: Budget & Variance Monitoring

| Who | QS Manager, Project Manager, Commercial Manager |
| --- | --- |
| When | Weekly or monthly review cycle |
| System Path | /dashboard/qs → Budget & Variance tab |

### Procedure Steps

- Navigate to QS → BOQ & Budget → Budget & Variance tab and select the project.

- Review the 4 KPI cards: Total Budget (locked BOQ total); Committed (approved POs/subcontracts not yet invoiced); Actual Cost (paid or approved invoices); Forecast/Spent progress bar (Actual ÷ Budget %).

- E

- A

- I

### Column Definitions

| Column | Definition |
| --- | --- |
| Budget | Locked BOQ item total |
| Committed | POs raised against this item |
| Actual | Invoiced/paid against this item |
| Forecast | Committed + Actual + estimated to complete |
| Variance | Budget − Forecast |
| Var % | Variance ÷ Budget × 100 |

### Variance Colour Coding

| Colour | Condition | Meaning |
| --- | --- | --- |
| Green | Variance > 0 and < 5% of budget | Under budget |
| Amber | Variance between 0% and negative | Minor over-run — watch |
| Red | Variance negative | Over budget — action required |

### Workflow Control

Process status flow:

continuous control loop: review → identify variance → investigate → corrective action → re-review

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Data source | Budget figures derive only from the locked BOQ; committed/actual figures derive only from recorded cost transactions | System rule |
| G2 — Red variance | Any red item triggers investigation by QS Manager within the same review cycle | Procedure |
| G3 — Escalation | Section-level over-run > 5% of section budget escalated to Commercial Manager; project over-run forecast escalated to Director | Procedure |
| G4 — Corrective action trace | Corrective actions (VO, re-procurement, value engineering) are recorded against the affected BOQ items | Procedure + audit |

| Entry criteria | BOQ locked; cost transactions being recorded |
| --- | --- |
| Exit criteria | Variance report reviewed and actions assigned each cycle |

Exception and rejection handling:

- Cost recorded without BOQ allocation: QS Engineer re-allocates the transaction to the correct BOQ item before the next review.

- Forecast exceeds contract sum: immediate escalation to Commercial Director with recovery plan (this is an EAC breach, see SOP-QS-09).

# 8. Phase 3 — Post-Contract: Cost Control

## SOP-QS-07: Cost Transaction Recording

| Who | QS Engineer, Site Quantity Surveyor, Finance Officer |
| --- | --- |
| When | On receipt of invoice, PO approval, timesheet, or delivery docket |
| System Path | /dashboard/qs → Cost Transactions tab |

### Procedure Steps

- Navigate to QS → BOQ & Budget → Cost Transactions tab.

- Click “Record Cost” to open the entry form.

- F

- S

- Use the Category Filter chips to filter the view by cost type.

- D

### Transaction Type Definitions

| Type | Use Case |
| --- | --- |
| Invoice | Supplier/subcontractor invoice received and to be paid |
| Purchase Order | Committed cost — PO raised but not yet invoiced |
| Timesheet | Direct labour costs logged by supervisors |
| Delivery | Site delivery docket matched to a PO |
| Other | Miscellaneous site costs not covered above |

### Workflow Control

Process status flow:

pending → approved → paid (delete permitted only at pending)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Entry integrity | Type, category, description, vendor, cost date, and amount are mandatory; reference number required for invoices and POs | System validation |
| G2 — Approval | QS Manager verifies the transaction against supporting documents before setting approved | RBAC + procedure |
| G3 — Payment | Finance sets paid only when payment is confirmed; paid transactions are immutable | RBAC + system rule |
| G4 — Deletion | Delete allowed only at pending; approved/paid records can only be reversed by a contra entry with reason | System rule + audit |

| Entry criteria | Supporting document received (invoice, PO, timesheet, docket) |
| --- | --- |
| Exit criteria | Transaction at paid; cost reflected in Budget & Variance and EVM Actual Cost |

Exception and rejection handling:

- Wrong amount discovered after approval: post a contra (negative) transaction referencing the original, then re-enter correctly.

- Invoice without a PO: record as Invoice type and flag to Procurement for retrospective PO or escalation.

## SOP-QS-08: Variation Order (VO) Management

| Who | QS Engineer (raise), QS Manager (review), PM / QS Manager / Director (approve per threshold) |
| --- | --- |
| When | Whenever scope, price, or programme changes are identified |
| System Path | /dashboard/qs/variations |

### Procedure Steps

- Navigate to QS → Variation Orders and click “New Variation Order”.

- E

- Save as draft — the VO number is auto-generated in the format VO-YYYY-XXXX.

- A

- When ready for approval, click “Submit” → draft → submitted.

- T

- E

- Rejection resets the VO to draft for revision and resubmission.

- Once all approval steps are complete → status approved.

- After the change is physically implemented on site → QS marks implemented.

### Multi-Step Approval Routing

| VO Amount | Approval Chain |
| --- | --- |
| < $5,000 | Project Manager (1 step) |
| $5,000 – $50,000 | PM → QS Manager (2 steps) |
| ≥ $50,000 | PM → QS Manager → Commercial Director (3 steps) |

### VO Impact on Contract Sum

- Approved VOs do not directly modify locked BOQ line items.

- Approved VO amounts accumulate as net_vo_amount in IPC claims.

- Running Contract Sum = Original Contract Sum + Net Approved VO Amount.

- Rejected VOs have no financial impact.

### Workflow Control

Process status flow:

draft → submitted → [step 1 → step 2 → step 3 per threshold] → approved → implemented └── rejected (reason mandatory) → returns to draft

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Submission | Title, VO type, description, and at least one line item required before submit | System validation |
| G2 — Threshold routing | Approval chain is computed from VO total at submission and cannot be shortened; changing line items after submission returns the VO to draft | System rule |
| G3 — Sequential approval | Approvers act in sequence; each decision is recorded in qs_vo_approvals with identity and timestamp | System rule + audit |
| G4 — Rejection reason | Reject requires a mandatory reason; the reason is visible to the originator | System validation |
| G5 — Implementation | Only approved VOs can be marked implemented; implemented VOs feed the IPC net_vo_amount | System rule |

| Entry criteria | Change event identified (client request, design change, site condition, regulatory) |
| --- | --- |
| Exit criteria | VO approved and, when executed on site, marked implemented — contract sum to date updated |

Exception and rejection handling:

- Urgent site instruction before VO approval: proceed only with PM written instruction; raise the VO within 48 hours and reference the instruction.

- Client disputes VO value: keep the VO at submitted, record the client position in the description, and negotiate; do not implement financially until approved.

- Approver unavailable: Commercial Director may reassign the approval step; reassignment is logged.

## SOP-QS-09: Earned Value Management (EVM) Monitoring

| Who | Commercial Manager, Project Manager, Director |
| --- | --- |
| When | Monthly project review meetings |
| System Path | /dashboard/qs → EVM Dashboard tab |

### Procedure Steps

- Navigate to QS → BOQ & Budget → EVM Dashboard tab and select the project.

- Click “Refresh” to compute the latest metrics from current task progress and cost data.

- R

- R

- N

- Use the Portfolio tab for cross-project EVM comparison.

### EVM Metrics

| Metric | Full Name | Formula | Target |
| --- | --- | --- | --- |
| BAC | Budget at Completion | Total locked BOQ | Reference |
| PV | Planned Value | Schedule-based budget consumed | Reference |
| EV | Earned Value | % Complete × BAC | EV ≥ PV |
| AC | Actual Cost | Sum of cost transactions | AC ≤ EV |
| CPI | Cost Performance Index | EV ÷ AC | ≥ 1.00 |
| SPI | Schedule Performance Index | EV ÷ PV | ≥ 1.00 |
| CV | Cost Variance | EV − AC | Positive |
| SV | Schedule Variance | EV − PV | Positive |
| EAC | Estimate at Completion | BAC ÷ CPI | ≤ BAC |
| VAC | Variance at Completion | BAC − EAC | Positive |
| TCPI | To-Complete Performance Index | (BAC − EV) ÷ (BAC − AC) | ≤ 1.00 |
| EAC% | EAC as % of BAC | EAC ÷ BAC × 100 | ≤ 100% |

### Interpretation & Escalation Guide

| CPI / SPI Value | Meaning | Action Required |
| --- | --- | --- |
| ≥ 1.10 | Significantly ahead/under | Verify data accuracy |
| 1.00 – 1.09 | On track | Monitor |
| 0.95 – 0.99 | Slight concern | Review with PM |
| 0.85 – 0.94 | At risk | Corrective action plan required |
| < 0.85 | Critical | Escalate to Director |

### Workflow Control

Process status flow:

monthly cycle: refresh metrics → health assessment → interpretation → action / escalation → record decisions

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Data freshness | EVM is computed only from locked BOQ (BAC), recorded task progress (EV), and approved/paid transactions (AC) — no manual metric overrides | System rule |
| G2 — Health thresholds | Amber health requires PM review; Red health requires a corrective action plan tabled at the monthly review | Procedure |
| G3 — EAC breach | EAC > BAC (VAC negative) mandates Director notification and a documented recovery plan | Procedure |
| G4 — Meeting record | EVM review outcomes and actions are minuted and linked to the project record | Procedure |

| Entry criteria | BOQ locked; task progress and cost transactions current for the period |
| --- | --- |
| Exit criteria | Monthly EVM position reviewed; actions assigned for at-risk metrics |

Exception and rejection handling:

- CPI/SPI ≥ 1.10 (too good): treat as a data-quality flag — verify progress claims and cost completeness before reporting.

- Progress data missing for the period: chase task owners; do not certify the monthly report with stale EV data.

## SOP-QS-10: Cost S-Curve Monitoring

| Who | QS Manager, Commercial Manager |
| --- | --- |
| When | Monthly or after major milestones |
| System Path | /dashboard/qs → Cost S-Curve tab |

### Procedure Steps

- Navigate to QS → BOQ & Budget → Cost S-Curve tab and select the project.

- Click “Capture Today” to record a progress snapshot — the system records current Planned Cost and Actual Cost at today's date.

- T

- K

- C

- B

Note — Planned Curve Source (updated in R3) The planned value on the S-curve now derives automatically from the approved time-phased budget baseline (SOP-QS-10A). Manual “Capture Today” planned entry is retained only as a fallback where no approved baseline exists, and such snapshots must be flagged as provisional.

### Workflow Control

Process status flow:

capture snapshot → curve update → variance check → trend review (repeat per period)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Snapshot cadence | At least one snapshot captured per calendar month; snapshots are timestamped and immutable | Procedure + system rule |
| G2 — Variance check | Negative cost variance at snapshot is cross-checked against Budget & Variance (SOP-QS-06) before reporting | Procedure |
| G3 — Trend divergence | Actual curve diverging above planned for two consecutive snapshots triggers EVM deep-dive (SOP-QS-09) | Procedure |

| Entry criteria | BOQ locked; cost transactions current |
| --- | --- |
| Exit criteria | Snapshot recorded; trend chart current for management reporting |

Exception and rejection handling:

- Missed monthly snapshot: capture immediately and note the gap — do not back-date snapshots.

## SOP-QS-10A: Time-Phased Budget Baseline & Cash Flow Forecast (NEW in R3)

| Who | QS Manager, Planner (schedule linkage), Finance Officer (cash flow) |
| --- | --- |
| When | After BOQ lock and baseline schedule approval; reviewed monthly |
| System Path | /dashboard/qs → Budget Baseline tab (new) |

This procedure converts the locked BOQ into a month-by-month planned spend distribution — the time-phased baseline. It is the single source of the planned S-curve (SOP-QS-10), the EVM Planned Value (SOP-QS-09), and the project cash flow forecast. Distribution is automatic from the schedule, with manual override where spend is not linear.

### Procedure Steps

- Navigate to QS → BOQ & Budget → Budget Baseline and select the project.

- Click “Generate Baseline” — the system auto-distributes each BOQ item value across calendar months using the planned start–finish dates of the linked WBS/task (linear spread by working days per month).

- Items without a schedule link appear in the Unallocated panel — allocate these manually across months.

- R

- Submit the baseline → QS Manager approves → status locked as Baseline Rev 0.

- Open the Cash Flow tab. The system derives: Cash Out = monthly cost forecast shifted by supplier/subcontractor payment terms; Cash In = forecast IPC certifications × (1 − retention %) shifted by certification and client payment terms; retention releases added at the PC and DLP months.

- R

- M

### Distribution Rules

| Case | Rule |
| --- | --- |
| Auto distribution | Item value spread linearly across the linked task's planned duration, by working days per month |
| Manual override | QS sets % per month for the item; the months must sum to exactly 100% of item value |
| Unlinked item | No schedule link — manual allocation only; item is flagged until allocated |
| Approved VO | Added to the forecast from its approval month, distributed per its schedule impact |
| Provisional item | Distributed like normal items but flagged; re-measurement updates flow through a baseline revision |

### Cash Flow Components

| Direction | Component | Timing Rule |
| --- | --- | --- |
| Cash In | Certified IPC value net of retention | Certification month + client payment terms (e.g., +30 days) |
| Cash In | Retention release — Practical Completion | PC month per contract (typically 50% of retained) |
| Cash In | Retention release — DLP completion | DLP end month (remaining retained) |
| Cash In | Advance payment (if applicable) | Per contract; recovered per recovery schedule as negative adjustment |
| Cash Out | Supplier payments | Cost month + supplier payment terms |
| Cash Out | Subcontractor payments (net of sub-retention) | Sub-IPC certification + subcontract payment terms |
| Cash Out | Preliminaries and running costs | Spread per baseline distribution |

### Workflow Control

Process status flow:

auto-generated → adjusted (manual overrides) → approved → locked (Rev 0) re-baseline: change request + reason → approved → Rev n (prior revisions retained for comparison)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Prerequisites | Baseline generation requires a locked BOQ and an approved baseline schedule; without both, generation is blocked | System rule |
| G2 — Override integrity | Manual monthly allocations must total exactly the item value — partial or excess distribution is rejected | System validation |
| G3 — Baseline lock | Rev 0 is immutable after approval; changes create a new revision with approver, reason, and comparison to prior revision retained | System rule + audit |
| G4 — Single source | EVM PV (SOP-QS-09) and the planned S-curve (SOP-QS-10) read only from the current approved baseline revision | System rule |
| G5 — Cash flow inputs | Payment terms and retention % are read from contract/subcontract records — no manual timing entry in the forecast | System rule |

| Entry criteria | BOQ locked (SOP-QS-05); baseline schedule approved; markup set locked (SOP-QS-05A) |
| --- | --- |
| Exit criteria | Baseline Rev 0 locked; planned S-curve and PV live; monthly cash flow forecast available to Finance |

Exception and rejection handling:

- Schedule re-baseline (EOT, acceleration): regenerate the forecast as a new baseline revision — never edit Rev 0.

- Persistent negative cash months: escalate to Commercial Director and Finance for facility arrangement or claim/IPC timing review.

- Large unallocated remainder (> 5% of contract sum): baseline cannot be approved until allocation is complete.

# 9. Phase 4 — Payment Certification

## SOP-QS-11: Interim Payment Certificate (IPC / Progress Claim)

| Who | Contractor QS (prepare), Client QS / Superintendent (certify) |
| --- | --- |
| When | Monthly, per contract payment interval |
| System Path | /dashboard/qs/claims |

### Procedure Steps — Contractor Side (Prepare Claim)

- Navigate to QS → Progress Claims and click “New Claim”.

- F

- Click “Initialize Items” — the system auto-populates claim items from the locked BOQ: Scheduled Value (from locked BOQ item total) and Previous Completed (sum from all prior certified or paid claims).

- F

- R

- Click “Submit” → status draft → submitted.

### Procedure Steps — Client Side (Review and Certify)

- C

- R

- Click “Mark Reviewed” → status submitted → client_reviewed.

- S

- Click “Certify” → the system automatically records the certified amount, certifier name, and timestamp; creates a retention deduction entry in qs_retention_ledger; and sets status client_reviewed → certified.

- When payment is received and banked: Finance clicks “Mark Paid” → status certified → paid.

### G702 Summary

| G702 Field | Source |
| --- | --- |
| Original Contract Sum | Locked BOQ total |
| Net VO Amount | Sum of all approved VOs |
| Contract Sum to Date | Original + Net VO |
| Total Completed & Stored | Sum of all claim item amounts |
| Less Retention | Total × Retention % |
| Less Previous Certificates | Sum of all prior certified/paid claims |
| Current Payment Due | Total − Retention − Previous Certificates |

### Percentage Complete Calculation

% Complete (item) = Total to Date ÷ Scheduled Value × 100 Total to Date = Previous Completed + This Period + Materials Stored

### Workflow Control

Process status flow:

draft → submitted → client_reviewed → certified → paid

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Baseline dependency | A claim can only be created against a locked BOQ; scheduled values are read-only copies of locked items | System rule |
| G2 — Over-claim block | This Period + Previous Completed + Materials Stored cannot exceed the item's Scheduled Value | System validation |
| G3 — One open claim | Only one claim per project may be open (pre-certified) at a time; the next claim initializes from the last certified claim | System rule |
| G4 — Client adjustment trace | Every client adjustment requires an amount and reason; claimed vs certified difference is stored per item | System rule + audit |
| G5 — Certification effects | Certification atomically records certifier + timestamp and auto-creates the retention deduction — no manual retention entry | System automation |
| G6 — Payment | Only Finance may set paid; paid claims are immutable and feed Previous Certificates for the next claim | RBAC + system rule |

| Entry criteria | Locked BOQ; approved VOs current; period progress measured |
| --- | --- |
| Exit criteria | IPC certified and paid; retention ledger updated; cumulative certified-to-date carried forward |

Exception and rejection handling:

- Client certifies less than claimed: the certified amount governs; the difference and reasons are retained in the claim record for Final Account negotiation.

- Claim rejected outright: return to draft, correct measurements/evidence, resubmit within the same period where possible.

- Materials stored disputed: provide delivery dockets and storage evidence; unresolved amounts are removed from the current claim and re-claimed next period.

## SOP-QS-12: Retention Register Management

| Who | QS Manager, Finance Officer |
| --- | --- |
| When | Automatic on IPC certification; manual at Practical Completion and DLP |
| System Path | /dashboard/qs/retention |

### Retention Deductions (Automatic)

- When an IPC is certified, a retention deduction entry is automatically created.

- The amount deducted = retention_amount from the certified IPC.

- Entry type = deduction, approval status = approved (auto-approved on certification).

### Viewing the Register

- Navigate to QS → Retention and select the project.

- R

- T

### Release Requests

- When a release trigger is reached, click “Request Release”.

- F

- Submit → approval status pending.

- QS Manager or Director reviews and clicks “Approve” or rejects with reason.

- On approval → status approved, and the outstanding balance updates.

### Standard Retention Split

| Event | Release % | Typical Timing |
| --- | --- | --- |
| Practical Completion | 50% of total deducted | On issuance of PC Certificate |
| DLP Completion | Remaining 50% | End of Defects Liability Period (typically 12 months) |

### Workflow Control

Process status flow:

deduction: IPC certified → auto deduction entry (approved) release: trigger reached → request → pending → approved / rejected

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Auto deduction | Deductions are created only by IPC certification — manual deduction entries are not permitted | System automation |
| G2 — Release trigger evidence | Release request must cite the trigger certificate (PC Certificate or DLP sign-off) in the notes | Procedure |
| G3 — Release ceiling | Release amount cannot exceed the outstanding balance; PC release is capped at the contractual % (typically 50%) | System validation |
| G4 — Release approval | QS Manager or Director approval required; rejection requires a reason; decision recorded with identity and timestamp | RBAC + audit |

| Entry criteria | At least one certified IPC (for deductions); PC/DLP certificate issued (for releases) |
| --- | --- |
| Exit criteria | Outstanding retention balance accurate; releases traceable to contract triggers |

Exception and rejection handling:

- Retention bond substituted for cash retention: record bond details in notes and suspend further deductions per contract terms.

- Client delays release beyond expected date: escalate via Contract Admin notice (SOP-QS-17 and Notice register) — retention receivable is a contractual entitlement.

# 10. Phase 5 — Portfolio Reporting

## SOP-QS-13: Portfolio Dashboard

| Who | Commercial Director, CFO, Executive Team |
| --- | --- |
| When | Weekly or monthly executive review |
| System Path | /dashboard/qs → Portfolio tab |

### Procedure Steps

- Navigate to QS → BOQ & Budget → Portfolio tab.

- R

- R

- A

- U

### Project Comparison Columns

| Column | Description |
| --- | --- |
| Project | Project name and code |
| Budget | Total locked BOQ |
| Actual | Total cost transactions |
| Variance % | (Budget − Actual) ÷ Budget |
| Progress % | Weighted task completion |
| CPI | Cost Performance Index |
| SPI | Schedule Performance Index |
| EAC | Estimate at Completion |
| Health | On Track / At Risk badge |

### Workflow Control

Process status flow:

executive cycle: review portfolio KPIs → drill into at-risk projects → assign management actions → track to next review

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Source integrity | Portfolio figures aggregate only from locked BOQs, recorded transactions, and computed EVM — no manual portfolio adjustments | System rule |
| G2 — At-risk flag | Projects flagged at-risk must have a named owner and action recorded at the executive review | Procedure |
| G3 — Access | Portfolio view restricted to Commercial Director, CFO, and Executive roles | RBAC |

| Entry criteria | Project EVM data refreshed for the period |
| --- | --- |
| Exit criteria | Portfolio position reviewed; at-risk actions assigned |

Exception and rejection handling:

- Project missing from portfolio: verify the BOQ is locked — unlocked projects have no budget baseline and are excluded from EAC aggregation.

# 11. Phase 6 — Close-Out

## SOP-QS-14: Final Account (in development)

| Who | QS Manager, Commercial Manager |
| --- | --- |
| When | After Practical Completion, before end of DLP |
| System Path | TBD |

### Procedure Steps (future implementation)

- Ensure all Variation Orders are in implemented status.

- A

- E

- P

- S

- O

- Issue the Final Certificate, triggering the final retention release (if DLP has ended).

### Workflow Control

Process status flow:

pre-checks complete → draft final account → client agreement → final contract sum locked → final certificate → final retention release

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Pre-check | No open VOs, no provisional items unmeasured, no unfinalised subcontractor accounts before drafting | Procedure + system check |
| G2 — Reconciliation | Final Contract Sum reconciles to cumulative certified IPCs plus final adjustments — differences must be explained line by line | Procedure |
| G3 — Client agreement | Final Account is binding only on client signature; the signed statement is filed in Document Control | Procedure |
| G4 — Final certificate | Final Certificate issuance triggers the final retention release request (SOP-QS-12) — not before DLP completion | System rule |

| Entry criteria | Practical Completion certified; DLP running or complete |
| --- | --- |
| Exit criteria | Final Contract Sum agreed and signed; project commercially closed |

Exception and rejection handling:

- Client disputes final measurement: unresolved items move to Claims & Disputes; agreed items are certified to keep cash flowing.

## SOP-QS-14A: Final QS Cost Report (NEW in R3)

| Who | QS Manager (prepare), Commercial Director (approve), Document Controller (issue) |
| --- | --- |
| When | At Final Account stage, alongside SOP-QS-14 |
| System Path | /dashboard/qs → Final Cost Report (new) |

Two-Version Rule The Final QS Cost Report exists in two versions generated from the same data. The INTERNAL version shows the complete commercial picture — budget, actual cost, sell value, and margin. The CLIENT version shows the sell side only — contract sum, variations, certified value, retention, and balance due. Internal cost and margin figures are never included in the client version; the system template physically contains no cost/margin fields, so exposure by editing error is impossible.

### Internal Final Cost Report — Columns (per BOQ item, section/trade, and project)

| Column | Source / Definition |
| --- | --- |
| Budget (Cost) | Cost baseline: Σ cost_rate × final quantity per item |
| Final Actual Cost | Σ approved/paid cost transactions allocated to the item |
| Cost Variance | Budget − Actual (positive = saving) |
| Contract Value (Sell) | Σ sell_rate × final quantity + approved VO values |
| Certified to Date | Cumulative certified from all IPCs |
| Final Margin | Sell − Actual Cost, per item and rolled up |
| Final Margin % | (Sell − Actual Cost) ÷ Sell × 100 |
| Tender Margin % | Expected margin at BOQ lock (SOP-QS-05A) |
| Margin Variance | Final Margin % − Tender Margin % (margin erosion / gain) |

### Client Final Statement — Columns (sell side only)

| Line | Source |
| --- | --- |
| Original Contract Sum | Locked BOQ total at sell rates |
| Approved Variation Orders | Net approved VO value |
| Remeasurement Adjustments | Final measured quantities × contract sell rates (provisional items) |
| Final Contract Sum | Original + VOs ± remeasurement |
| Total Certified to Date | Cumulative certified IPCs |
| Retention Outstanding | Retention ledger balance |
| Balance Due | Final Contract Sum − Total Certified + Retention releases due |

### Procedure Steps

- C

- Generate the Internal Final Cost Report; review margin variance versus tender margin per trade — this is the project's commercial lessons-learned record.

- QS Manager review → Commercial Director approval → internal version archived (status approved).

- Generate the Client Final Statement — the system renders sell-side fields only, from the approved data set.

- I

- O

### Workflow Control

Process status flow:

draft → internal review → Director approved → client version generated → issued (transmittal) → signed → archived & locked

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Pre-check dependency | Report generation is blocked until SOP-QS-14 pre-checks pass (no open VOs, transactions closed, sub accounts final) | System rule |
| G2 — Reconciliation | Final Contract Sum must reconcile line-by-line to cumulative certified IPCs plus final adjustments; unexplained differences block approval | System validation + procedure |
| G3 — Version firewall | Client version is generated from a template containing no cost/margin fields; manual editing of the client statement is prohibited | System rule |
| G4 — Access | Internal version visible to QS Manager+, Commercial Director, and Finance only | RBAC |
| G5 — Issue control | Client version leaves the system only via a Document Control transmittal — direct download/export to external parties is blocked | System rule + audit |

| Entry criteria | Final Account in progress (SOP-QS-14); Practical Completion certified |
| --- | --- |
| Exit criteria | Internal report approved and archived; signed client statement filed; project margin history feeds the unit rate library and future tender pricing |

Exception and rejection handling:

- Client demands cost breakdown (open-book request): release requires Commercial Director approval and a contractual open-book basis — record the decision and scope of disclosure.

- Disputed final items: split the client statement into agreed and disputed sections; certify and close the agreed portion, route disputed items to Claims & Disputes.

# 12. Subcontractor Management (in development)

## SOP-QS-15: Subcontractor IPC (Sub-IPC)

| Who | QS Engineer, Subcontract Manager |
| --- | --- |
| When | Monthly, per subcontract payment terms |
| System Path | /dashboard/qs/subcontractors/sub-ipc (TBD) |

### Procedure Steps (future implementation)

- Navigate to QS → Subcontractors → Sub-IPCs.

- C

- A

- I

- Sub-IPC status: draft → submitted → certified → paid.

- T

### Workflow Control

Process status flow:

draft → submitted → certified → paid (mirrors head-contract IPC, with retention deducted per subcontract terms)

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Subcontract baseline | Sub-IPC is assessed only against the agreed subcontract BOQ/schedule of rates | System rule |
| G2 — Assessment authority | Certified value is the assessor's value, not the claimed value; differences recorded with reasons | Procedure + audit |
| G3 — Retention mirror | Retention is deducted from each Sub-IPC per subcontract terms, mirroring head-contract treatment | System automation |
| G4 — Back-charge deduction | Agreed back charges (SOP-QS-16) are deducted before certification | System rule |
| G5 — Cost linkage | Certification auto-creates a Subcontract-category cost transaction against the main contract budget | System automation |

| Entry criteria | Executed subcontract with BOQ/schedule of rates loaded |
| --- | --- |
| Exit criteria | Sub-IPC certified and paid; subcontract cost reflected in project budget |

Exception and rejection handling:

- Subcontractor disputes assessment: record the dispute against the Sub-IPC; pay the undisputed certified amount on time.

## SOP-QS-16: Back Charges

| Who | QS Engineer, Site Manager |
| --- | --- |
| When | When costs are incurred due to subcontractor default |
| System Path | /dashboard/qs/subcontractors/back-charges (TBD) |

### Procedure Steps (future implementation)

- Navigate to QS → Subcontractors → Back Charges.

- C

- A

- D

- N

### Workflow Control

Process status flow:

raised → notified → accepted / disputed → agreed amount → deducted from next Sub-IPC → closed

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Evidence | A back charge cannot be raised without attached evidence (instruction, photos, day work sheets) | System validation |
| G2 — Formal notice | Subcontractor must be formally notified before deduction — notice reference recorded | Procedure + audit |
| G3 — Dispute window | Deduction applies only after acceptance or expiry of the contractual dispute window | Procedure |
| G4 — Deduction trace | The deduction is itemised on the Sub-IPC and cross-referenced to the back-charge record | System rule |

| Entry criteria | Cost incurred due to subcontractor default, with evidence |
| --- | --- |
| Exit criteria | Agreed amount deducted and back charge closed |

Exception and rejection handling:

- Subcontractor disputes the charge: hold the deduction, escalate through Contract Admin; deduct only the finally agreed amount.

# 13. Contract Administration (in development)

## SOP-QS-17: Employer Instructions (EIs)

| Who | QS Manager, Contract Administrator |
| --- | --- |
| When | On receipt of instruction from client or superintendent |
| System Path | /dashboard/qs/contract-admin/instructions (TBD) |

### EI Register Fields (planned)

| Field | Description |
| --- | --- |
| EI Number | Sequential number (EI-YYYY-NNNN) |
| Date Issued | Date instruction received |
| Issued By | Client representative / Superintendent |
| Description | Full instruction narrative |
| Contract Reference | Applicable contract clause |
| Cost Impact | Estimated cost effect |
| Time Impact | Estimated programme effect (days) |
| VO Reference | Linked VO raised in response |
| Status | Open / Responded / Closed |

### Workflow Control

Process status flow:

received → registered (open) → impact assessed → responded (notice / VO raised) → closed

Control gates:

| Gate | Control Applied | Enforced By |
| --- | --- | --- |
| G1 — Same-day registration | Every EI is registered on the day of receipt with the contract clause reference | Procedure |
| G2 — Time-bar control | Contractual notice deadlines are tracked from the EI date; the system alerts before expiry — missing a time bar forfeits entitlement | System alert + procedure |
| G3 — Impact assessment | Cost and time impact assessed before response; EIs with impact must link to a VO (SOP-QS-08) or entitlement record | Procedure + system rule |
| G4 — Closure | An EI closes only when the response is issued and any linked VO is approved or formally withdrawn | System rule |

| Entry criteria | Instruction received from client or superintendent |
| --- | --- |
| Exit criteria | EI responded within the contractual notice period; entitlement preserved |

Exception and rejection handling:

- Verbal instruction received on site: confirm in writing to the issuer within 24 hours and register the confirmation as the EI.

- Instruction with no apparent cost/time impact: register and close with a nil-impact assessment — never leave EIs unregistered.

# 14. Gap Register & Implementation Status

| Gap ID | Description | Priority | Status |
| --- | --- | --- | --- |
| GAP-01 | RBAC not enforced on QS components | Critical | Open |
| GAP-02 | Multi-step VO approval not role-wired | Critical | Open |
| GAP-03 | Tendering module — no frontend implementation | High | Open |
| GAP-04 | Contract Administration module — zero implementation | High | Open |
| GAP-05 | Subcontractor management — zero implementation | High | Open |
| GAP-06 | Payment voucher integration with certified IPCs | High | Open |
| GAP-07 | Budget revision approval workflow UI | Medium | Open |
| GAP-08 | QS KPIs absent from Executive Dashboard | Medium | Open |
| GAP-09 | No PDF/report generation (IPC, BOQ, VO, Retention) | Medium | Open |
| GAP-10 | Cost code breakdown not shown in budget analysis | Medium | Open |
| GAP-11 | No time-phased planned cash flow baseline | Medium | Designed — SOP-QS-10A (R3) |
| GAP-12 | No contingency reserve drawdown tracking | Medium | Open |
| GAP-13 | VO approval audit trail not visible in UI | Medium | Open |
| GAP-14 | No email/notification triggers for approvals | Low | Open |
| GAP-15 | No Excel/CSV export for BOQ, budget, claim reports | Low | Open |
| GAP-16 | No multi-currency support on QS tables | Low | Open |
| GAP-17 | No audit log viewer for QS transactions | Low | Open |
| GAP-18 | WBS-level budget rollup not in WBS tree view | Low | Open |
| GAP-19 | Dual-rate (cost/sell) fields and markup engine not implemented (SOP-QS-05A) | High | Designed — build pending |
| GAP-20 | Monthly baseline generation and cash flow forecast UI not implemented (SOP-QS-10A) | High | Designed — build pending |
| GAP-21 | Final QS Cost Report generation (internal + client versions) not implemented (SOP-QS-14A) | High | Designed — build pending |

# 15. Roles & Responsibilities Matrix (RACI)

| Activity | QS Engineer | QS Manager | PM | Commercial Director | Finance |
| --- | --- | --- | --- | --- | --- |
| Cost Library maintenance | C | A/R | I | I | — |
| BOQ creation | R | A | C | I | — |
| BOQ approval | C | R/A | C | I | — |
| BOQ lock | — | R/A | C | I | — |
| Budget monitoring | R | A | C | I | I |
| Cost transaction entry | R | A | I | — | C |
| VO creation | R | A | C | I | — |
| VO approval (<$5K) | C | I | A/R | — | — |
| VO approval ($5K–$50K) | — | R | A | I | — |
| VO approval (≥$50K) | — | C | C | A/R | — |
| IPC preparation | R | A | C | I | — |
| IPC certification | — | C | C | I | A/R |
| Retention release request | C | R/A | C | I | C |
| Retention release approval | — | C | — | A/R | C |
| Markup settings approval | C | R | C | A | — |
| Monthly baseline approval | R | A | C | I | C |
| Cash flow forecast review | C | R/A | I | I | C |
| Final cost report (internal) | C | R | C | A | C |
| Client final statement issue | — | R | C | A | I |
| Portfolio reporting | C | R | C | A | I |

R = Responsible,  A = Accountable,  C = Consulted,  I = Informed

# 16. Document Control

| Field | Value |
| --- | --- |
| Document Number | SOP-QS-001 |
| Title | Quantity Surveying Module SOP |
| Revision | R3 |
| Prepared By | DCOS Commercial Team |
| Reviewed By | QS Manager |
| Approved By | Commercial Director |
| Issue Date | 2026-07-12 |
| Next Review | 2027-01-12 |
| Storage Location | docs/01-Governance/01-SOP/22-SOP-Quantity-Surveying/ |

## Revision History

| Revision | Date | Description | Author |
| --- | --- | --- | --- |
| R1 | 2026-06-06 | Initial issue (Markdown working version) | DCOS Commercial Team |
| R2 | 2026-07-12 | Word standard issue — added Definitions, master workflow map, and Workflow Control (flow, control gates, entry/exit criteria, exception handling) for every procedure SOP-QS-01 to SOP-QS-17 | DCOS Commercial Team |
| R3 | 2026-07-12 | Added SOP-QS-05A Rate Build-Up & Margin Application (dual cost/sell rates, component markups, visibility firewall); SOP-QS-10A Time-Phased Budget Baseline & Cash Flow Forecast (auto distribution from schedule with manual override, monthly cash in/out); SOP-QS-14A Final QS Cost Report (internal full-cost + client sell-side versions). Updated definitions, database tables, master workflow map, golden rules, S-curve source note, gap register (GAP-19–21), and RACI | DCOS Commercial Team |

End of Document — SOP-QS-001 R3