## Slide 1
DCOS SYSTEM ARCHITECTURE
Multi-Project AI-Assured
Telegram Daily Reporting
Architecture · Setup · Roles · Process · Controls
Database is system of record · Telegram is field interface · AI assures · PM decides

## Slide 2
OVERVIEW
Master Content
DCOS · Daily Reporting Architecture
02 / 21
03
Master Principle & Hierarchy
04
Master System Architecture
05
System Ownership Model
06
Traditional vs DCOS System
07
Telegram Integration Layer
08
Telegram Group Naming Convention
09
Setup Group & Assign Bot
10
Subcontractor User Creation
11
Roles & Permissions
12
Mini App R03 — Report Form
13
End-to-End Data Flow
14
Ruleset Catalogue
15
AI Specialist Agents
16
AI Scoring Flow & Thresholds
17
Scoring Decision Logic
18
PM Review UI
19
Report Lifecycle & Correction
20
Project Summary & Management
21
Authoritative Chain

## Slide 3
FOUNDATION
Master Principle & Hierarchy
DCOS · Daily Reporting Architecture
03 / 21
Many Projects → Many Subcontractors → One Telegram Group per SC per Project
→ DCOS Database → AI Assurance → PM Approval → Verified Data → Management
MULTI-PROJECT
Portfolio control
PROJECT
WBS · Schedule · PM
SUBCONTRACTOR
Discipline · Scope
TELEGRAM GROUP
1 Project + 1 SC
CORE MAPPING RULE
One Project + One Subcontractor = One Telegram Project Group
Group → Project → Subcontractor → Discipline / Scope → Assigned WBS · Mapping lives in DCOS

## Slide 4
ARCHITECTURE
Master System Architecture
DCOS · Daily Reporting Architecture
04 / 21
MULTI-PROJECT PORTFOLIO
SC-A1 Group
SC-A2 Group
SC-B1 Group
SC-C1 Group
Bot + Mini App
→
DCOS API
→
DCOS Database
RULES ENGINE
Deterministic validation — fields, ranges, WBS,
deadlines, duplicates → structured ERROR / WARN
AI ASSURANCE LAYER
Orchestrator + specialist agents — findings,
dimension scoring, consolidation → PM package
PM REVIEW
Approve or Return
PROJECT SUMMARY
Approved SC data only
MANAGEMENT
Multi-project dashboard

## Slide 5
GOVERNANCE
System Ownership Model
DCOS · Daily Reporting Architecture
05 / 21
Subcontractor
Submit factual field information
Telegram Group
Communication + reporting entry point
DCOS Bot
Identity, context, triggers, notifications
Mini App
Structured report entry form
DCOS API
Auth, validation, persistence, events
Database
System of record — authoritative
Rules Engine
Deterministic validation
AI Assurance
Check, interpret, score, recommend
PM
Final review and approval authority
Management
Consume approved information only

## Slide 6
WHY CHANGE
Traditional Way vs DCOS System
DCOS · Daily Reporting Architecture
06 / 21
TRADITIONAL
DCOS SYSTEM
Paper / Excel / WhatsApp chat
Structured Mini App form
No single system of record
DCOS Database is authoritative
Hard to verify completeness
Rules + AI completeness checks
Progress claims unchecked
Progress / manpower anomaly flags
PM reads hundreds of messages
PM reviews scored assurance pack
Corrections informal / lost
Structured return loop + audit
Management sees raw noise
Only PM-approved summaries

## Slide 7
INTERFACE
Telegram Integration Layer
DCOS · Daily Reporting Architecture
07 / 21
Project Group
One group = one project + one SC
Coordination and site chat
Formal “Submit Daily Report”
Evidence and notifications
Chat is never official data
DCOS Bot
Identify group and user
Resolve project / SC context
Verify authorization
Launch Mini App (R03)
Status and correction alerts
Mini App (R03)
Structured reporting form
Standard + custom fields
Manpower, progress, issues
Photos and documents
Submit only via DCOS API

## Slide 8
SETUP
Telegram Group Naming Convention
DCOS · Daily Reporting Architecture
08 / 21
Standard format ensures one group maps cleanly to one Project + one Subcontractor in DCOS.
FORMAT
DCOS | {PROJECT_CODE} | {SC_SHORT_NAME} | {DISCIPLINE}
EXAMPLES
DCOS | PRJ-001 | ABC Masonry | Masonry
Project PRJ-001 · SC ABC · Discipline Masonry
DCOS | PRJ-001 | XYZ MEP | MEP
Project PRJ-001 · SC XYZ · Discipline MEP
DCOS | PRJ-002 | SteelCo | Structural
Project PRJ-002 · SC SteelCo · Discipline Structural

## Slide 9
SETUP
Create Telegram Group & Assign Bot
DCOS · Daily Reporting Architecture
09 / 21
1
Create group
Create a new Telegram group. Apply the standard naming convention.
2
Add DCOS Bot
Search and add the official DCOS Bot as a member of the group.
3
Promote bot
Make the bot an administrator (required for group identity resolution).
4
Register in DCOS
In DCOS admin: map Group ID → Project → Subcontractor → Discipline / WBS.
5
Verify
Bot posts confirmation. Users with access can open Mini App R03.

## Slide 10
SETUP
Subcontractor User Creation Flow
DCOS · Daily Reporting Architecture
10 / 21
01
Create company
Register subcontractor company in DCOS (name, discipline, contacts).
02
Assign to project
Link company to project with scope, WBS, and reporting requirements.
03
Add users
Create site users: name, role, Telegram ID / username, contact.
04
Grant access
Assign project + SC permissions. Only authorized users can submit.
05
Join group
Users join the mapped Telegram Project Group for that SC assignment.
06
Activate
Bot recognizes authorized users. Mini App R03 becomes available.

## Slide 11
ACCESS CONTROL
Roles & Permissions — Site System vs Telegram Bot
DCOS · Daily Reporting Architecture
11 / 21
Role
DCOS Site System
Telegram Bot / Group
SC Site User
Submit own reports only
Open Mini App in own group only
SC Supervisor
View team reports; submit
Same group; may receive alerts
PM
Review / approve all SCs
Not in SC groups (dashboard only)
Project Admin
Map groups, users, WBS
Add bot; register Group ID
Management
Read approved summaries
No Telegram field access
DCOS Bot
N/A (service account)
Resolve context; launch Mini App

## Slide 12
FIELD INTERFACE · R03
Telegram Mini App — Daily Site Report
DCOS · Daily Reporting Architecture
12 / 21
‹ DCOS Bot
Daily Report
📋 Daily Site Report
Step 1 of 1
PRJ-001 · Building A · ABC Masonry
STANDARD FIELDS
Report Date
Contractor
04 Oct 2026
ABC Masonry
Discipline
Location
Masonry
Building A · L06 · Z03 ▾
Activity
Blockwork ▾
Manpower
Progress
24 workers
65%
Issue / Constraint
No issue
Tomorrow Plan
Continue L06 blockwork
Save Draft
Submit Report →
R03 · Form Structure
Standard Fields
· Report Date, Contractor (auto)
· Discipline, Location (WBS zone)
· Activity, Manpower, Progress %
· Issue / Constraint, Tomorrow Plan
Custom Fields
· Per SC / discipline template
· e.g. Wall Type, Thickness, Area
· Extensible without schema change
Evidence
· Photos & documents
· Linked to report + activity
· Timestamped on submit

## Slide 13
PROCESS
End-to-End Data Flow
DCOS · Daily Reporting Architecture
13 / 21
01
Submit
Mini App R03
02
API
Store
03
Rules
Validate
04
AI
Score
05
PM
Decide
06
Summary
Publish
1 Subcontractor → Telegram Group → Bot → Mini App (R03) → DCOS API → Raw report stored
2 Rules Engine returns structured ERROR / WARNING results
3 AI Orchestrator runs specialist agents → findings + dimension scores
4 Consolidation builds the PM assurance package
5 APPROVE → verified data → project summary → management dashboard
6 RETURN → structured correction → SC re-submit → full cycle repeats

## Slide 14
CONTROLS
Rules Engine — Ruleset Catalogue
DCOS · Daily Reporting Architecture
14 / 21
Rule ID
Severity
Description
REQ_FIELD
ERROR
Required field missing
PROGRESS_MAX
ERROR
Progress exceeds 100%
INVALID_WBS
ERROR
WBS / activity not valid for subcontractor
INVALID_PROJ
ERROR
Project / subcontractor mismatch
DUPLICATE
ERROR
Duplicate report for same date and SC
UNIT_MISMATCH
ERROR
Unit inconsistent with activity
STATUS_RULE
ERROR
Invalid work status transition
DEADLINE
WARN
Submitted after reporting deadline
EVIDENCE_REQ
WARN / ERR
Required evidence missing (configurable)
MANPOWER_MIN
WARN
Manpower below planned threshold
QTY_RANGE
WARN / ERR
Quantity outside configured range

## Slide 15
ASSURANCE
AI Specialist Agents
DCOS · Daily Reporting Architecture
15 / 21
Orchestrator coordinates agents through structured inputs and outputs — no free-form agent dialogue.
Completeness
Missing fields, evidence, plans
Validation
Values, logic, units, references
Progress
History, baseline, schedule
Manpower
Plan vs reported vs output
Cross-Report
Conflicts across SCs and days
Evidence
Existence, relevance, support
Anomaly
Unusual patterns and risks
Recommend
Actions for PM decision

## Slide 16
ASSURANCE
AI Scoring Flow & Thresholds
DCOS · Daily Reporting Architecture
16 / 21
1
Rules first
Hard errors
flagged first
2
Run agents
Parallel
specialist checks
3
Score dims
Weighted
dimension scores
4
Consolidate
Findings +
recommendation
5
PM package
Ready for
human review
Configurable dimension thresholds (illustrative)
Dimension
Weight
Pass ≥
Review <
Fail <
Completeness
20%
90
70
70
Validation / Consistency
25%
85
60
60
Progress plausibility
20%
80
55
55
Evidence quality
20%
80
50
50
Manpower / Cross-check
15%
75
50
50

## Slide 17
ASSURANCE
Scoring Decision Logic
DCOS · Daily Reporting Architecture
17 / 21
CRITICAL ERROR
Any Rules Engine ERROR
or dimension below Fail
Status: BLOCKED / RETURN
Correction auto-prepared
PM still receives package
REVIEW REQUIRED
No hard ERROR present
Score in Review band
or AI WARNING findings
Status: PM_REVIEW
Recommendation attached
READY TO APPROVE
All dimensions at Pass
No critical findings
Status: PM_REVIEW
Suggest APPROVE
PM remains final authority

## Slide 18
DECISION
PM Review — After AI Assurance
DCOS · Daily Reporting Architecture
18 / 21
DR-0048 · PRJ-001 · ABC Masonry · 04 Oct 2026
REVIEW REQUIRED
ASSURANCE SCORES
Completeness
92
Consistency
78
Progress
61
Evidence
55
Manpower
88
KEY FINDINGS
· Progress 3× historical average
· Evidence for Area B insufficient
· Manpower within planned range
· Completeness checks passed
· No cross-SC conflict detected
RECOMMENDATION
Request clarification
and additional
evidence
PM ACTIONS
APPROVE
RETURN
REQUEST INFO

## Slide 19
PROCESS
Report Lifecycle & Correction Loop
DCOS · Daily Reporting Architecture
19 / 21
DRAFT
→
SUBMITTED
→
VALIDATING
→
AI REVIEW
→
PM REVIEW
APPROVE PATH
1 PM approves the report
2 Data marked verified
3 Included in project daily summary
4 Rolled into multi-project view
5 Full audit trail retained
RETURN PATH
1 PM returns for correction
2 AI prepares structured request
3 SC notified via Telegram
4 Correct and re-submit
5 Full AI + PM cycle repeats

## Slide 20
OUTPUTS
Project Summary & Management Reporting
DCOS · Daily Reporting Architecture
20 / 21
Project Daily Summary
Approved SC reports consolidated
Overall manpower and progress
Completed, ongoing, delayed work
Issues, constraints, materials
Equipment and next-day plan
Schedule risks and open findings
Only PM-approved data included
Management Dashboard
Project status overview
Reporting compliance rates
Manpower and progress trends
Major issues and delays
Critical risks and constraints
Subcontractor performance
Cross-project comparison

## Slide 21
AUTHORITATIVE CHAIN
Subcontractor → Report → DCOS → AI Assurance
→ PM Approval → Verified Data → Management
Telegram
Field interface only
DCOS Database
System of record
Rules Engine
Deterministic control
AI
Assurance and consultation
PM
Final human authority
Management
Approved-data consumer
Never confuse communication with formal reporting · AI recommendation with PM approval · submission with verified data