## Master WBS
WBS Code | Level Breakdown | Activity / Work Package | Type | Discipline | Floor / Area | Duration (Days) | Baseline Start | Baseline Finish | Predecessors | Resources | Cost Code | Notes / Remarks
0 | 0 | PROJECT - 7 FLOOR BUILDING | Project |  |  | 731 | 01-Oct-2026 | 30-Sep-2028 |  | PM Team | PRJ-000 | Master Project
01 | 1 | DESIGN & ENGINEERING | Phase | Design |  | 182 | 01-Oct-2026 | 31-Mar-2027 |  | PM Team | D-1000 | Produce approved design information
01.01 | 2 | DESIGN MANAGEMENT | Work Package | Design |  | 182 | 01-Oct-2026 | 31-Mar-2027 | 01 | Design Manager, Consultants | D-1100
01.01.01 | 3 | Design Brief | Activity | Design |  | 11 | 01-Oct-2026 | 11-Oct-2026 | 01.01 | Design Manager, Client, Consultants | D-1100
01.01.02 | 3 | Design Criteria | Activity | Design |  | 8 | 13-Oct-2026 | 20-Oct-2026 | 01.01.01 | Design Manager, Client, Consultants | D-1100
01.01.03 | 3 | Design Programme | Activity | Design |  | 6 | 26-Oct-2026 | 31-Oct-2026 | 01.01.02 | Design Manager, Client, Consultants | D-1100
01.01.04 | 3 | Design Responsibility Matrix | Activity | Design |  | 6 | 08-Nov-2026 | 13-Nov-2026 | 01.01.03 | Design Manager, Client, Consultants | D-1100
01.01.05 | 3 | Design Deliverable Register | Activity | Design |  | 6 | 21-Nov-2026 | 26-Nov-2026 | 01.01.04 | Design Manager, Client, Consultants | D-1100
01.01.06 | 3 | Design Interface Matrix | Activity | Design |  | 6 | 04-Dec-2026 | 09-Dec-2026 | 01.01.05 | Design Manager, Client, Consultants | D-1100
01.01.07 | 3 | Design Coordination Meetings | Activity | Design |  | 105 | 17-Dec-2026 | 31-Mar-2027 | 01.01.06 | Design Manager, Client, Consultants | D-1100
01.01.08 | 3 | Design Review | Activity | Design |  | 11 | 30-Dec-2026 | 09-Jan-2027 | 01.01.07 | Design Manager, Client, Consultants | D-1100
01.01.09 | 3 | Client Review | Activity | Design |  | 11 | 12-Jan-2027 | 22-Jan-2027 | 01.01.08 | Design Manager, Client, Consultants | D-1100
01.01.10 | 3 | Consultant Review | Activity | Design |  | 11 | 25-Jan-2027 | 04-Feb-2027 | 01.01.09 | Design Manager, Client, Consultants | D-1100
01.01.11 | 3 | Authority Submission | Activity | Design |  | 16 | 07-Feb-2027 | 22-Feb-2027 | 01.01.10 | Design Manager, Client, Consultants | D-1100
01.01.12 | 3 | Authority Approval | Activity | Design |  | 31 | 20-Feb-2027 | 22-Mar-2027 | 01.01.11 | Design Manager, Client, Consultants | D-1100
01.01.13 | 3 | Design Change Management | Activity | Design |  | 27 | 05-Mar-2027 | 31-Mar-2027 | 01.01.12 | Design Manager, Client, Consultants | D-1100
01.01.14 | 3 | IFC Release | Activity | Design |  | 6 | 18-Mar-2027 | 23-Mar-2027 | 01.01.13 | Design Manager, Client, Consultants | D-1100
01.02 | 2 | 01.02 ARCHITECTURAL DESIGN | Work Package | Architectural |  | 151 | 01-Oct-2026 | 28-Feb-2027 | 01.01 | Design Manager, Consultants | D-1200
01.02.01 | 3 | Architectural Design Brief | Activity | Architectural |  | 16 | 01-Oct-2026 | 16-Oct-2026 | 01.01.01 | Architect, Draftsman | D-1200
01.02.02 | 3 | Space Planning | Activity | Architectural |  | 16 | 06-Oct-2026 | 21-Oct-2026 | 01.02.01 | Architect, Draftsman | D-1200
01.02.03 | 3 | Floor Plans | Activity | Architectural |  | 21 | 11-Oct-2026 | 31-Oct-2026 | 01.02.02 | Architect, Draftsman | D-1200
01.02.04 | 3 | Elevations | Activity | Architectural |  | 21 | 16-Oct-2026 | 05-Nov-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.05 | 3 | Sections | Activity | Architectural |  | 21 | 22-Oct-2026 | 11-Nov-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.06 | 3 | Roof Plan | Activity | Architectural |  | 11 | 27-Oct-2026 | 06-Nov-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.07 | 3 | Door Schedule | Activity | Architectural |  | 13 | 01-Nov-2026 | 13-Nov-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.08 | 3 | Window Schedule | Activity | Architectural |  | 13 | 06-Nov-2026 | 18-Nov-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.09 | 3 | Finishes Schedule | Activity | Architectural |  | 13 | 12-Nov-2026 | 24-Nov-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.10 | 3 | Room Data Sheets | Activity | Architectural |  | 16 | 17-Nov-2026 | 02-Dec-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.11 | 3 | Toilet Details | Activity | Architectural |  | 16 | 22-Nov-2026 | 07-Dec-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.12 | 3 | Stair Details | Activity | Architectural |  | 16 | 27-Nov-2026 | 12-Dec-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.13 | 3 | Façade Design | Activity | Architectural |  | 26 | 02-Dec-2026 | 27-Dec-2026 | 01.02.04 | Architect, Draftsman | D-1200
01.02.14 | 3 | Ceiling Plans | Activity | Architectural |  | 13 | 08-Dec-2026 | 20-Dec-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.15 | 3 | Flooring Layout | Activity | Architectural |  | 13 | 13-Dec-2026 | 25-Dec-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.16 | 3 | Wall Finishes | Activity | Architectural |  | 13 | 18-Dec-2026 | 30-Dec-2026 | 01.02.03 | Architect, Draftsman | D-1200
01.02.17 | 3 | Waterproofing Details | Activity | Architectural |  | 11 | 24-Dec-2026 | 03-Jan-2027 | 01.02.03 | Architect, Draftsman | D-1200
01.02.18 | 3 | Detailed Architectural Drawings | Activity | Architectural |  | 16 | 29-Dec-2026 | 13-Jan-2027 | 01.02.13,01.02.14,01.02.15 | Architect, Draftsman | D-1200
01.02.19 | 3 | Architectural Specifications | Activity | Architectural |  | 21 | 03-Jan-2027 | 23-Jan-2027 | 01.02.18 | Architect, Draftsman | D-1200
01.02.20 | 3 | IFC Architectural Drawings | Activity | Architectural |  | 11 | 08-Jan-2027 | 18-Jan-2027 | 01.02.18,01.02.19 | Architect, Draftsman | D-1200
01.03 | 2 | 01.03 STRUCTURAL DESIGN | Work Package | Structural |  | 138 | 01-Oct-2026 | 15-Feb-2027 | 01.02 | Design Manager, Consultants | D-1300
01.03.01 | 3 | Structural Design Criteria | Activity | Structural |  | 11 | 01-Oct-2026 | 11-Oct-2026 | 01.01.02 | Structural Engineer, Draftsman | D-1300
01.03.02 | 3 | Geotechnical Data Review | Activity | Structural |  | 11 | 05-Oct-2026 | 15-Oct-2026 | 01.03.01 | Structural Engineer, Draftsman | D-1300
01.03.03 | 3 | Foundation Design | Activity | Structural |  | 16 | 09-Oct-2026 | 24-Oct-2026 | 01.03.02 | Structural Engineer, Draftsman | D-1300
01.03.04 | 3 | Pile Design | Activity | Structural |  | 16 | 13-Oct-2026 | 28-Oct-2026 | 01.03.03 | Structural Engineer, Draftsman | D-1300
01.03.05 | 3 | Pile Cap Design | Activity | Structural |  | 16 | 17-Oct-2026 | 01-Nov-2026 | 01.03.04 | Structural Engineer, Draftsman | D-1300
01.03.06 | 3 | Ground Beam Design | Activity | Structural |  | 16 | 21-Oct-2026 | 05-Nov-2026 | 01.03.05 | Structural Engineer, Draftsman | D-1300
01.03.07 | 3 | Basement Structure Design | Activity | Structural |  | 16 | 26-Oct-2026 | 10-Nov-2026 | 01.03.06 | Structural Engineer, Draftsman | D-1300
01.03.08 | 3 | Retaining Wall Design | Activity | Structural |  | 16 | 30-Oct-2026 | 14-Nov-2026 | 01.03.07 | Structural Engineer, Draftsman | D-1300
01.03.09 | 3 | Column Design | Activity | Structural |  | 13 | 03-Nov-2026 | 15-Nov-2026 | 01.03.07 | Structural Engineer, Draftsman | D-1300
01.03.10 | 3 | Shear Wall Design | Activity | Structural |  | 13 | 07-Nov-2026 | 19-Nov-2026 | 01.03.09 | Structural Engineer, Draftsman | D-1300
01.03.11 | 3 | Beam Design | Activity | Structural |  | 13 | 11-Nov-2026 | 23-Nov-2026 | 01.03.09 | Structural Engineer, Draftsman | D-1300
01.03.12 | 3 | Slab Design | Activity | Structural |  | 13 | 15-Nov-2026 | 27-Nov-2026 | 01.03.11 | Structural Engineer, Draftsman | D-1300
01.03.13 | 3 | Stair Design | Activity | Structural |  | 11 | 20-Nov-2026 | 30-Nov-2026 | 01.03.11 | Structural Engineer, Draftsman | D-1300
01.03.14 | 3 | Roof Structure Design | Activity | Structural |  | 11 | 24-Nov-2026 | 04-Dec-2026 | 01.03.12 | Structural Engineer, Draftsman | D-1300
01.03.15 | 3 | Structural Analysis | Activity | Structural |  | 16 | 28-Nov-2026 | 13-Dec-2026 | 01.03.12,01.03.13 | Structural Engineer, Draftsman | D-1300
01.03.16 | 3 | Seismic Analysis | Activity | Structural |  | 16 | 02-Dec-2026 | 17-Dec-2026 | 01.03.15 | Structural Engineer, Draftsman | D-1300
01.03.17 | 3 | Wind Analysis | Activity | Structural |  | 16 | 06-Dec-2026 | 21-Dec-2026 | 01.03.15 | Structural Engineer, Draftsman | D-1300
01.03.18 | 3 | Foundation Calculations | Activity | Structural |  | 16 | 10-Dec-2026 | 25-Dec-2026 | 01.03.03,01.03.15 | Structural Engineer, Draftsman | D-1300
01.03.19 | 3 | Superstructure Calculations | Activity | Structural |  | 13 | 15-Dec-2026 | 27-Dec-2026 | 01.03.15 | Structural Engineer, Draftsman | D-1300
01.03.20 | 3 | Structural Drawings | Activity | Structural |  | 21 | 19-Dec-2026 | 08-Jan-2027 | 01.03.18,01.03.19 | Structural Engineer, Draftsman | D-1300
01.03.21 | 3 | Reinforcement Drawings | Activity | Structural |  | 21 | 23-Dec-2026 | 12-Jan-2027 | 01.03.20 | Structural Engineer, Draftsman | D-1300
01.03.22 | 3 | Rebar Detailing | Activity | Structural |  | 21 | 27-Dec-2026 | 16-Jan-2027 | 01.03.21 | Structural Engineer, Draftsman | D-1300
01.03.23 | 3 | IFC Structural Drawings | Activity | Structural |  | 21 | 31-Dec-2026 | 20-Jan-2027 | 01.03.20,01.03.22 | Structural Engineer, Draftsman | D-1300
01.04 | 2 | 01.04 MEP DESIGN | Work Package | MEP |  | 152 | 15-Oct-2026 | 15-Mar-2027 | 01.03 | Design Manager, Consultants | D-1400
01.04.01 | 3 | 01.04.01 ELECTRICAL | Work Package | Electrical |  | 71 | 15-Oct-2026 | 24-Dec-2026 | 01.02.03,01.03.12 | Electrical Engineer | D-1410
01.04.01.01 | 4 | Load Calculation | Activity | Electrical |  | 7 | 25-Oct-2026 | 01-Nov-2026 | 01.04.01 | Electrical Engineer | D-1100
01.04.01.02 | 4 | Single Line Diagram | Activity | Electrical |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.01.01 | Electrical Engineer | D-1200
01.04.01.03 | 4 | Power Layout | Activity | Electrical |  | 12 | 25-Oct-2026 | 06-Nov-2026 | 01.04.01.02 | Electrical Engineer | D-1300
01.04.01.04 | 4 | Lighting Layout | Activity | Electrical |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.01.03 | Electrical Engineer | D-1410
01.04.01.05 | 4 | DB Schedule | Activity | Electrical |  | 8 | 25-Oct-2026 | 02-Nov-2026 | 01.04.01.04 | Electrical Engineer | D-1410
01.04.01.06 | 4 | Cable Schedule | Activity | Electrical |  | 8 | 25-Oct-2026 | 02-Nov-2026 | 01.04.01.05 | Electrical Engineer | D-1410
01.04.01.07 | 4 | Earthing System | Activity | Electrical |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.01.06 | Electrical Engineer | D-1410
01.04.01.08 | 4 | Lightning Protection | Activity | Electrical |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.01.07 | Electrical Engineer | D-1410
01.04.01.09 | 4 | IFC Electrical Drawings | Activity | Electrical |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.01.08 | Electrical Engineer | D-1410
01.04.02 | 3 | 01.04.02 ELV | Work Package | ELV |  | 61 | 25-Oct-2026 | 24-Dec-2026 | 01.02.03,01.03.12 | ELV Engineer | D-1420
01.04.02.01 | 4 | Data | Activity | ELV |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.02 | ELV Engineer | D-1420
01.04.02.02 | 4 | Telephone | Activity | ELV |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.02.01 | ELV Engineer | D-1420
01.04.02.03 | 4 | CCTV | Activity | ELV |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.02.02 | ELV Engineer | D-1420
01.04.02.04 | 4 | Access Control | Activity | ELV |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.02.03 | ELV Engineer | D-1420
01.04.02.05 | 4 | Public Address | Activity | ELV |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.02.04 | ELV Engineer | D-1420
01.04.02.06 | 4 | IFC ELV Drawings | Activity | ELV |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.02.05 | ELV Engineer | D-1420
01.04.03 | 3 | 01.04.03 FIRE ALARM | Work Package | Fire Alarm |  | 61 | 25-Oct-2026 | 24-Dec-2026 | 01.02.03,01.03.12 | Fire Alarm Engineer | D-1430
01.04.03.01 | 4 | Fire Alarm Layout | Activity | Fire Alarm |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.03 | Fire Alarm Engineer | D-1430
01.04.03.02 | 4 | Detection System | Activity | Fire Alarm |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.03.01 | Fire Alarm Engineer | D-1430
01.04.03.03 | 4 | Alarm System | Activity | Fire Alarm |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.03.02 | Fire Alarm Engineer | D-1430
01.04.03.04 | 4 | IFC Fire Alarm Drawings | Activity | Fire Alarm |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.03.03 | Fire Alarm Engineer | D-1430
01.04.04 | 3 | 01.04.04 HVAC | Work Package | HVAC |  | 71 | 20-Oct-2026 | 29-Dec-2026 | 01.02.03,01.03.12 | HVAC Engineer | D-1440
01.04.04.01 | 4 | Cooling Load Calculation | Activity | HVAC |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.04 | HVAC Engineer | D-1440
01.04.04.02 | 4 | Equipment Selection | Activity | HVAC |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.04.01 | HVAC Engineer | D-1440
01.04.04.03 | 4 | HVAC Layout | Activity | HVAC |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.04.02 | HVAC Engineer | D-1440
01.04.04.04 | 4 | Duct Layout | Activity | HVAC |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.04.03 | HVAC Engineer | D-1440
01.04.04.05 | 4 | Pipe Layout | Activity | HVAC |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.04.04 | HVAC Engineer | D-1440
01.04.04.06 | 4 | IFC HVAC Drawings | Activity | HVAC |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.04.05 | HVAC Engineer | D-1440
01.04.05 | 3 | 01.04.05 PLUMBING | Work Package | Plumbing |  | 71 | 20-Oct-2026 | 29-Dec-2026 | 01.02.03,01.03.12 | Plumbing Engineer | D-1450
01.04.05.01 | 4 | Water Demand Calculation | Activity | Plumbing |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.05 | Plumbing Engineer | D-1450
01.04.05.02 | 4 | Water Supply Layout | Activity | Plumbing |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.05.01 | Plumbing Engineer | D-1450
01.04.05.03 | 4 | Sanitary Layout | Activity | Plumbing |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.05.02 | Plumbing Engineer | D-1450
01.04.05.04 | 4 | Drainage Layout | Activity | Plumbing |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.05.03 | Plumbing Engineer | D-1450
01.04.05.05 | 4 | IFC Plumbing Drawings | Activity | Plumbing |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.05.04 | Plumbing Engineer | D-1450
01.04.06 | 3 | 01.04.06 FIRE FIGHTING | Work Package | Fire Fighting |  | 66 | 25-Oct-2026 | 29-Dec-2026 | 01.02.03,01.03.12 | Fire Fighting Engineer | D-1460
01.04.06.01 | 4 | Hydraulic Calculation | Activity | Fire Fighting |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.06 | Fire Fighting Engineer | D-1460
01.04.06.02 | 4 | Fire Fighting Layout | Activity | Fire Fighting |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.06.01 | Fire Fighting Engineer | D-1460
01.04.06.03 | 4 | Sprinkler Layout | Activity | Fire Fighting |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.06.02 | Fire Fighting Engineer | D-1460
01.04.06.04 | 4 | Fire Hydrant Layout | Activity | Fire Fighting |  | 15 | 25-Oct-2026 | 09-Nov-2026 | 01.04.06.03 | Fire Fighting Engineer | D-1460
01.04.06.05 | 4 | IFC Fire Fighting Drawings | Activity | Fire Fighting |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.06.04 | Fire Fighting Engineer | D-1460
01.04.07 | 3 | 01.04.07 MEP COORDINATION | Work Package | MEP |  | 51 | 24-Nov-2026 | 13-Jan-2027 | 01.02.03,01.03.12 | MEP Coordinator, All MEP Engineers | D-1470
01.04.07.01 | 4 | MEP Coordination | Activity | MEP |  | 20 | 25-Oct-2026 | 14-Nov-2026 | 01.04.07 | MEP Coordinator, All MEP Engineers | D-1470
01.04.07.02 | 4 | Builder Work Drawings | Activity | MEP |  | 20 | 25-Oct-2026 | 14-Nov-2026 | 01.04.07.01 | MEP Coordinator, All MEP Engineers | D-1470
01.04.07.03 | 4 | Sleeve Coordination | Activity | MEP |  | 20 | 25-Oct-2026 | 14-Nov-2026 | 01.04.07.02 | MEP Coordinator, All MEP Engineers | D-1470
01.04.07.04 | 4 | Opening Coordination | Activity | MEP |  | 20 | 25-Oct-2026 | 14-Nov-2026 | 01.04.07.03 | MEP Coordinator, All MEP Engineers | D-1470
01.04.07.05 | 4 | MEP IFC Package | Activity | MEP |  | 10 | 25-Oct-2026 | 04-Nov-2026 | 01.04.07.04 | MEP Coordinator, All MEP Engineers | D-1470
01.05 | 2 | 01.05 BIM COORDINATION | Work Package | BIM |  | 140 | 01-Nov-2026 | 20-Mar-2027 | 01.04 | Project Team | D-1500
01.05.01 | 3 | Architectural Model | Activity | BIM |  | 31 | 01-Nov-2026 | 01-Dec-2026 | 01.02.20 | BIM Coordinator, Modellers | D-1500
01.05.02 | 3 | Structural Model | Activity | BIM |  | 31 | 09-Nov-2026 | 09-Dec-2026 | 01.03.23 | BIM Coordinator, Modellers | D-1500
01.05.03 | 3 | MEP Model | Activity | BIM |  | 31 | 17-Nov-2026 | 17-Dec-2026 | 01.04.07 | BIM Coordinator, Modellers | D-1500
01.05.04 | 3 | Model Federation | Activity | BIM |  | 31 | 25-Nov-2026 | 25-Dec-2026 | 01.05.01,01.05.02,01.05.03 | BIM Coordinator, Modellers | D-1500
01.05.05 | 3 | Clash Detection | Activity | BIM |  | 16 | 03-Dec-2026 | 18-Dec-2026 | 01.05.04 | BIM Coordinator, Modellers | D-1500
01.05.06 | 3 | Clash Analysis | Activity | BIM |  | 16 | 11-Dec-2026 | 26-Dec-2026 | 01.05.05 | BIM Coordinator, Modellers | D-1500
01.05.07 | 3 | Clash Resolution | Activity | BIM |  | 16 | 19-Dec-2026 | 03-Jan-2027 | 01.05.06 | BIM Coordinator, Modellers | D-1500
01.05.08 | 3 | Design Coordination | Activity | BIM |  | 21 | 27-Dec-2026 | 16-Jan-2027 | 01.05.07 | BIM Coordinator, Modellers | D-1500
01.05.09 | 3 | Constructability Review | Activity | BIM |  | 11 | 04-Jan-2027 | 14-Jan-2027 | 01.05.07 | BIM Coordinator, Modellers | D-1500
01.05.10 | 3 | BIM Coordination Meeting | Activity | BIM |  | 21 | 12-Jan-2027 | 01-Feb-2027 | 01.05.08 | BIM Coordinator, Modellers | D-1500
01.05.11 | 3 | Coordinated Model | Activity | BIM |  | 31 | 20-Jan-2027 | 19-Feb-2027 | 01.05.07,01.05.09 | BIM Coordinator, Modellers | D-1500
01.05.12 | 3 | Model Approval | Activity | BIM |  | 31 | 28-Jan-2027 | 27-Feb-2027 | 01.05.11 | BIM Coordinator, Modellers | D-1500
01.06 | 2 | 01.06 SHOP DRAWINGS | Work Package | Shop Drawings |  | 167 | 15-Jan-2027 | 30-Jun-2027 | 01.05 | Project Team | D-1600
01.06.01 | 3 | Structural Shop Drawings | Activity | Shop Drawings |  | 21 | 15-Jan-2027 | 04-Feb-2027 | 01.03.23 | Structural Detailer, Formwork Engineer | D-1600
01.06.02 | 3 | Rebar Shop Drawings | Activity | Shop Drawings |  | 21 | 22-Jan-2027 | 11-Feb-2027 | 01.03.23 | Structural Detailer, Formwork Engineer | D-1600
01.06.03 | 3 | Formwork Drawings | Activity | Shop Drawings |  | 21 | 29-Jan-2027 | 18-Feb-2027 | 01.03.23 | Structural Detailer, Formwork Engineer | D-1600
01.06.04 | 3 | Architectural Shop Drawings | Activity | Shop Drawings |  | 21 | 05-Feb-2027 | 25-Feb-2027 | 01.02.20 | Architectural Detailer | D-1600
01.06.05 | 3 | Façade Shop Drawings | Activity | Shop Drawings |  | 21 | 12-Feb-2027 | 04-Mar-2027 | 01.02.20 | Architectural Detailer | D-1600
01.06.06 | 3 | Ceiling Shop Drawings | Activity | Shop Drawings |  | 21 | 19-Feb-2027 | 11-Mar-2027 | 01.02.20 | Architectural Detailer | D-1600
01.06.07 | 3 | Flooring Shop Drawings | Activity | Shop Drawings |  | 21 | 26-Feb-2027 | 18-Mar-2027 | 01.02.20 | Shop Drawing Team, Consultants | D-1600
01.06.08 | 3 | Door & Window Shop Drawings | Activity | Shop Drawings |  | 21 | 05-Mar-2027 | 25-Mar-2027 | 01.02.20 | Architectural Detailer | D-1600
01.06.09 | 3 | MEP Shop Drawings | Activity | Shop Drawings |  | 21 | 12-Mar-2027 | 01-Apr-2027 | 01.04.07 | MEP Detailer | D-1600
01.06.10 | 3 | Builder Work Drawings | Activity | Shop Drawings |  | 16 | 19-Mar-2027 | 03-Apr-2027 | 01.04.07 | Shop Drawing Team, Consultants | D-1600
01.06.11 | 3 | Coordination Drawings | Activity | Shop Drawings |  | 16 | 26-Mar-2027 | 10-Apr-2027 | 01.06.10 | Shop Drawing Team, Consultants | D-1600
01.06.12 | 3 | Shop Drawing Submission | Activity | Shop Drawings |  | 21 | 02-Apr-2027 | 22-Apr-2027 | 01.06.01,01.06.04,01.06.09 | Shop Drawing Team, Consultants | D-1600
01.06.13 | 3 | Consultant Review | Activity | Shop Drawings |  | 11 | 09-Apr-2027 | 19-Apr-2027 | 01.06.12 | Shop Drawing Team, Consultants | D-1600
01.06.14 | 3 | Client Review | Activity | Shop Drawings |  | 11 | 16-Apr-2027 | 26-Apr-2027 | 01.06.12 | Shop Drawing Team, Consultants | D-1600
01.06.15 | 3 | Shop Drawing Revision | Activity | Shop Drawings |  | 21 | 23-Apr-2027 | 13-May-2027 | 01.06.13,01.06.14 | Shop Drawing Team, Consultants | D-1600
01.06.16 | 3 | Shop Drawing Approval | Activity | Shop Drawings |  | 21 | 30-Apr-2027 | 20-May-2027 | 01.06.15 | Shop Drawing Team, Consultants | D-1600
02 | 1 | 02 PROCUREMENT | Phase | Procurement |  | 608 | 01-Nov-2026 | 30-Jun-2028 | 01.01.14 | PM Team | P-2000 | Obtain approved materials, equipment and subcontracted packages
02.01 | 2 | 02.01 PROCUREMENT MANAGEMENT | Work Package | Procurement |  | 608 | 01-Nov-2026 | 30-Jun-2028 | 02 | Procurement Manager | P-2100
02.01.01 | 3 | Procurement Strategy | Activity | Procurement |  | 8 | 01-Nov-2026 | 08-Nov-2026 | 02.01 | Procurement Manager, Buyers | P-2100
02.01.02 | 3 | Procurement Schedule | Activity | Procurement |  | 13 | 11-Nov-2026 | 23-Nov-2026 | 02.01.01 | Procurement Manager, Buyers | P-2100
02.01.03 | 3 | Procurement Responsibility Matrix | Activity | Procurement |  | 13 | 21-Nov-2026 | 03-Dec-2026 | 02.01.02 | Procurement Manager, Buyers | P-2100
02.01.04 | 3 | Material Requirement Plan | Activity | Procurement |  | 11 | 01-Dec-2026 | 11-Dec-2026 | 02.01.03 | Procurement Manager, Buyers | P-2100
02.01.05 | 3 | Long Lead Item Register | Activity | Procurement |  | 11 | 11-Dec-2026 | 21-Dec-2026 | 02.01.04 | Procurement Manager, Buyers | P-2100
02.01.06 | 3 | Procurement Tracking | Activity | Procurement |  | 16 | 21-Dec-2026 | 05-Jan-2027 | 02.01.05 | Procurement Manager, Buyers | P-2100
02.01.07 | 3 | Procurement Expediting | Activity | Procurement |  | 401 | 31-Dec-2026 | 04-Feb-2028 | 02.01.06 | Procurement Manager, Buyers | P-2100
02.02 | 2 | 02.02 STRUCTURAL MATERIALS | Work Package | Structural |  | 228 | 15-Nov-2026 | 30-Jun-2027 | 02.01 | Project Team | P-2200
02.02.01 | 3 | Reinforcement Steel | Material Package | Structural |  | 11 | 15-Nov-2026 | 25-Nov-2026 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2100
02.02.02 | 3 | Ready Mix Concrete | Material Package | Structural |  | 61 | 25-Nov-2026 | 24-Jan-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.02.03 | 3 | Cement | Material Package | Structural |  | 61 | 05-Dec-2026 | 03-Feb-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.02.04 | 3 | Formwork Materials | Material Package | Structural |  | 61 | 15-Dec-2026 | 13-Feb-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.02.05 | 3 | Waterproofing Materials | Material Package | Structural |  | 61 | 25-Dec-2026 | 23-Feb-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.02.06 | 3 | Embedded Items | Material Package | Structural |  | 61 | 04-Jan-2027 | 05-Mar-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.02.07 | 3 | Structural Steel | Material Package | Structural |  | 61 | 14-Jan-2027 | 15-Mar-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.02.08 | 3 | Expansion / Movement Joint Materials | Material Package | Structural |  | 61 | 24-Jan-2027 | 25-Mar-2027 | 01.03.23,02.05.12 | Procurement, Structural Supplier | P-2200
02.03 | 2 | 02.03 ARCHITECTURAL MATERIALS | Work Package | Architectural |  | 425 | 01-Feb-2027 | 31-Mar-2028 | 02.02 | Project Team | P-2300
02.03.01 | 3 | Block / Brick | Material Package | Architectural |  | 61 | 01-Feb-2027 | 02-Apr-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.02 | 3 | Plaster Materials | Material Package | Architectural |  | 61 | 11-Feb-2027 | 12-Apr-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.03 | 3 | Screed | Material Package | Architectural |  | 61 | 21-Feb-2027 | 22-Apr-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.04 | 3 | Tiles | Material Package | Architectural |  | 61 | 03-Mar-2027 | 02-May-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.05 | 3 | Marble / Stone | Material Package | Architectural |  | 61 | 13-Mar-2027 | 12-May-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.06 | 3 | Paint | Material Package | Architectural |  | 61 | 23-Mar-2027 | 22-May-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.07 | 3 | Ceiling | Material Package | Architectural |  | 61 | 02-Apr-2027 | 01-Jun-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.08 | 3 | Doors | Material Package | Architectural |  | 61 | 12-Apr-2027 | 11-Jun-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.09 | 3 | Windows | Material Package | Architectural |  | 61 | 22-Apr-2027 | 21-Jun-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.10 | 3 | Glass | Material Package | Architectural |  | 61 | 02-May-2027 | 01-Jul-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.11 | 3 | Curtain Wall / Façade | Material Package | Architectural |  | 61 | 12-May-2027 | 11-Jul-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.12 | 3 | Waterproofing | Material Package | Architectural |  | 61 | 22-May-2027 | 21-Jul-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.13 | 3 | Sanitary Fixtures | Material Package | Architectural |  | 61 | 01-Jun-2027 | 31-Jul-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.03.14 | 3 | Hardware | Material Package | Architectural |  | 61 | 11-Jun-2027 | 10-Aug-2027 | 01.02.20,02.05.12 | Procurement, Architectural Supplier | P-2300
02.04 | 2 | 02.04 MEP MATERIALS | Work Package | MEP |  | 472 | 15-Jan-2027 | 30-Apr-2028 | 02.03 | Project Team | P-2400
02.04.01 | 3 | Cables | Material Package | MEP |  | 61 | 15-Jan-2027 | 16-Mar-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.02 | 3 | Conduits | Material Package | MEP |  | 61 | 25-Jan-2027 | 26-Mar-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.03 | 3 | Cable Trays | Material Package | MEP |  | 61 | 04-Feb-2027 | 05-Apr-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.04 | 3 | Distribution Boards | Material Package | MEP |  | 61 | 14-Feb-2027 | 15-Apr-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.05 | 3 | Lighting Fixtures | Material Package | MEP |  | 61 | 24-Feb-2027 | 25-Apr-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.06 | 3 | ELV Equipment | Material Package | MEP |  | 61 | 06-Mar-2027 | 05-May-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.07 | 3 | Fire Alarm Equipment | Material Package | MEP |  | 61 | 16-Mar-2027 | 15-May-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.08 | 3 | HVAC Equipment | Material Package | MEP |  | 61 | 26-Mar-2027 | 25-May-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.09 | 3 | Ductwork | Material Package | MEP |  | 61 | 05-Apr-2027 | 04-Jun-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.10 | 3 | HVAC Pipes | Material Package | MEP |  | 61 | 15-Apr-2027 | 14-Jun-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.11 | 3 | Water Pipes | Material Package | MEP |  | 61 | 25-Apr-2027 | 24-Jun-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.12 | 3 | Drainage Pipes | Material Package | MEP |  | 61 | 05-May-2027 | 04-Jul-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.13 | 3 | Pumps | Material Package | MEP |  | 61 | 15-May-2027 | 14-Jul-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.14 | 3 | Fire Fighting Pipes | Material Package | MEP |  | 61 | 25-May-2027 | 24-Jul-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.15 | 3 | Sprinklers | Material Package | MEP |  | 61 | 04-Jun-2027 | 03-Aug-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.04.16 | 3 | Fire Fighting Equipment | Material Package | MEP |  | 61 | 14-Jun-2027 | 13-Aug-2027 | 01.04.07,02.05.12 | Procurement, MEP Supplier | P-2400
02.05 | 2 | 02.05 PROCUREMENT PROCESS | Work Package | Procurement |  | 578 | 01-Nov-2026 | 31-May-2028 | 02.04 | Procurement Manager | P-2500
02.05.01 | 3 | Material Requisition | Activity | Procurement |  | 6 | 01-Nov-2026 | 06-Nov-2026 | 02.01.04 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.02 | 3 | RFQ Preparation | Activity | Procurement |  | 6 | 11-Nov-2026 | 16-Nov-2026 | 02.05.01 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.03 | 3 | RFQ Issued | Activity | Procurement |  | 6 | 21-Nov-2026 | 26-Nov-2026 | 02.05.02 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.04 | 3 | Supplier Quotation | Activity | Procurement |  | 15 | 01-Dec-2026 | 15-Dec-2026 | 02.05.03 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.05 | 3 | Technical Evaluation | Activity | Procurement |  | 8 | 11-Dec-2026 | 18-Dec-2026 | 02.05.04 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.06 | 3 | Commercial Evaluation | Activity | Procurement |  | 8 | 21-Dec-2026 | 28-Dec-2026 | 02.05.04 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.07 | 3 | Supplier Recommendation | Activity | Procurement |  | 6 | 31-Dec-2026 | 05-Jan-2027 | 02.05.05,02.05.06 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.08 | 3 | Supplier Approval | Activity | Procurement |  | 6 | 10-Jan-2027 | 15-Jan-2027 | 02.05.07 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.09 | 3 | Purchase Order | Activity | Procurement |  | 4 | 20-Jan-2027 | 23-Jan-2027 | 02.05.08 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.10 | 3 | Material Submittal | Activity | Procurement |  | 11 | 30-Jan-2027 | 09-Feb-2027 | 02.05.09 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.11 | 3 | Consultant Approval | Activity | Procurement |  | 6 | 09-Feb-2027 | 14-Feb-2027 | 02.05.10 | Buyer, Technical Evaluator, Commercial | P-2500
02.05.12 | 3 | Material Approval | Activity | Procurement |  | 6 | 19-Feb-2027 | 24-Feb-2027 | 02.05.11 | Buyer, Technical Evaluator, Commercial | P-2500
02.06 | 2 | 02.06 MANUFACTURING & EXPEDITING | Work Package | Procurement |  | 486 | 01-Jan-2027 | 30-Apr-2028 | 02.05 | Project Team | P-2600
02.06.01 | 3 | Production | Activity | Procurement |  | 61 | 01-Jan-2027 | 02-Mar-2027 | 02.05.09 | Expeditor, QA Inspector, Supplier | P-2600
02.06.02 | 3 | Factory Inspection | Activity | Procurement |  | 6 | 11-Jan-2027 | 16-Jan-2027 | 02.05.09 | Expeditor, QA Inspector, Supplier | P-2600
02.06.03 | 3 | Factory Acceptance Test | Activity | Procurement |  | 6 | 21-Jan-2027 | 26-Jan-2027 | 02.05.09 | Expeditor, QA Inspector, Supplier | P-2600
02.06.04 | 3 | Manufacturing Progress | Activity | Procurement |  | 46 | 31-Jan-2027 | 17-Mar-2027 | 02.05.09 | Expeditor, QA Inspector, Supplier | P-2600
02.06.05 | 3 | Quality Inspection | Activity | Procurement |  | 6 | 10-Feb-2027 | 15-Feb-2027 | 02.05.09 | Expeditor, QA Inspector, Supplier | P-2600
02.06.06 | 3 | Expediting | Activity | Procurement |  | 46 | 20-Feb-2027 | 06-Apr-2027 | 02.05.09 | Expeditor, QA Inspector, Supplier | P-2600
02.07 | 2 | 02.07 DELIVERY & RECEIVING | Work Package | Procurement |  | 516 | 01-Feb-2027 | 30-Jun-2028 | 02.06 | Project Team | P-2700
02.07.01 | 3 | Transportation | Activity | Procurement |  | 8 | 01-Feb-2027 | 08-Feb-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.02 | 3 | Site Delivery | Activity | Procurement |  | 8 | 11-Feb-2027 | 18-Feb-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.03 | 3 | Delivery Inspection | Activity | Procurement |  | 8 | 21-Feb-2027 | 28-Feb-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.04 | 3 | Material Inspection Request | Activity | Procurement |  | 4 | 03-Mar-2027 | 06-Mar-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.05 | 3 | Material Testing | Activity | Procurement |  | 4 | 13-Mar-2027 | 16-Mar-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.06 | 3 | Material Acceptance | Activity | Procurement |  | 3 | 23-Mar-2027 | 25-Mar-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.07 | 3 | Storage | Activity | Procurement |  | 3 | 02-Apr-2027 | 04-Apr-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
02.07.08 | 3 | Inventory Registration | Activity | Procurement |  | 3 | 12-Apr-2027 | 14-Apr-2027 | 02.06.01 | Storekeeper, QA/QC, Logistics | P-2700
03 | 1 | 03 CONSTRUCTION | Phase | Construction |  | 578 | 01-Jan-2027 | 31-Jul-2028 | 01.03.23,01.06.16 | PM Team | C-3000 | Physically execute the works
03.01 | 2 | 03.01 BA – MAIN BUILDING | Work Package | Construction | Main Building | 547 | 01-Jan-2027 | 30-Jun-2028 | 03 | Construction Manager, Site Team | C-3000
03.01.01 | 3 | 03.01.01 B1 – BASEMENT / UNDERGROUND | Work Package | Construction | B1 | 135 | 01-Jan-2027 | 15-May-2027 | 01.03.23,02.02.01 | Site Team | C-3100
03.01.01.01 | 4 | 01 EARTHWORK | Work Package | Civil | B1 | 7 | 01-Jan-2027 | 15-Feb-2027 | 03.01.01 | Civil Crew, Surveyor | C-3110
03.01.01.01.01 | 5 | Site Preparation | Activity | Civil | B1 | 7 | 01-Jan-2027 | 08-Jan-2027 | 03.01.01.01 | Civil Crew, Surveyor | C-3110
03.01.01.01.02 | 5 | Excavation | Activity | Civil | B1 | 7 | 04-Jan-2027 | 11-Jan-2027 | 03.01.01.01.01 | Excavator Crew, Operator | C-3110
03.01.01.01.03 | 5 | Earth Disposal | Activity | Civil | B1 | 7 | 07-Jan-2027 | 14-Jan-2027 | 03.01.01.01.02 | Civil Crew, Surveyor | C-3110
03.01.01.01.04 | 5 | Dewatering | Activity | Civil | B1 | 7 | 10-Jan-2027 | 17-Jan-2027 | 03.01.01.01.03 | Dewatering Crew | C-3110
03.01.01.01.05 | 5 | Excavation Support | Activity | Civil | B1 | 7 | 13-Jan-2027 | 20-Jan-2027 | 03.01.01.01.04 | Excavator Crew, Operator | C-3110
03.01.01.01.06 | 5 | Formation Level | Activity | Civil | B1 | 7 | 16-Jan-2027 | 23-Jan-2027 | 03.01.01.01.05 | Civil Crew, Surveyor | C-3110
03.01.01.01.07 | 5 | Soil Compaction | Activity | Civil | B1 | 7 | 19-Jan-2027 | 26-Jan-2027 | 03.01.01.01.06 | Civil Crew, Surveyor | C-3110
03.01.01.02 | 4 | 02 FOUNDATION | Work Package | Structural | B1 | 7 | 01-Feb-2027 | 31-Mar-2027 | 03.01.01.01 | Foundation Crew, Surveyor | C-3120
03.01.01.02.01 | 5 | Pile Setting Out | Activity | Structural | B1 | 7 | 01-Feb-2027 | 08-Feb-2027 | 03.01.01.02 | Surveyor, Piling Crew | C-3120
03.01.01.02.02 | 5 | Pile Installation | Activity | Structural | B1 | 7 | 04-Feb-2027 | 11-Feb-2027 | 03.01.01.02.01 | Piling Rig, Piling Crew | C-3120
03.01.01.02.03 | 5 | Pile Testing | Activity | Structural | B1 | 7 | 07-Feb-2027 | 14-Feb-2027 | 03.01.01.02.02 | Piling Crew, Testing Engineer | C-3120
03.01.01.02.04 | 5 | Pile Head Breaking | Activity | Structural | B1 | 7 | 10-Feb-2027 | 17-Feb-2027 | 03.01.01.02.03 | Foundation Crew, Surveyor | C-3120
03.01.01.02.05 | 5 | Pile Cap Excavation | Activity | Structural | B1 | 7 | 13-Feb-2027 | 20-Feb-2027 | 03.01.01.02.04 | Foundation Crew, Surveyor | C-3120
03.01.01.02.06 | 5 | Pile Cap Reinforcement | Activity | Structural | B1 | 7 | 16-Feb-2027 | 23-Feb-2027 | 03.01.01.02.05 | Rebar Crew (8 men) | C-3120
03.01.01.02.07 | 5 | Pile Cap Formwork | Activity | Structural | B1 | 7 | 19-Feb-2027 | 26-Feb-2027 | 03.01.01.02.06 | Formwork Crew (6 men) | C-3120
03.01.01.02.08 | 5 | Pile Cap Concrete | Activity | Structural | B1 | 7 | 22-Feb-2027 | 01-Mar-2027 | 03.01.01.02.07 | Concrete Crew, Pump | C-3120
03.01.01.02.09 | 5 | Ground Beam Reinforcement | Activity | Structural | B1 | 7 | 25-Feb-2027 | 04-Mar-2027 | 03.01.01.02.08 | Rebar Crew (8 men) | C-3120
03.01.01.02.10 | 5 | Ground Beam Formwork | Activity | Structural | B1 | 7 | 28-Feb-2027 | 07-Mar-2027 | 03.01.01.02.09 | Formwork Crew (6 men) | C-3120
03.01.01.02.11 | 5 | Ground Beam Concrete | Activity | Structural | B1 | 7 | 03-Mar-2027 | 10-Mar-2027 | 03.01.01.02.10 | Concrete Crew, Pump | C-3120
03.01.01.03 | 4 | 03 STRUCTURAL | Work Package | Structural | B1 | 7 | 15-Mar-2027 | 30-Apr-2027 | 03.01.01.02 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.03.01 | 5 | B1 Columns | Activity | Structural | B1 | 7 | 15-Mar-2027 | 22-Mar-2027 | 03.01.01.03 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.03.02 | 5 | B1 Shear Walls | Activity | Structural | B1 | 7 | 18-Mar-2027 | 25-Mar-2027 | 03.01.01.03.01 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.03.03 | 5 | B1 Retaining Walls | Activity | Structural | B1 | 7 | 21-Mar-2027 | 28-Mar-2027 | 03.01.01.03.02 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.03.04 | 5 | B1 Beams | Activity | Structural | B1 | 7 | 24-Mar-2027 | 31-Mar-2027 | 03.01.01.03.03 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.03.05 | 5 | B1 Slab | Activity | Structural | B1 | 7 | 27-Mar-2027 | 03-Apr-2027 | 03.01.01.03.04 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.03.06 | 5 | B1 Staircase | Activity | Structural | B1 | 7 | 30-Mar-2027 | 06-Apr-2027 | 03.01.01.03.05 | Rebar Crew, Formwork Crew, Concrete Crew | C-3130
03.01.01.04 | 4 | 04 WATERPROOFING | Work Package | Architectural | B1 | 7 | 20-Mar-2027 | 20-Apr-2027 | 03.01.01.02,03.01.01.03 | Waterproofing Crew | C-3140
03.01.01.04.01 | 5 | Foundation Waterproofing | Activity | Architectural | B1 | 7 | 20-Mar-2027 | 27-Mar-2027 | 03.01.01.04 | Electrical Engineer | C-3140
03.01.01.04.02 | 5 | Retaining Wall Waterproofing | Activity | Architectural | B1 | 7 | 23-Mar-2027 | 30-Mar-2027 | 03.01.01.04.01 | ELV Engineer | C-3140
03.01.01.04.03 | 5 | Slab Waterproofing | Activity | Architectural | B1 | 7 | 26-Mar-2027 | 02-Apr-2027 | 03.01.01.04.02 | Fire Alarm Engineer | C-3140
03.01.01.04.04 | 5 | Waterproofing Protection | Activity | Architectural | B1 | 7 | 29-Mar-2027 | 05-Apr-2027 | 03.01.01.04.03 | HVAC Engineer | C-3140
03.01.01.05 | 4 | 05 ARCHITECTURAL | Work Package | Architectural | B1 | 7 | 01-Apr-2027 | 15-May-2027 | 03.01.01.03,03.01.01.04 | Architectural Finishes Crew | C-3150
03.01.01.05.01 | 5 | Blockwork | Activity | Architectural | B1 | 7 | 01-Apr-2027 | 08-Apr-2027 | 03.01.01.05 | Masonry Crew (10 men) | C-3150
03.01.01.05.02 | 5 | Plaster | Activity | Architectural | B1 | 7 | 04-Apr-2027 | 11-Apr-2027 | 03.01.01.05.01 | Plaster Crew (8 men) | C-3150
03.01.01.05.03 | 5 | Screed | Activity | Architectural | B1 | 7 | 07-Apr-2027 | 14-Apr-2027 | 03.01.01.05.02 | Architectural Finishes Crew | C-3150
03.01.01.05.04 | 5 | Ceiling | Activity | Architectural | B1 | 7 | 10-Apr-2027 | 17-Apr-2027 | 03.01.01.05.03 | Architectural Finishes Crew | C-3150
03.01.01.05.05 | 5 | Flooring | Activity | Architectural | B1 | 7 | 13-Apr-2027 | 20-Apr-2027 | 03.01.01.05.04 | Architectural Finishes Crew | C-3150
03.01.01.05.06 | 5 | Wall Finishes | Activity | Architectural | B1 | 7 | 16-Apr-2027 | 23-Apr-2027 | 03.01.01.05.05 | Architectural Finishes Crew | C-3150
03.01.01.05.07 | 5 | Painting | Activity | Architectural | B1 | 7 | 19-Apr-2027 | 26-Apr-2027 | 03.01.01.05.06 | Paint Crew | C-3150
03.01.01.05.08 | 5 | Doors | Activity | Architectural | B1 | 7 | 22-Apr-2027 | 29-Apr-2027 | 03.01.01.05.07 | Joinery Crew | C-3150
03.01.01.06 | 4 | 06 MEP | Work Package | MEP | B1 | 7 | 20-Mar-2027 | 15-May-2027 | 03.01.01.03 | MEP Crews | C-3160
03.01.01.06.01 | 5 | Electrical First Fix | Activity | MEP | B1 | 7 | 20-Mar-2027 | 27-Mar-2027 | 03.01.01.06 | Electrical Crew | C-3160
03.01.01.06.02 | 5 | Plumbing First Fix | Activity | MEP | B1 | 7 | 23-Mar-2027 | 30-Mar-2027 | 03.01.01.06.01 | Plumbing Crew | C-3160
03.01.01.06.03 | 5 | Drainage | Activity | MEP | B1 | 7 | 26-Mar-2027 | 02-Apr-2027 | 03.01.01.06.02 | Plumbing Crew | C-3160
03.01.01.06.04 | 5 | Fire Fighting | Activity | MEP | B1 | 7 | 29-Mar-2027 | 05-Apr-2027 | 03.01.01.06.03 | Fire Fighting / FA Crew | C-3160
03.01.01.06.05 | 5 | Fire Alarm | Activity | MEP | B1 | 7 | 01-Apr-2027 | 08-Apr-2027 | 03.01.01.06.04 | Fire Fighting / FA Crew | C-3160
03.01.01.06.06 | 5 | HVAC | Activity | MEP | B1 | 7 | 04-Apr-2027 | 11-Apr-2027 | 03.01.01.06.05 | HVAC Crew | C-3160
03.01.01.06.07 | 5 | ELV | Activity | MEP | B1 | 7 | 07-Apr-2027 | 14-Apr-2027 | 03.01.01.06.06 | ELV Crew | C-3160
03.01.01.06.08 | 5 | MEP Testing | Activity | MEP | B1 | 7 | 10-Apr-2027 | 17-Apr-2027 | 03.01.01.06.07 | MEP Crews | C-3160
03.01.02 | 3 | 03.01.02 GF | Work Package | Construction | GF | 76 | 01-May-2027 | 15-Jul-2027 | 03.01.01 | Site Team | C-32G1
03.01.02.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | GF | 10 | 01-May-2027 | 23-May-2027 | 03.01.02 | Structural Crew | C-32G1
03.01.02.01.01 | 5 | Setting Out | Activity | Structural | GF | 7 | 01-May-2027 | 08-May-2027 | 03.01.02.01 | Surveyor | C-32G1
03.01.02.01.02 | 5 | Column Reinforcement | Activity | Structural | GF | 10 | 03-May-2027 | 13-May-2027 | 03.01.02.01.01 | Rebar Crew (10 men) | C-32G1
03.01.02.01.03 | 5 | Column Formwork | Activity | Structural | GF | 10 | 05-May-2027 | 15-May-2027 | 03.01.02.01.02 | Formwork Crew (12 men) | C-32G1
03.01.02.01.04 | 5 | Column Concrete | Activity | Structural | GF | 10 | 07-May-2027 | 17-May-2027 | 03.01.02.01.03 | Concrete Crew, Pump Operator | C-32G1
03.01.02.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | GF | 12 | 09-May-2027 | 21-May-2027 | 03.01.02.01.01 | Rebar Crew (10 men) | C-32G1
03.01.02.01.06 | 5 | Shear Wall Formwork | Activity | Structural | GF | 12 | 11-May-2027 | 23-May-2027 | 03.01.02.01.05 | Formwork Crew (12 men) | C-32G1
03.01.02.01.07 | 5 | Shear Wall Concrete | Activity | Structural | GF | 12 | 11-May-2027 | 23-May-2027 | 03.01.02.01.06 | Concrete Crew, Pump Operator | C-32G1
03.01.02.01.08 | 5 | Beam Formwork | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.04,03.01.02.01.07 | Formwork Crew (12 men) | C-32G1
03.01.02.01.09 | 5 | Slab Formwork | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.04,03.01.02.01.07 | Formwork Crew (12 men) | C-32G1
03.01.02.01.10 | 5 | Beam Reinforcement | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.08 | Rebar Crew (10 men) | C-32G1
03.01.02.01.11 | 5 | Slab Reinforcement | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.09 | Rebar Crew (10 men) | C-32G1
03.01.02.01.12 | 5 | MEP Embedded Items | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.10,03.01.02.01.11 | MEP + Structural | C-32G1
03.01.02.01.13 | 5 | Structural Inspection | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.12 | QA/QC Inspector, Structural Engineer | C-32G1
03.01.02.01.14 | 5 | Concrete Pour | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.13 | Concrete Crew, Pump Operator | C-32G1
03.01.02.01.15 | 5 | Concrete Curing | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.14 | Concrete Crew, Pump Operator | C-32G1
03.01.02.01.16 | 5 | Formwork Removal | Activity | Structural | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.01.15 | Formwork Crew (12 men) | C-32G1
03.01.02.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | GF | 10 | 16-May-2027 | 15-Jun-2027 | 03.01.02.01.16 | Architectural Crew | C-32G1
03.01.02.02.01 | 5 | Blockwork | Activity | Architectural | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.02 | Masonry / Partition Crew | C-32G1
03.01.02.02.02 | 5 | Internal Partition | Activity | Architectural | GF | 10 | 18-May-2027 | 28-May-2027 | 03.01.02.02.01 | Masonry / Partition Crew | C-32G1
03.01.02.02.03 | 5 | Plastering | Activity | Architectural | GF | 10 | 20-May-2027 | 30-May-2027 | 03.01.02.02.02 | Plaster Crew (8 men) | C-32G1
03.01.02.02.04 | 5 | Waterproofing | Activity | Architectural | GF | 10 | 22-May-2027 | 01-Jun-2027 | 03.01.02.02.01 | WP Crew | C-32G1
03.01.02.02.05 | 5 | Screed | Activity | Architectural | GF | 10 | 24-May-2027 | 03-Jun-2027 | 03.01.02.02.04 | Screed Crew | C-32G1
03.01.02.02.06 | 5 | Ceiling | Activity | Architectural | GF | 12 | 26-May-2027 | 07-Jun-2027 | 03.01.02.03 | Ceiling Crew | C-32G1
03.01.02.02.07 | 5 | Flooring | Activity | Architectural | GF | 12 | 28-May-2027 | 09-Jun-2027 | 03.01.02.02.05 | Flooring / Tiling Crew | C-32G1
03.01.02.02.08 | 5 | Wall Tiling | Activity | Architectural | GF | 12 | 30-May-2027 | 11-Jun-2027 | 03.01.02.02.03 | Flooring / Tiling Crew | C-32G1
03.01.02.02.09 | 5 | Stone / Marble | Activity | Architectural | GF | 10 | 01-Jun-2027 | 11-Jun-2027 | 03.01.02.02.05 | Flooring / Tiling Crew | C-32G1
03.01.02.02.10 | 5 | Door Frames | Activity | Architectural | GF | 10 | 03-Jun-2027 | 13-Jun-2027 | 03.01.02.02.01 | Joinery / Glazing Crew | C-32G1
03.01.02.02.11 | 5 | Doors | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.02.10,03.01.02.02.15 | Joinery / Glazing Crew | C-32G1
03.01.02.02.12 | 5 | Windows | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.01.16 | Joinery / Glazing Crew | C-32G1
03.01.02.02.13 | 5 | Glass | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.02.12 | Joinery / Glazing Crew | C-32G1
03.01.02.02.14 | 5 | Painting Primer | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.02.03 | Paint Crew (6 men) | C-32G1
03.01.02.02.15 | 5 | Internal Painting | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.02.14 | Paint Crew (6 men) | C-32G1
03.01.02.02.16 | 5 | External Finishing | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.01.16 | External Finishes Crew | C-32G1
03.01.02.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.02.15 | Architectural Crew | C-32G1
03.01.02.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | GF | 10 | 11-May-2027 | 26-May-2027 | 03.01.02.01.16 | MEP First Fix Crews | C-32G1
03.01.02.03.01 | 5 | Electrical Conduits | Activity | MEP | GF | 10 | 11-May-2027 | 21-May-2027 | 03.01.02.03 | Electrical Crew (6 men) | C-32G1
03.01.02.03.02 | 5 | Cable Trays | Activity | MEP | GF | 10 | 13-May-2027 | 23-May-2027 | 03.01.02.03.01 | Electrical Crew (6 men) | C-32G1
03.01.02.03.03 | 5 | Plumbing Pipes | Activity | MEP | GF | 10 | 15-May-2027 | 25-May-2027 | 03.01.02.03.02 | Plumbing Crew (5 men) | C-32G1
03.01.02.03.04 | 5 | Drainage Pipes | Activity | MEP | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.03.03 | Plumbing Crew (5 men) | C-32G1
03.01.02.03.05 | 5 | HVAC Ductwork | Activity | MEP | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.03.04 | HVAC Crew (6 men) | C-32G1
03.01.02.03.06 | 5 | HVAC Pipes | Activity | MEP | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.03.05 | HVAC Crew (6 men) | C-32G1
03.01.02.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.03.06 | Fire Fighting / FA Crew | C-32G1
03.01.02.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.03.07 | Fire Fighting / FA Crew | C-32G1
03.01.02.03.09 | 5 | ELV Conduits | Activity | MEP | GF | 10 | 16-May-2027 | 26-May-2027 | 03.01.02.03.08 | ELV Crew | C-32G1
03.01.02.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | GF | 10 | 31-May-2027 | 15-Jun-2027 | 03.01.02.02.06,03.01.02.03 | MEP Second Fix Crews | C-32G1
03.01.02.04.01 | 5 | Cable Pulling | Activity | MEP | GF | 10 | 31-May-2027 | 10-Jun-2027 | 03.01.02.04 | Electrical Crew | C-32G1
03.01.02.04.02 | 5 | DB Installation | Activity | MEP | GF | 10 | 02-Jun-2027 | 12-Jun-2027 | 03.01.02.04.01 | Electrical Crew | C-32G1
03.01.02.04.03 | 5 | Lighting | Activity | MEP | GF | 10 | 04-Jun-2027 | 14-Jun-2027 | 03.01.02.04.02 | Electrical Crew | C-32G1
03.01.02.04.04 | 5 | Switches & Sockets | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.03 | Electrical Crew | C-32G1
03.01.02.04.05 | 5 | Plumbing Fixtures | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.04 | Plumbing Crew | C-32G1
03.01.02.04.06 | 5 | HVAC Equipment | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.05 | HVAC Crew | C-32G1
03.01.02.04.07 | 5 | Fire Alarm Devices | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.06 | Fire Fighting / FA Crew | C-32G1
03.01.02.04.08 | 5 | Sprinkler Heads | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.07 | Fire Fighting / FA Crew | C-32G1
03.01.02.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.08 | Fire Fighting / FA Crew | C-32G1
03.01.02.04.10 | 5 | ELV Devices | Activity | MEP | GF | 10 | 05-Jun-2027 | 15-Jun-2027 | 03.01.02.04.09 | ELV Crew | C-32G1
03.01.02.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | GF | 10 | 10-Jun-2027 | 18-Jun-2027 | 03.01.02.02.17,03.01.02.04 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.01 | 5 | Structural Inspection | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.01.16 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.02 | 5 | Architectural Inspection | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.02.17 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.03 | 5 | MEP Inspection | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.04 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.04 | 5 | Testing | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.05.03 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.05 | 5 | Snagging | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.05.04 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.06 | 5 | Snag Rectification | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.05.05 | QA/QC, Inspectors, All Trades | C-32G1
03.01.02.05.07 | 5 | Floor Completion | Activity | QA/QC | GF | 10 | 10-Jun-2027 | 20-Jun-2027 | 03.01.02.05.06 | QA/QC, Inspectors, All Trades | C-32G1
03.01.03 | 3 | 03.01.03 1F | Work Package | Construction | 1F | 80 | 28-May-2027 | 15-Aug-2027 | 03.01.02 | Site Team | C-3211
03.01.03.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 1F | 12 | 28-May-2027 | 19-Jun-2027 | 03.01.03 | Structural Crew | C-3211
03.01.03.01.01 | 5 | Setting Out | Activity | Structural | 1F | 7 | 28-May-2027 | 04-Jun-2027 | 03.01.03.01 | Surveyor | C-3211
03.01.03.01.02 | 5 | Column Reinforcement | Activity | Structural | 1F | 10 | 30-May-2027 | 09-Jun-2027 | 03.01.03.01.01 | Rebar Crew (10 men) | C-3211
03.01.03.01.03 | 5 | Column Formwork | Activity | Structural | 1F | 12 | 01-Jun-2027 | 13-Jun-2027 | 03.01.03.01.02 | Formwork Crew (12 men) | C-3211
03.01.03.01.04 | 5 | Column Concrete | Activity | Structural | 1F | 12 | 03-Jun-2027 | 15-Jun-2027 | 03.01.03.01.03 | Concrete Crew, Pump Operator | C-3211
03.01.03.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 1F | 12 | 05-Jun-2027 | 17-Jun-2027 | 03.01.03.01.01 | Rebar Crew (10 men) | C-3211
03.01.03.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.05 | Formwork Crew (12 men) | C-3211
03.01.03.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.06 | Concrete Crew, Pump Operator | C-3211
03.01.03.01.08 | 5 | Beam Formwork | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.04,03.01.03.01.07 | Formwork Crew (12 men) | C-3211
03.01.03.01.09 | 5 | Slab Formwork | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.04,03.01.03.01.07 | Formwork Crew (12 men) | C-3211
03.01.03.01.10 | 5 | Beam Reinforcement | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.08 | Rebar Crew (10 men) | C-3211
03.01.03.01.11 | 5 | Slab Reinforcement | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.09 | Rebar Crew (10 men) | C-3211
03.01.03.01.12 | 5 | MEP Embedded Items | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.10,03.01.03.01.11 | MEP + Structural | C-3211
03.01.03.01.13 | 5 | Structural Inspection | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.12 | QA/QC Inspector, Structural Engineer | C-3211
03.01.03.01.14 | 5 | Concrete Pour | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.13 | Concrete Crew, Pump Operator | C-3211
03.01.03.01.15 | 5 | Concrete Curing | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.14 | Concrete Crew, Pump Operator | C-3211
03.01.03.01.16 | 5 | Formwork Removal | Activity | Structural | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.01.15 | Formwork Crew (12 men) | C-3211
03.01.03.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 1F | 12 | 12-Jun-2027 | 12-Jul-2027 | 03.01.03.01.16 | Architectural Crew | C-3211
03.01.03.02.01 | 5 | Blockwork | Activity | Architectural | 1F | 12 | 12-Jun-2027 | 24-Jun-2027 | 03.01.03.02 | Masonry / Partition Crew | C-3211
03.01.03.02.02 | 5 | Internal Partition | Activity | Architectural | 1F | 12 | 14-Jun-2027 | 26-Jun-2027 | 03.01.03.02.01 | Masonry / Partition Crew | C-3211
03.01.03.02.03 | 5 | Plastering | Activity | Architectural | 1F | 12 | 16-Jun-2027 | 28-Jun-2027 | 03.01.03.02.02 | Plaster Crew (8 men) | C-3211
03.01.03.02.04 | 5 | Waterproofing | Activity | Architectural | 1F | 10 | 18-Jun-2027 | 28-Jun-2027 | 03.01.03.02.01 | WP Crew | C-3211
03.01.03.02.05 | 5 | Screed | Activity | Architectural | 1F | 12 | 20-Jun-2027 | 02-Jul-2027 | 03.01.03.02.04 | Screed Crew | C-3211
03.01.03.02.06 | 5 | Ceiling | Activity | Architectural | 1F | 12 | 22-Jun-2027 | 04-Jul-2027 | 03.01.03.03 | Ceiling Crew | C-3211
03.01.03.02.07 | 5 | Flooring | Activity | Architectural | 1F | 12 | 24-Jun-2027 | 06-Jul-2027 | 03.01.03.02.05 | Flooring / Tiling Crew | C-3211
03.01.03.02.08 | 5 | Wall Tiling | Activity | Architectural | 1F | 12 | 26-Jun-2027 | 08-Jul-2027 | 03.01.03.02.03 | Flooring / Tiling Crew | C-3211
03.01.03.02.09 | 5 | Stone / Marble | Activity | Architectural | 1F | 12 | 28-Jun-2027 | 10-Jul-2027 | 03.01.03.02.05 | Flooring / Tiling Crew | C-3211
03.01.03.02.10 | 5 | Door Frames | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.02.01 | Joinery / Glazing Crew | C-3211
03.01.03.02.11 | 5 | Doors | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.02.10,03.01.03.02.15 | Joinery / Glazing Crew | C-3211
03.01.03.02.12 | 5 | Windows | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.01.16 | Joinery / Glazing Crew | C-3211
03.01.03.02.13 | 5 | Glass | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.02.12 | Joinery / Glazing Crew | C-3211
03.01.03.02.14 | 5 | Painting Primer | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.02.03 | Paint Crew (6 men) | C-3211
03.01.03.02.15 | 5 | Internal Painting | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.02.14 | Paint Crew (6 men) | C-3211
03.01.03.02.16 | 5 | External Finishing | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.01.16 | External Finishes Crew | C-3211
03.01.03.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.02.15 | Architectural Crew | C-3211
03.01.03.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 1F | 12 | 07-Jun-2027 | 22-Jun-2027 | 03.01.03.01.16 | MEP First Fix Crews | C-3211
03.01.03.03.01 | 5 | Electrical Conduits | Activity | MEP | 1F | 12 | 07-Jun-2027 | 19-Jun-2027 | 03.01.03.03 | Electrical Crew (6 men) | C-3211
03.01.03.03.02 | 5 | Cable Trays | Activity | MEP | 1F | 12 | 09-Jun-2027 | 21-Jun-2027 | 03.01.03.03.01 | Electrical Crew (6 men) | C-3211
03.01.03.03.03 | 5 | Plumbing Pipes | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.02 | Plumbing Crew (5 men) | C-3211
03.01.03.03.04 | 5 | Drainage Pipes | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.03 | Plumbing Crew (5 men) | C-3211
03.01.03.03.05 | 5 | HVAC Ductwork | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.04 | HVAC Crew (6 men) | C-3211
03.01.03.03.06 | 5 | HVAC Pipes | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.05 | HVAC Crew (6 men) | C-3211
03.01.03.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.06 | Fire Fighting / FA Crew | C-3211
03.01.03.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.07 | Fire Fighting / FA Crew | C-3211
03.01.03.03.09 | 5 | ELV Conduits | Activity | MEP | 1F | 12 | 10-Jun-2027 | 22-Jun-2027 | 03.01.03.03.08 | ELV Crew | C-3211
03.01.03.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 1F | 12 | 27-Jun-2027 | 12-Jul-2027 | 03.01.03.02.06,03.01.03.03 | MEP Second Fix Crews | C-3211
03.01.03.04.01 | 5 | Cable Pulling | Activity | MEP | 1F | 12 | 27-Jun-2027 | 09-Jul-2027 | 03.01.03.04 | Electrical Crew | C-3211
03.01.03.04.02 | 5 | DB Installation | Activity | MEP | 1F | 12 | 29-Jun-2027 | 11-Jul-2027 | 03.01.03.04.01 | Electrical Crew | C-3211
03.01.03.04.03 | 5 | Lighting | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.02 | Electrical Crew | C-3211
03.01.03.04.04 | 5 | Switches & Sockets | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.03 | Electrical Crew | C-3211
03.01.03.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.04 | Plumbing Crew | C-3211
03.01.03.04.06 | 5 | HVAC Equipment | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.05 | HVAC Crew | C-3211
03.01.03.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.06 | Fire Fighting / FA Crew | C-3211
03.01.03.04.08 | 5 | Sprinkler Heads | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.07 | Fire Fighting / FA Crew | C-3211
03.01.03.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.08 | Fire Fighting / FA Crew | C-3211
03.01.03.04.10 | 5 | ELV Devices | Activity | MEP | 1F | 12 | 30-Jun-2027 | 12-Jul-2027 | 03.01.03.04.09 | ELV Crew | C-3211
03.01.03.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 1F | 12 | 07-Jul-2027 | 15-Jul-2027 | 03.01.03.02.17,03.01.03.04 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.01 | 5 | Structural Inspection | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.01.16 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.02.17 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.03 | 5 | MEP Inspection | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.04 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.04 | 5 | Testing | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.05.03 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.05 | 5 | Snagging | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.05.04 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.06 | 5 | Snag Rectification | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.05.05 | QA/QC, Inspectors, All Trades | C-3211
03.01.03.05.07 | 5 | Floor Completion | Activity | QA/QC | 1F | 12 | 07-Jul-2027 | 19-Jul-2027 | 03.01.03.05.06 | QA/QC, Inspectors, All Trades | C-3211
03.01.04 | 3 | 03.01.04 2F | Work Package | Construction | 2F | 83 | 25-Jun-2027 | 15-Sep-2027 | 03.01.03 | Site Team | C-3221
03.01.04.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 2F | 10 | 25-Jun-2027 | 17-Jul-2027 | 03.01.04 | Electrical Engineer | C-3221
03.01.04.01.01 | 5 | Setting Out | Activity | Structural | 2F | 7 | 25-Jun-2027 | 02-Jul-2027 | 03.01.04.01 | Electrical Engineer | C-3221
03.01.04.01.02 | 5 | Column Reinforcement | Activity | Structural | 2F | 10 | 27-Jun-2027 | 07-Jul-2027 | 03.01.04.01.01 | Electrical Engineer | C-3221
03.01.04.01.03 | 5 | Column Formwork | Activity | Structural | 2F | 12 | 29-Jun-2027 | 11-Jul-2027 | 03.01.04.01.02 | Electrical Engineer | C-3221
03.01.04.01.04 | 5 | Column Concrete | Activity | Structural | 2F | 10 | 01-Jul-2027 | 11-Jul-2027 | 03.01.04.01.03 | Electrical Engineer | C-3221
03.01.04.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 2F | 10 | 03-Jul-2027 | 13-Jul-2027 | 03.01.04.01.01 | Electrical Engineer | C-3221
03.01.04.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 2F | 10 | 05-Jul-2027 | 15-Jul-2027 | 03.01.04.01.05 | Electrical Engineer | C-3221
03.01.04.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.06 | Electrical Engineer | C-3221
03.01.04.01.08 | 5 | Beam Formwork | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.04,03.01.04.01.07 | Electrical Engineer | C-3221
03.01.04.01.09 | 5 | Slab Formwork | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.04,03.01.04.01.07 | Electrical Engineer | C-3221
03.01.04.01.10 | 5 | Beam Reinforcement | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.08 | Electrical Engineer | C-3221
03.01.04.01.11 | 5 | Slab Reinforcement | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.09 | Electrical Engineer | C-3221
03.01.04.01.12 | 5 | MEP Embedded Items | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.10,03.01.04.01.11 | Electrical Engineer | C-3221
03.01.04.01.13 | 5 | Structural Inspection | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.12 | Electrical Engineer | C-3221
03.01.04.01.14 | 5 | Concrete Pour | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.13 | Electrical Engineer | C-3221
03.01.04.01.15 | 5 | Concrete Curing | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.14 | Electrical Engineer | C-3221
03.01.04.01.16 | 5 | Formwork Removal | Activity | Structural | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.01.15 | Electrical Engineer | C-3221
03.01.04.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 2F | 10 | 10-Jul-2027 | 09-Aug-2027 | 03.01.04.01.16 | ELV Engineer | C-3221
03.01.04.02.01 | 5 | Blockwork | Activity | Architectural | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.02 | ELV Engineer | C-3221
03.01.04.02.02 | 5 | Internal Partition | Activity | Architectural | 2F | 10 | 12-Jul-2027 | 22-Jul-2027 | 03.01.04.02.01 | ELV Engineer | C-3221
03.01.04.02.03 | 5 | Plastering | Activity | Architectural | 2F | 10 | 14-Jul-2027 | 24-Jul-2027 | 03.01.04.02.02 | ELV Engineer | C-3221
03.01.04.02.04 | 5 | Waterproofing | Activity | Architectural | 2F | 10 | 16-Jul-2027 | 26-Jul-2027 | 03.01.04.02.01 | ELV Engineer | C-3221
03.01.04.02.05 | 5 | Screed | Activity | Architectural | 2F | 10 | 18-Jul-2027 | 28-Jul-2027 | 03.01.04.02.04 | ELV Engineer | C-3221
03.01.04.02.06 | 5 | Ceiling | Activity | Architectural | 2F | 10 | 20-Jul-2027 | 30-Jul-2027 | 03.01.04.03 | ELV Engineer | C-3221
03.01.04.02.07 | 5 | Flooring | Activity | Architectural | 2F | 10 | 22-Jul-2027 | 01-Aug-2027 | 03.01.04.02.05 | ELV Engineer | C-3221
03.01.04.02.08 | 5 | Wall Tiling | Activity | Architectural | 2F | 10 | 24-Jul-2027 | 03-Aug-2027 | 03.01.04.02.03 | ELV Engineer | C-3221
03.01.04.02.09 | 5 | Stone / Marble | Activity | Architectural | 2F | 10 | 26-Jul-2027 | 05-Aug-2027 | 03.01.04.02.05 | ELV Engineer | C-3221
03.01.04.02.10 | 5 | Door Frames | Activity | Architectural | 2F | 10 | 28-Jul-2027 | 07-Aug-2027 | 03.01.04.02.01 | ELV Engineer | C-3221
03.01.04.02.11 | 5 | Doors | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.02.10,03.01.04.02.15 | ELV Engineer | C-3221
03.01.04.02.12 | 5 | Windows | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.01.16 | ELV Engineer | C-3221
03.01.04.02.13 | 5 | Glass | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.02.12 | ELV Engineer | C-3221
03.01.04.02.14 | 5 | Painting Primer | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.02.03 | ELV Engineer | C-3221
03.01.04.02.15 | 5 | Internal Painting | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.02.14 | ELV Engineer | C-3221
03.01.04.02.16 | 5 | External Finishing | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.01.16 | ELV Engineer | C-3221
03.01.04.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.02.15 | ELV Engineer | C-3221
03.01.04.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 2F | 10 | 05-Jul-2027 | 20-Jul-2027 | 03.01.04.01.16 | Fire Alarm Engineer | C-3221
03.01.04.03.01 | 5 | Electrical Conduits | Activity | MEP | 2F | 10 | 05-Jul-2027 | 15-Jul-2027 | 03.01.04.03 | Fire Alarm Engineer | C-3221
03.01.04.03.02 | 5 | Cable Trays | Activity | MEP | 2F | 10 | 07-Jul-2027 | 17-Jul-2027 | 03.01.04.03.01 | Fire Alarm Engineer | C-3221
03.01.04.03.03 | 5 | Plumbing Pipes | Activity | MEP | 2F | 10 | 09-Jul-2027 | 19-Jul-2027 | 03.01.04.03.02 | Fire Alarm Engineer | C-3221
03.01.04.03.04 | 5 | Drainage Pipes | Activity | MEP | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.03.03 | Fire Alarm Engineer | C-3221
03.01.04.03.05 | 5 | HVAC Ductwork | Activity | MEP | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.03.04 | Fire Alarm Engineer | C-3221
03.01.04.03.06 | 5 | HVAC Pipes | Activity | MEP | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.03.05 | Fire Alarm Engineer | C-3221
03.01.04.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.03.06 | Fire Alarm Engineer | C-3221
03.01.04.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.03.07 | Fire Alarm Engineer | C-3221
03.01.04.03.09 | 5 | ELV Conduits | Activity | MEP | 2F | 10 | 10-Jul-2027 | 20-Jul-2027 | 03.01.04.03.08 | Fire Alarm Engineer | C-3221
03.01.04.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 2F | 10 | 25-Jul-2027 | 09-Aug-2027 | 03.01.04.02.06,03.01.04.03 | HVAC Engineer | C-3221
03.01.04.04.01 | 5 | Cable Pulling | Activity | MEP | 2F | 10 | 25-Jul-2027 | 04-Aug-2027 | 03.01.04.04 | HVAC Engineer | C-3221
03.01.04.04.02 | 5 | DB Installation | Activity | MEP | 2F | 10 | 27-Jul-2027 | 06-Aug-2027 | 03.01.04.04.01 | HVAC Engineer | C-3221
03.01.04.04.03 | 5 | Lighting | Activity | MEP | 2F | 10 | 29-Jul-2027 | 08-Aug-2027 | 03.01.04.04.02 | HVAC Engineer | C-3221
03.01.04.04.04 | 5 | Switches & Sockets | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.03 | HVAC Engineer | C-3221
03.01.04.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.04 | HVAC Engineer | C-3221
03.01.04.04.06 | 5 | HVAC Equipment | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.05 | HVAC Engineer | C-3221
03.01.04.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.06 | HVAC Engineer | C-3221
03.01.04.04.08 | 5 | Sprinkler Heads | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.07 | HVAC Engineer | C-3221
03.01.04.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.08 | HVAC Engineer | C-3221
03.01.04.04.10 | 5 | ELV Devices | Activity | MEP | 2F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.04.04.09 | HVAC Engineer | C-3221
03.01.04.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 2F | 10 | 04-Aug-2027 | 12-Aug-2027 | 03.01.04.02.17,03.01.04.04 | Plumbing Engineer | C-3221
03.01.04.05.01 | 5 | Structural Inspection | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.01.16 | Plumbing Engineer | C-3221
03.01.04.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.02.17 | Plumbing Engineer | C-3221
03.01.04.05.03 | 5 | MEP Inspection | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.04 | Plumbing Engineer | C-3221
03.01.04.05.04 | 5 | Testing | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.05.03 | Plumbing Engineer | C-3221
03.01.04.05.05 | 5 | Snagging | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.05.04 | Plumbing Engineer | C-3221
03.01.04.05.06 | 5 | Snag Rectification | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.05.05 | Plumbing Engineer | C-3221
03.01.04.05.07 | 5 | Floor Completion | Activity | QA/QC | 2F | 10 | 04-Aug-2027 | 14-Aug-2027 | 03.01.04.05.06 | Plumbing Engineer | C-3221
03.01.05 | 3 | 03.01.05 3F | Work Package | Construction | 3F | 86 | 22-Jul-2027 | 15-Oct-2027 | 03.01.04 | Site Team | C-3231
03.01.05.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 3F | 10 | 22-Jul-2027 | 13-Aug-2027 | 03.01.05 | Structural Crew | C-3231
03.01.05.01.01 | 5 | Setting Out | Activity | Structural | 3F | 7 | 22-Jul-2027 | 29-Jul-2027 | 03.01.05.01 | Surveyor | C-3231
03.01.05.01.02 | 5 | Column Reinforcement | Activity | Structural | 3F | 10 | 24-Jul-2027 | 03-Aug-2027 | 03.01.05.01.01 | Rebar Crew (10 men) | C-3231
03.01.05.01.03 | 5 | Column Formwork | Activity | Structural | 3F | 12 | 26-Jul-2027 | 07-Aug-2027 | 03.01.05.01.02 | Formwork Crew (12 men) | C-3231
03.01.05.01.04 | 5 | Column Concrete | Activity | Structural | 3F | 10 | 28-Jul-2027 | 07-Aug-2027 | 03.01.05.01.03 | Concrete Crew, Pump Operator | C-3231
03.01.05.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 3F | 10 | 30-Jul-2027 | 09-Aug-2027 | 03.01.05.01.01 | Rebar Crew (10 men) | C-3231
03.01.05.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 3F | 10 | 01-Aug-2027 | 11-Aug-2027 | 03.01.05.01.05 | Formwork Crew (12 men) | C-3231
03.01.05.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.06 | Concrete Crew, Pump Operator | C-3231
03.01.05.01.08 | 5 | Beam Formwork | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.04,03.01.05.01.07 | Formwork Crew (12 men) | C-3231
03.01.05.01.09 | 5 | Slab Formwork | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.04,03.01.05.01.07 | Formwork Crew (12 men) | C-3231
03.01.05.01.10 | 5 | Beam Reinforcement | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.08 | Rebar Crew (10 men) | C-3231
03.01.05.01.11 | 5 | Slab Reinforcement | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.09 | Rebar Crew (10 men) | C-3231
03.01.05.01.12 | 5 | MEP Embedded Items | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.10,03.01.05.01.11 | MEP + Structural | C-3231
03.01.05.01.13 | 5 | Structural Inspection | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.12 | QA/QC Inspector, Structural Engineer | C-3231
03.01.05.01.14 | 5 | Concrete Pour | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.13 | Concrete Crew, Pump Operator | C-3231
03.01.05.01.15 | 5 | Concrete Curing | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.14 | Concrete Crew, Pump Operator | C-3231
03.01.05.01.16 | 5 | Formwork Removal | Activity | Structural | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.01.15 | Formwork Crew (12 men) | C-3231
03.01.05.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 3F | 10 | 06-Aug-2027 | 05-Sep-2027 | 03.01.05.01.16 | Architectural Crew | C-3231
03.01.05.02.01 | 5 | Blockwork | Activity | Architectural | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.02 | Masonry / Partition Crew | C-3231
03.01.05.02.02 | 5 | Internal Partition | Activity | Architectural | 3F | 10 | 08-Aug-2027 | 18-Aug-2027 | 03.01.05.02.01 | Masonry / Partition Crew | C-3231
03.01.05.02.03 | 5 | Plastering | Activity | Architectural | 3F | 10 | 10-Aug-2027 | 20-Aug-2027 | 03.01.05.02.02 | Plaster Crew (8 men) | C-3231
03.01.05.02.04 | 5 | Waterproofing | Activity | Architectural | 3F | 10 | 12-Aug-2027 | 22-Aug-2027 | 03.01.05.02.01 | WP Crew | C-3231
03.01.05.02.05 | 5 | Screed | Activity | Architectural | 3F | 10 | 14-Aug-2027 | 24-Aug-2027 | 03.01.05.02.04 | Screed Crew | C-3231
03.01.05.02.06 | 5 | Ceiling | Activity | Architectural | 3F | 10 | 16-Aug-2027 | 26-Aug-2027 | 03.01.05.03 | Ceiling Crew | C-3231
03.01.05.02.07 | 5 | Flooring | Activity | Architectural | 3F | 10 | 18-Aug-2027 | 28-Aug-2027 | 03.01.05.02.05 | Flooring / Tiling Crew | C-3231
03.01.05.02.08 | 5 | Wall Tiling | Activity | Architectural | 3F | 10 | 20-Aug-2027 | 30-Aug-2027 | 03.01.05.02.03 | Flooring / Tiling Crew | C-3231
03.01.05.02.09 | 5 | Stone / Marble | Activity | Architectural | 3F | 10 | 22-Aug-2027 | 01-Sep-2027 | 03.01.05.02.05 | Flooring / Tiling Crew | C-3231
03.01.05.02.10 | 5 | Door Frames | Activity | Architectural | 3F | 10 | 24-Aug-2027 | 03-Sep-2027 | 03.01.05.02.01 | Joinery / Glazing Crew | C-3231
03.01.05.02.11 | 5 | Doors | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.02.10,03.01.05.02.15 | Joinery / Glazing Crew | C-3231
03.01.05.02.12 | 5 | Windows | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.01.16 | Joinery / Glazing Crew | C-3231
03.01.05.02.13 | 5 | Glass | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.02.12 | Joinery / Glazing Crew | C-3231
03.01.05.02.14 | 5 | Painting Primer | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.02.03 | Paint Crew (6 men) | C-3231
03.01.05.02.15 | 5 | Internal Painting | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.02.14 | Paint Crew (6 men) | C-3231
03.01.05.02.16 | 5 | External Finishing | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.01.16 | External Finishes Crew | C-3231
03.01.05.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.02.15 | Architectural Crew | C-3231
03.01.05.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 3F | 10 | 01-Aug-2027 | 16-Aug-2027 | 03.01.05.01.16 | MEP First Fix Crews | C-3231
03.01.05.03.01 | 5 | Electrical Conduits | Activity | MEP | 3F | 10 | 01-Aug-2027 | 11-Aug-2027 | 03.01.05.03 | Electrical Crew (6 men) | C-3231
03.01.05.03.02 | 5 | Cable Trays | Activity | MEP | 3F | 10 | 03-Aug-2027 | 13-Aug-2027 | 03.01.05.03.01 | Electrical Crew (6 men) | C-3231
03.01.05.03.03 | 5 | Plumbing Pipes | Activity | MEP | 3F | 10 | 05-Aug-2027 | 15-Aug-2027 | 03.01.05.03.02 | Plumbing Crew (5 men) | C-3231
03.01.05.03.04 | 5 | Drainage Pipes | Activity | MEP | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.03.03 | Plumbing Crew (5 men) | C-3231
03.01.05.03.05 | 5 | HVAC Ductwork | Activity | MEP | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.03.04 | HVAC Crew (6 men) | C-3231
03.01.05.03.06 | 5 | HVAC Pipes | Activity | MEP | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.03.05 | HVAC Crew (6 men) | C-3231
03.01.05.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.03.06 | Fire Fighting / FA Crew | C-3231
03.01.05.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.03.07 | Fire Fighting / FA Crew | C-3231
03.01.05.03.09 | 5 | ELV Conduits | Activity | MEP | 3F | 10 | 06-Aug-2027 | 16-Aug-2027 | 03.01.05.03.08 | ELV Crew | C-3231
03.01.05.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 3F | 10 | 21-Aug-2027 | 05-Sep-2027 | 03.01.05.02.06,03.01.05.03 | MEP Second Fix Crews | C-3231
03.01.05.04.01 | 5 | Cable Pulling | Activity | MEP | 3F | 10 | 21-Aug-2027 | 31-Aug-2027 | 03.01.05.04 | Electrical Crew | C-3231
03.01.05.04.02 | 5 | DB Installation | Activity | MEP | 3F | 10 | 23-Aug-2027 | 02-Sep-2027 | 03.01.05.04.01 | Electrical Crew | C-3231
03.01.05.04.03 | 5 | Lighting | Activity | MEP | 3F | 10 | 25-Aug-2027 | 04-Sep-2027 | 03.01.05.04.02 | Electrical Crew | C-3231
03.01.05.04.04 | 5 | Switches & Sockets | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.03 | Electrical Crew | C-3231
03.01.05.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.04 | Plumbing Crew | C-3231
03.01.05.04.06 | 5 | HVAC Equipment | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.05 | HVAC Crew | C-3231
03.01.05.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.06 | Fire Fighting / FA Crew | C-3231
03.01.05.04.08 | 5 | Sprinkler Heads | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.07 | Fire Fighting / FA Crew | C-3231
03.01.05.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.08 | Fire Fighting / FA Crew | C-3231
03.01.05.04.10 | 5 | ELV Devices | Activity | MEP | 3F | 10 | 26-Aug-2027 | 05-Sep-2027 | 03.01.05.04.09 | ELV Crew | C-3231
03.01.05.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 3F | 10 | 31-Aug-2027 | 08-Sep-2027 | 03.01.05.02.17,03.01.05.04 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.01 | 5 | Structural Inspection | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.01.16 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.02.17 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.03 | 5 | MEP Inspection | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.04 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.04 | 5 | Testing | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.05.03 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.05 | 5 | Snagging | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.05.04 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.06 | 5 | Snag Rectification | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.05.05 | QA/QC, Inspectors, All Trades | C-3231
03.01.05.05.07 | 5 | Floor Completion | Activity | QA/QC | 3F | 10 | 31-Aug-2027 | 10-Sep-2027 | 03.01.05.05.06 | QA/QC, Inspectors, All Trades | C-3231
03.01.06 | 3 | 03.01.06 4F | Work Package | Construction | 4F | 89 | 19-Aug-2027 | 15-Nov-2027 | 03.01.05 | Site Team | C-3241
03.01.06.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 4F | 15 | 19-Aug-2027 | 10-Sep-2027 | 03.01.06 | Structural Crew | C-3241
03.01.06.01.01 | 5 | Setting Out | Activity | Structural | 4F | 7 | 19-Aug-2027 | 26-Aug-2027 | 03.01.06.01 | Surveyor | C-3241
03.01.06.01.02 | 5 | Column Reinforcement | Activity | Structural | 4F | 10 | 21-Aug-2027 | 31-Aug-2027 | 03.01.06.01.01 | Rebar Crew (10 men) | C-3241
03.01.06.01.03 | 5 | Column Formwork | Activity | Structural | 4F | 12 | 23-Aug-2027 | 04-Sep-2027 | 03.01.06.01.02 | Formwork Crew (12 men) | C-3241
03.01.06.01.04 | 5 | Column Concrete | Activity | Structural | 4F | 10 | 25-Aug-2027 | 04-Sep-2027 | 03.01.06.01.03 | Concrete Crew, Pump Operator | C-3241
03.01.06.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 4F | 10 | 27-Aug-2027 | 06-Sep-2027 | 03.01.06.01.01 | Rebar Crew (10 men) | C-3241
03.01.06.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 4F | 20 | 21-Aug-2027 | 10-Sep-2027 | 03.01.06.01.05 | Formwork Crew (12 men) | C-3241
03.01.06.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.06 | Concrete Crew, Pump Operator | C-3241
03.01.06.01.08 | 5 | Beam Formwork | Activity | Structural | 4F | 20 | 21-Aug-2027 | 10-Sep-2027 | 03.01.06.01.04,03.01.06.01.07 | Formwork Crew (12 men) | C-3241
03.01.06.01.09 | 5 | Slab Formwork | Activity | Structural | 4F | 20 | 21-Aug-2027 | 10-Sep-2027 | 03.01.06.01.04,03.01.06.01.07 | Formwork Crew (12 men) | C-3241
03.01.06.01.10 | 5 | Beam Reinforcement | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.08 | Rebar Crew (10 men) | C-3241
03.01.06.01.11 | 5 | Slab Reinforcement | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.09 | Rebar Crew (10 men) | C-3241
03.01.06.01.12 | 5 | MEP Embedded Items | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.10,03.01.06.01.11 | MEP + Structural | C-3241
03.01.06.01.13 | 5 | Structural Inspection | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.12 | QA/QC Inspector, Structural Engineer | C-3241
03.01.06.01.14 | 5 | Concrete Pour | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.13 | Concrete Crew, Pump Operator | C-3241
03.01.06.01.15 | 5 | Concrete Curing | Activity | Structural | 4F | 15 | 26-Aug-2027 | 10-Sep-2027 | 03.01.06.01.14 | Concrete Crew, Pump Operator | C-3241
03.01.06.01.16 | 5 | Formwork Removal | Activity | Structural | 4F | 20 | 21-Aug-2027 | 10-Sep-2027 | 03.01.06.01.15 | Formwork Crew (12 men) | C-3241
03.01.06.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 4F | 15 | 03-Sep-2027 | 03-Oct-2027 | 03.01.06.01.16 | Architectural Crew | C-3241
03.01.06.02.01 | 5 | Blockwork | Activity | Architectural | 4F | 15 | 03-Sep-2027 | 18-Sep-2027 | 03.01.06.02 | Masonry / Partition Crew | C-3241
03.01.06.02.02 | 5 | Internal Partition | Activity | Architectural | 4F | 15 | 05-Sep-2027 | 20-Sep-2027 | 03.01.06.02.01 | Masonry / Partition Crew | C-3241
03.01.06.02.03 | 5 | Plastering | Activity | Architectural | 4F | 15 | 07-Sep-2027 | 22-Sep-2027 | 03.01.06.02.02 | Plaster Crew (8 men) | C-3241
03.01.06.02.04 | 5 | Waterproofing | Activity | Architectural | 4F | 15 | 09-Sep-2027 | 24-Sep-2027 | 03.01.06.02.01 | WP Crew | C-3241
03.01.06.02.05 | 5 | Screed | Activity | Architectural | 4F | 15 | 11-Sep-2027 | 26-Sep-2027 | 03.01.06.02.04 | Screed Crew | C-3241
03.01.06.02.06 | 5 | Ceiling | Activity | Architectural | 4F | 15 | 13-Sep-2027 | 28-Sep-2027 | 03.01.06.03 | Ceiling Crew | C-3241
03.01.06.02.07 | 5 | Flooring | Activity | Architectural | 4F | 15 | 15-Sep-2027 | 30-Sep-2027 | 03.01.06.02.05 | Flooring / Tiling Crew | C-3241
03.01.06.02.08 | 5 | Wall Tiling | Activity | Architectural | 4F | 15 | 17-Sep-2027 | 02-Oct-2027 | 03.01.06.02.03 | Flooring / Tiling Crew | C-3241
03.01.06.02.09 | 5 | Stone / Marble | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.05 | Flooring / Tiling Crew | C-3241
03.01.06.02.10 | 5 | Door Frames | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.01 | Joinery / Glazing Crew | C-3241
03.01.06.02.11 | 5 | Doors | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.10,03.01.06.02.15 | Joinery / Glazing Crew | C-3241
03.01.06.02.12 | 5 | Windows | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.01.16 | Joinery / Glazing Crew | C-3241
03.01.06.02.13 | 5 | Glass | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.12 | Joinery / Glazing Crew | C-3241
03.01.06.02.14 | 5 | Painting Primer | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.03 | Paint Crew (6 men) | C-3241
03.01.06.02.15 | 5 | Internal Painting | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.14 | Paint Crew (6 men) | C-3241
03.01.06.02.16 | 5 | External Finishing | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.01.16 | External Finishes Crew | C-3241
03.01.06.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.15 | Architectural Crew | C-3241
03.01.06.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.01.16 | MEP First Fix Crews | C-3241
03.01.06.03.01 | 5 | Electrical Conduits | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03 | Electrical Crew (6 men) | C-3241
03.01.06.03.02 | 5 | Cable Trays | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.01 | Electrical Crew (6 men) | C-3241
03.01.06.03.03 | 5 | Plumbing Pipes | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.02 | Plumbing Crew (5 men) | C-3241
03.01.06.03.04 | 5 | Drainage Pipes | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.03 | Plumbing Crew (5 men) | C-3241
03.01.06.03.05 | 5 | HVAC Ductwork | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.04 | HVAC Crew (6 men) | C-3241
03.01.06.03.06 | 5 | HVAC Pipes | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.05 | HVAC Crew (6 men) | C-3241
03.01.06.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.06 | Fire Fighting / FA Crew | C-3241
03.01.06.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.07 | Fire Fighting / FA Crew | C-3241
03.01.06.03.09 | 5 | ELV Conduits | Activity | MEP | 4F | 15 | 29-Aug-2027 | 13-Sep-2027 | 03.01.06.03.08 | ELV Crew | C-3241
03.01.06.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.02.06,03.01.06.03 | MEP Second Fix Crews | C-3241
03.01.06.04.01 | 5 | Cable Pulling | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04 | Electrical Crew | C-3241
03.01.06.04.02 | 5 | DB Installation | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.01 | Electrical Crew | C-3241
03.01.06.04.03 | 5 | Lighting | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.02 | Electrical Crew | C-3241
03.01.06.04.04 | 5 | Switches & Sockets | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.03 | Electrical Crew | C-3241
03.01.06.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.04 | Plumbing Crew | C-3241
03.01.06.04.06 | 5 | HVAC Equipment | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.05 | HVAC Crew | C-3241
03.01.06.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.06 | Fire Fighting / FA Crew | C-3241
03.01.06.04.08 | 5 | Sprinkler Heads | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.07 | Fire Fighting / FA Crew | C-3241
03.01.06.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.08 | Fire Fighting / FA Crew | C-3241
03.01.06.04.10 | 5 | ELV Devices | Activity | MEP | 4F | 15 | 18-Sep-2027 | 03-Oct-2027 | 03.01.06.04.09 | ELV Crew | C-3241
03.01.06.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 4F | 15 | 28-Sep-2027 | 06-Oct-2027 | 03.01.06.02.17,03.01.06.04 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.01 | 5 | Structural Inspection | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.01.16 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.02.17 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.03 | 5 | MEP Inspection | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.04 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.04 | 5 | Testing | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.05.03 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.05 | 5 | Snagging | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.05.04 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.06 | 5 | Snag Rectification | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.05.05 | QA/QC, Inspectors, All Trades | C-3241
03.01.06.05.07 | 5 | Floor Completion | Activity | QA/QC | 4F | 15 | 28-Sep-2027 | 13-Oct-2027 | 03.01.06.05.06 | QA/QC, Inspectors, All Trades | C-3241
03.01.07 | 3 | 03.01.07 5F | Work Package | Construction | 5F | 91 | 16-Sep-2027 | 15-Dec-2027 | 03.01.06 | Site Team | C-3251
03.01.07.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 5F | 2 | 16-Sep-2027 | 08-Oct-2027 | 03.01.07 | Structural Crew | C-3251
03.01.07.01.01 | 5 | Setting Out | Activity | Structural | 5F | 7 | 16-Sep-2027 | 23-Sep-2027 | 03.01.07.01 | Surveyor | C-3251
03.01.07.01.02 | 5 | Column Reinforcement | Activity | Structural | 5F | 10 | 18-Sep-2027 | 28-Sep-2027 | 03.01.07.01.01 | Rebar Crew (10 men) | C-3251
03.01.07.01.03 | 5 | Column Formwork | Activity | Structural | 5F | 12 | 20-Sep-2027 | 02-Oct-2027 | 03.01.07.01.02 | Formwork Crew (12 men) | C-3251
03.01.07.01.04 | 5 | Column Concrete | Activity | Structural | 5F | 10 | 22-Sep-2027 | 02-Oct-2027 | 03.01.07.01.03 | Concrete Crew, Pump Operator | C-3251
03.01.07.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 5F | 10 | 24-Sep-2027 | 04-Oct-2027 | 03.01.07.01.01 | Rebar Crew (10 men) | C-3251
03.01.07.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 5F | 20 | 18-Sep-2027 | 08-Oct-2027 | 03.01.07.01.05 | Formwork Crew (12 men) | C-3251
03.01.07.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 5F | 1 | 28-Sep-2027 | 29-Sep-2027 | 03.01.07.01.06 | Concrete Crew, Pump Operator | C-3251
03.01.07.01.08 | 5 | Beam Formwork | Activity | Structural | 5F | 3 | 30-Sep-2027 | 03-Oct-2027 | 03.01.07.01.04,03.01.07.01.07 | Formwork Crew (12 men) | C-3251
03.01.07.01.09 | 5 | Slab Formwork | Activity | Structural | 5F | 3 | 02-Oct-2027 | 05-Oct-2027 | 03.01.07.01.04,03.01.07.01.07 | Formwork Crew (12 men) | C-3251
03.01.07.01.10 | 5 | Beam Reinforcement | Activity | Structural | 5F | 2 | 04-Oct-2027 | 06-Oct-2027 | 03.01.07.01.08 | Rebar Crew (10 men) | C-3251
03.01.07.01.11 | 5 | Slab Reinforcement | Activity | Structural | 5F | 2 | 06-Oct-2027 | 08-Oct-2027 | 03.01.07.01.09 | Rebar Crew (10 men) | C-3251
03.01.07.01.12 | 5 | MEP Embedded Items | Activity | Structural | 5F | 1 | 07-Oct-2027 | 08-Oct-2027 | 03.01.07.01.10,03.01.07.01.11 | MEP + Structural | C-3251
03.01.07.01.13 | 5 | Structural Inspection | Activity | Structural | 5F | 1 | 07-Oct-2027 | 08-Oct-2027 | 03.01.07.01.12 | QA/QC Inspector, Structural Engineer | C-3251
03.01.07.01.14 | 5 | Concrete Pour | Activity | Structural | 5F | 1 | 07-Oct-2027 | 08-Oct-2027 | 03.01.07.01.13 | Concrete Crew, Pump Operator | C-3251
03.01.07.01.15 | 5 | Concrete Curing | Activity | Structural | 5F | 7 | 01-Oct-2027 | 08-Oct-2027 | 03.01.07.01.14 | Concrete Crew, Pump Operator | C-3251
03.01.07.01.16 | 5 | Formwork Removal | Activity | Structural | 5F | 2 | 06-Oct-2027 | 08-Oct-2027 | 03.01.07.01.15 | Formwork Crew (12 men) | C-3251
03.01.07.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 5F | 2 | 01-Oct-2027 | 31-Oct-2027 | 03.01.07.01.16 | Architectural Crew | C-3251
03.01.07.02.01 | 5 | Blockwork | Activity | Architectural | 5F | 10 | 01-Oct-2027 | 11-Oct-2027 | 03.01.07.02 | Masonry / Partition Crew | C-3251
03.01.07.02.02 | 5 | Internal Partition | Activity | Architectural | 5F | 60 | 01-Oct-2027 | 30-Nov-2027 | 03.01.07.02.01 | Masonry / Partition Crew | C-3251
03.01.07.02.03 | 5 | Plastering | Activity | Architectural | 5F | 60 | 01-Oct-2027 | 30-Nov-2027 | 03.01.07.02.02 | Plaster Crew (8 men) | C-3251
03.01.07.02.04 | 5 | Waterproofing | Activity | Architectural | 5F | 60 | 01-Oct-2027 | 30-Nov-2027 | 03.01.07.02.01 | WP Crew | C-3251
03.01.07.02.05 | 5 | Screed | Activity | Architectural | 5F | 7 | 09-Oct-2027 | 16-Oct-2027 | 03.01.07.02.04 | Screed Crew | C-3251
03.01.07.02.06 | 5 | Ceiling | Activity | Architectural | 5F | 10 | 11-Oct-2027 | 21-Oct-2027 | 03.01.07.03 | Ceiling Crew | C-3251
03.01.07.02.07 | 5 | Flooring | Activity | Architectural | 5F | 5 | 13-Oct-2027 | 18-Oct-2027 | 03.01.07.02.05 | Flooring / Tiling Crew | C-3251
03.01.07.02.08 | 5 | Wall Tiling | Activity | Architectural | 5F | 2 | 15-Oct-2027 | 17-Oct-2027 | 03.01.07.02.03 | Flooring / Tiling Crew | C-3251
03.01.07.02.09 | 5 | Stone / Marble | Activity | Architectural | 5F | 2 | 17-Oct-2027 | 19-Oct-2027 | 03.01.07.02.05 | Flooring / Tiling Crew | C-3251
03.01.07.02.10 | 5 | Door Frames | Activity | Architectural | 5F | 2 | 19-Oct-2027 | 21-Oct-2027 | 03.01.07.02.01 | Joinery / Glazing Crew | C-3251
03.01.07.02.11 | 5 | Doors | Activity | Architectural | 5F | 2 | 21-Oct-2027 | 23-Oct-2027 | 03.01.07.02.10,03.01.07.02.15 | Joinery / Glazing Crew | C-3251
03.01.07.02.12 | 5 | Windows | Activity | Architectural | 5F | 2 | 23-Oct-2027 | 25-Oct-2027 | 03.01.07.01.16 | Joinery / Glazing Crew | C-3251
03.01.07.02.13 | 5 | Glass | Activity | Architectural | 5F | 2 | 25-Oct-2027 | 27-Oct-2027 | 03.01.07.02.12 | Joinery / Glazing Crew | C-3251
03.01.07.02.14 | 5 | Painting Primer | Activity | Architectural | 5F | 2 | 27-Oct-2027 | 29-Oct-2027 | 03.01.07.02.03 | Paint Crew (6 men) | C-3251
03.01.07.02.15 | 5 | Internal Painting | Activity | Architectural | 5F | 2 | 29-Oct-2027 | 31-Oct-2027 | 03.01.07.02.14 | Paint Crew (6 men) | C-3251
03.01.07.02.16 | 5 | External Finishing | Activity | Architectural | 5F | 2 | 29-Oct-2027 | 31-Oct-2027 | 03.01.07.01.16 | External Finishes Crew | C-3251
03.01.07.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 5F | 2 | 29-Oct-2027 | 31-Oct-2027 | 03.01.07.02.15 | Architectural Crew | C-3251
03.01.07.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 5F | 2 | 26-Sep-2027 | 11-Oct-2027 | 03.01.07.01.16 | MEP First Fix Crews | C-3251
03.01.07.03.01 | 5 | Electrical Conduits | Activity | MEP | 5F | 2 | 26-Sep-2027 | 28-Sep-2027 | 03.01.07.03 | Electrical Crew (6 men) | C-3251
03.01.07.03.02 | 5 | Cable Trays | Activity | MEP | 5F | 2 | 28-Sep-2027 | 30-Sep-2027 | 03.01.07.03.01 | Electrical Crew (6 men) | C-3251
03.01.07.03.03 | 5 | Plumbing Pipes | Activity | MEP | 5F | 2 | 30-Sep-2027 | 02-Oct-2027 | 03.01.07.03.02 | Plumbing Crew (5 men) | C-3251
03.01.07.03.04 | 5 | Drainage Pipes | Activity | MEP | 5F | 2 | 02-Oct-2027 | 04-Oct-2027 | 03.01.07.03.03 | Plumbing Crew (5 men) | C-3251
03.01.07.03.05 | 5 | HVAC Ductwork | Activity | MEP | 5F | 2 | 04-Oct-2027 | 06-Oct-2027 | 03.01.07.03.04 | HVAC Crew (6 men) | C-3251
03.01.07.03.06 | 5 | HVAC Pipes | Activity | MEP | 5F | 2 | 06-Oct-2027 | 08-Oct-2027 | 03.01.07.03.05 | HVAC Crew (6 men) | C-3251
03.01.07.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 5F | 2 | 08-Oct-2027 | 10-Oct-2027 | 03.01.07.03.06 | Fire Fighting / FA Crew | C-3251
03.01.07.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 5F | 2 | 09-Oct-2027 | 11-Oct-2027 | 03.01.07.03.07 | Fire Fighting / FA Crew | C-3251
03.01.07.03.09 | 5 | ELV Conduits | Activity | MEP | 5F | 2 | 09-Oct-2027 | 11-Oct-2027 | 03.01.07.03.08 | ELV Crew | C-3251
03.01.07.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 5F | 2 | 16-Oct-2027 | 31-Oct-2027 | 03.01.07.02.06,03.01.07.03 | MEP Second Fix Crews | C-3251
03.01.07.04.01 | 5 | Cable Pulling | Activity | MEP | 5F | 2 | 16-Oct-2027 | 18-Oct-2027 | 03.01.07.04 | Electrical Crew | C-3251
03.01.07.04.02 | 5 | DB Installation | Activity | MEP | 5F | 2 | 18-Oct-2027 | 20-Oct-2027 | 03.01.07.04.01 | Electrical Crew | C-3251
03.01.07.04.03 | 5 | Lighting | Activity | MEP | 5F | 2 | 20-Oct-2027 | 22-Oct-2027 | 03.01.07.04.02 | Electrical Crew | C-3251
03.01.07.04.04 | 5 | Switches & Sockets | Activity | MEP | 5F | 2 | 22-Oct-2027 | 24-Oct-2027 | 03.01.07.04.03 | Electrical Crew | C-3251
03.01.07.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 5F | 2 | 24-Oct-2027 | 26-Oct-2027 | 03.01.07.04.04 | Plumbing Crew | C-3251
03.01.07.04.06 | 5 | HVAC Equipment | Activity | MEP | 5F | 2 | 26-Oct-2027 | 28-Oct-2027 | 03.01.07.04.05 | HVAC Crew | C-3251
03.01.07.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 5F | 2 | 28-Oct-2027 | 30-Oct-2027 | 03.01.07.04.06 | Fire Fighting / FA Crew | C-3251
03.01.07.04.08 | 5 | Sprinkler Heads | Activity | MEP | 5F | 2 | 29-Oct-2027 | 31-Oct-2027 | 03.01.07.04.07 | Fire Fighting / FA Crew | C-3251
03.01.07.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 5F | 2 | 29-Oct-2027 | 31-Oct-2027 | 03.01.07.04.08 | Fire Fighting / FA Crew | C-3251
03.01.07.04.10 | 5 | ELV Devices | Activity | MEP | 5F | 2 | 29-Oct-2027 | 31-Oct-2027 | 03.01.07.04.09 | ELV Crew | C-3251
03.01.07.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 5F | 1 | 26-Oct-2027 | 03-Nov-2027 | 03.01.07.02.17,03.01.07.04 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.01 | 5 | Structural Inspection | Activity | QA/QC | 5F | 1 | 26-Oct-2027 | 27-Oct-2027 | 03.01.07.01.16 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 5F | 1 | 28-Oct-2027 | 29-Oct-2027 | 03.01.07.02.17 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.03 | 5 | MEP Inspection | Activity | QA/QC | 5F | 1 | 30-Oct-2027 | 31-Oct-2027 | 03.01.07.04 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.04 | 5 | Testing | Activity | QA/QC | 5F | 2 | 01-Nov-2027 | 03-Nov-2027 | 03.01.07.05.03 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.05 | 5 | Snagging | Activity | QA/QC | 5F | 2 | 01-Nov-2027 | 03-Nov-2027 | 03.01.07.05.04 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.06 | 5 | Snag Rectification | Activity | QA/QC | 5F | 2 | 01-Nov-2027 | 03-Nov-2027 | 03.01.07.05.05 | QA/QC, Inspectors, All Trades | C-3251
03.01.07.05.07 | 5 | Floor Completion | Activity | QA/QC | 5F | 2 | 01-Nov-2027 | 03-Nov-2027 | 03.01.07.05.06 | QA/QC, Inspectors, All Trades | C-3251
03.01.08 | 3 | 03.01.08 6F | Work Package | Construction | 6F | 94 | 14-Oct-2027 | 15-Jan-2028 | 03.01.07 | Site Team | C-3261
03.01.08.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 6F | 2 | 14-Oct-2027 | 05-Nov-2027 | 03.01.08 | Structural Crew | C-3261
03.01.08.01.01 | 5 | Setting Out | Activity | Structural | 6F | 7 | 14-Oct-2027 | 21-Oct-2027 | 03.01.08.01 | Surveyor | C-3261
03.01.08.01.02 | 5 | Column Reinforcement | Activity | Structural | 6F | 10 | 16-Oct-2027 | 26-Oct-2027 | 03.01.08.01.01 | Rebar Crew (10 men) | C-3261
03.01.08.01.03 | 5 | Column Formwork | Activity | Structural | 6F | 12 | 18-Oct-2027 | 30-Oct-2027 | 03.01.08.01.02 | Formwork Crew (12 men) | C-3261
03.01.08.01.04 | 5 | Column Concrete | Activity | Structural | 6F | 10 | 20-Oct-2027 | 30-Oct-2027 | 03.01.08.01.03 | Concrete Crew, Pump Operator | C-3261
03.01.08.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 6F | 10 | 22-Oct-2027 | 01-Nov-2027 | 03.01.08.01.01 | Rebar Crew (10 men) | C-3261
03.01.08.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 6F | 20 | 16-Oct-2027 | 05-Nov-2027 | 03.01.08.01.05 | Formwork Crew (12 men) | C-3261
03.01.08.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 6F | 1 | 26-Oct-2027 | 27-Oct-2027 | 03.01.08.01.06 | Concrete Crew, Pump Operator | C-3261
03.01.08.01.08 | 5 | Beam Formwork | Activity | Structural | 6F | 3 | 28-Oct-2027 | 31-Oct-2027 | 03.01.08.01.04,03.01.08.01.07 | Formwork Crew (12 men) | C-3261
03.01.08.01.09 | 5 | Slab Formwork | Activity | Structural | 6F | 3 | 30-Oct-2027 | 02-Nov-2027 | 03.01.08.01.04,03.01.08.01.07 | Formwork Crew (12 men) | C-3261
03.01.08.01.10 | 5 | Beam Reinforcement | Activity | Structural | 6F | 2 | 01-Nov-2027 | 03-Nov-2027 | 03.01.08.01.08 | Rebar Crew (10 men) | C-3261
03.01.08.01.11 | 5 | Slab Reinforcement | Activity | Structural | 6F | 2 | 03-Nov-2027 | 05-Nov-2027 | 03.01.08.01.09 | Rebar Crew (10 men) | C-3261
03.01.08.01.12 | 5 | MEP Embedded Items | Activity | Structural | 6F | 1 | 04-Nov-2027 | 05-Nov-2027 | 03.01.08.01.10,03.01.08.01.11 | MEP + Structural | C-3261
03.01.08.01.13 | 5 | Structural Inspection | Activity | Structural | 6F | 1 | 04-Nov-2027 | 05-Nov-2027 | 03.01.08.01.12 | QA/QC Inspector, Structural Engineer | C-3261
03.01.08.01.14 | 5 | Concrete Pour | Activity | Structural | 6F | 1 | 04-Nov-2027 | 05-Nov-2027 | 03.01.08.01.13 | Concrete Crew, Pump Operator | C-3261
03.01.08.01.15 | 5 | Concrete Curing | Activity | Structural | 6F | 7 | 29-Oct-2027 | 05-Nov-2027 | 03.01.08.01.14 | Concrete Crew, Pump Operator | C-3261
03.01.08.01.16 | 5 | Formwork Removal | Activity | Structural | 6F | 2 | 03-Nov-2027 | 05-Nov-2027 | 03.01.08.01.15 | Formwork Crew (12 men) | C-3261
03.01.08.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 6F | 2 | 29-Oct-2027 | 28-Nov-2027 | 03.01.08.01.16 | Architectural Crew | C-3261
03.01.08.02.01 | 5 | Blockwork | Activity | Architectural | 6F | 10 | 29-Oct-2027 | 08-Nov-2027 | 03.01.08.02 | Masonry / Partition Crew | C-3261
03.01.08.02.02 | 5 | Internal Partition | Activity | Architectural | 6F | 60 | 29-Oct-2027 | 28-Dec-2027 | 03.01.08.02.01 | Masonry / Partition Crew | C-3261
03.01.08.02.03 | 5 | Plastering | Activity | Architectural | 6F | 60 | 29-Oct-2027 | 28-Dec-2027 | 03.01.08.02.02 | Plaster Crew (8 men) | C-3261
03.01.08.02.04 | 5 | Waterproofing | Activity | Architectural | 6F | 60 | 29-Oct-2027 | 28-Dec-2027 | 03.01.08.02.01 | WP Crew | C-3261
03.01.08.02.05 | 5 | Screed | Activity | Architectural | 6F | 7 | 06-Nov-2027 | 13-Nov-2027 | 03.01.08.02.04 | Screed Crew | C-3261
03.01.08.02.06 | 5 | Ceiling | Activity | Architectural | 6F | 10 | 08-Nov-2027 | 18-Nov-2027 | 03.01.08.03 | Ceiling Crew | C-3261
03.01.08.02.07 | 5 | Flooring | Activity | Architectural | 6F | 5 | 10-Nov-2027 | 15-Nov-2027 | 03.01.08.02.05 | Flooring / Tiling Crew | C-3261
03.01.08.02.08 | 5 | Wall Tiling | Activity | Architectural | 6F | 2 | 12-Nov-2027 | 14-Nov-2027 | 03.01.08.02.03 | Flooring / Tiling Crew | C-3261
03.01.08.02.09 | 5 | Stone / Marble | Activity | Architectural | 6F | 2 | 14-Nov-2027 | 16-Nov-2027 | 03.01.08.02.05 | Flooring / Tiling Crew | C-3261
03.01.08.02.10 | 5 | Door Frames | Activity | Architectural | 6F | 2 | 16-Nov-2027 | 18-Nov-2027 | 03.01.08.02.01 | Joinery / Glazing Crew | C-3261
03.01.08.02.11 | 5 | Doors | Activity | Architectural | 6F | 2 | 18-Nov-2027 | 20-Nov-2027 | 03.01.08.02.10,03.01.08.02.15 | Joinery / Glazing Crew | C-3261
03.01.08.02.12 | 5 | Windows | Activity | Architectural | 6F | 2 | 20-Nov-2027 | 22-Nov-2027 | 03.01.08.01.16 | Joinery / Glazing Crew | C-3261
03.01.08.02.13 | 5 | Glass | Activity | Architectural | 6F | 2 | 22-Nov-2027 | 24-Nov-2027 | 03.01.08.02.12 | Joinery / Glazing Crew | C-3261
03.01.08.02.14 | 5 | Painting Primer | Activity | Architectural | 6F | 2 | 24-Nov-2027 | 26-Nov-2027 | 03.01.08.02.03 | Paint Crew (6 men) | C-3261
03.01.08.02.15 | 5 | Internal Painting | Activity | Architectural | 6F | 2 | 26-Nov-2027 | 28-Nov-2027 | 03.01.08.02.14 | Paint Crew (6 men) | C-3261
03.01.08.02.16 | 5 | External Finishing | Activity | Architectural | 6F | 2 | 26-Nov-2027 | 28-Nov-2027 | 03.01.08.01.16 | External Finishes Crew | C-3261
03.01.08.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 6F | 2 | 26-Nov-2027 | 28-Nov-2027 | 03.01.08.02.15 | Architectural Crew | C-3261
03.01.08.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 6F | 2 | 24-Oct-2027 | 08-Nov-2027 | 03.01.08.01.16 | MEP First Fix Crews | C-3261
03.01.08.03.01 | 5 | Electrical Conduits | Activity | MEP | 6F | 2 | 24-Oct-2027 | 26-Oct-2027 | 03.01.08.03 | Electrical Crew (6 men) | C-3261
03.01.08.03.02 | 5 | Cable Trays | Activity | MEP | 6F | 2 | 26-Oct-2027 | 28-Oct-2027 | 03.01.08.03.01 | Electrical Crew (6 men) | C-3261
03.01.08.03.03 | 5 | Plumbing Pipes | Activity | MEP | 6F | 2 | 28-Oct-2027 | 30-Oct-2027 | 03.01.08.03.02 | Plumbing Crew (5 men) | C-3261
03.01.08.03.04 | 5 | Drainage Pipes | Activity | MEP | 6F | 2 | 30-Oct-2027 | 01-Nov-2027 | 03.01.08.03.03 | Plumbing Crew (5 men) | C-3261
03.01.08.03.05 | 5 | HVAC Ductwork | Activity | MEP | 6F | 2 | 01-Nov-2027 | 03-Nov-2027 | 03.01.08.03.04 | HVAC Crew (6 men) | C-3261
03.01.08.03.06 | 5 | HVAC Pipes | Activity | MEP | 6F | 2 | 03-Nov-2027 | 05-Nov-2027 | 03.01.08.03.05 | HVAC Crew (6 men) | C-3261
03.01.08.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 6F | 2 | 05-Nov-2027 | 07-Nov-2027 | 03.01.08.03.06 | Fire Fighting / FA Crew | C-3261
03.01.08.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 6F | 2 | 06-Nov-2027 | 08-Nov-2027 | 03.01.08.03.07 | Fire Fighting / FA Crew | C-3261
03.01.08.03.09 | 5 | ELV Conduits | Activity | MEP | 6F | 2 | 06-Nov-2027 | 08-Nov-2027 | 03.01.08.03.08 | ELV Crew | C-3261
03.01.08.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 6F | 2 | 13-Nov-2027 | 28-Nov-2027 | 03.01.08.02.06,03.01.08.03 | MEP Second Fix Crews | C-3261
03.01.08.04.01 | 5 | Cable Pulling | Activity | MEP | 6F | 2 | 13-Nov-2027 | 15-Nov-2027 | 03.01.08.04 | Electrical Crew | C-3261
03.01.08.04.02 | 5 | DB Installation | Activity | MEP | 6F | 2 | 15-Nov-2027 | 17-Nov-2027 | 03.01.08.04.01 | Electrical Crew | C-3261
03.01.08.04.03 | 5 | Lighting | Activity | MEP | 6F | 2 | 17-Nov-2027 | 19-Nov-2027 | 03.01.08.04.02 | Electrical Crew | C-3261
03.01.08.04.04 | 5 | Switches & Sockets | Activity | MEP | 6F | 2 | 19-Nov-2027 | 21-Nov-2027 | 03.01.08.04.03 | Electrical Crew | C-3261
03.01.08.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 6F | 2 | 21-Nov-2027 | 23-Nov-2027 | 03.01.08.04.04 | Plumbing Crew | C-3261
03.01.08.04.06 | 5 | HVAC Equipment | Activity | MEP | 6F | 2 | 23-Nov-2027 | 25-Nov-2027 | 03.01.08.04.05 | HVAC Crew | C-3261
03.01.08.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 6F | 2 | 25-Nov-2027 | 27-Nov-2027 | 03.01.08.04.06 | Fire Fighting / FA Crew | C-3261
03.01.08.04.08 | 5 | Sprinkler Heads | Activity | MEP | 6F | 2 | 26-Nov-2027 | 28-Nov-2027 | 03.01.08.04.07 | Fire Fighting / FA Crew | C-3261
03.01.08.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 6F | 2 | 26-Nov-2027 | 28-Nov-2027 | 03.01.08.04.08 | Fire Fighting / FA Crew | C-3261
03.01.08.04.10 | 5 | ELV Devices | Activity | MEP | 6F | 2 | 26-Nov-2027 | 28-Nov-2027 | 03.01.08.04.09 | ELV Crew | C-3261
03.01.08.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 6F | 1 | 23-Nov-2027 | 01-Dec-2027 | 03.01.08.02.17,03.01.08.04 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.01 | 5 | Structural Inspection | Activity | QA/QC | 6F | 1 | 23-Nov-2027 | 24-Nov-2027 | 03.01.08.01.16 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 6F | 1 | 25-Nov-2027 | 26-Nov-2027 | 03.01.08.02.17 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.03 | 5 | MEP Inspection | Activity | QA/QC | 6F | 1 | 27-Nov-2027 | 28-Nov-2027 | 03.01.08.04 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.04 | 5 | Testing | Activity | QA/QC | 6F | 2 | 29-Nov-2027 | 01-Dec-2027 | 03.01.08.05.03 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.05 | 5 | Snagging | Activity | QA/QC | 6F | 2 | 29-Nov-2027 | 01-Dec-2027 | 03.01.08.05.04 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.06 | 5 | Snag Rectification | Activity | QA/QC | 6F | 2 | 29-Nov-2027 | 01-Dec-2027 | 03.01.08.05.05 | QA/QC, Inspectors, All Trades | C-3261
03.01.08.05.07 | 5 | Floor Completion | Activity | QA/QC | 6F | 2 | 29-Nov-2027 | 01-Dec-2027 | 03.01.08.05.06 | QA/QC, Inspectors, All Trades | C-3261
03.01.09 | 3 | 03.01.09 7F | Work Package | Construction | 7F | 97 | 11-Nov-2027 | 15-Feb-2028 | 03.01.08 | Site Team | C-3271
03.01.09.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | 7F | 2 | 11-Nov-2027 | 03-Dec-2027 | 03.01.09 | Structural Crew | C-3271
03.01.09.01.01 | 5 | Setting Out | Activity | Structural | 7F | 7 | 11-Nov-2027 | 18-Nov-2027 | 03.01.09.01 | Surveyor | C-3271
03.01.09.01.02 | 5 | Column Reinforcement | Activity | Structural | 7F | 10 | 13-Nov-2027 | 23-Nov-2027 | 03.01.09.01.01 | Rebar Crew (10 men) | C-3271
03.01.09.01.03 | 5 | Column Formwork | Activity | Structural | 7F | 12 | 15-Nov-2027 | 27-Nov-2027 | 03.01.09.01.02 | Formwork Crew (12 men) | C-3271
03.01.09.01.04 | 5 | Column Concrete | Activity | Structural | 7F | 10 | 17-Nov-2027 | 27-Nov-2027 | 03.01.09.01.03 | Concrete Crew, Pump Operator | C-3271
03.01.09.01.05 | 5 | Shear Wall Reinforcement | Activity | Structural | 7F | 10 | 19-Nov-2027 | 29-Nov-2027 | 03.01.09.01.01 | Rebar Crew (10 men) | C-3271
03.01.09.01.06 | 5 | Shear Wall Formwork | Activity | Structural | 7F | 20 | 13-Nov-2027 | 03-Dec-2027 | 03.01.09.01.05 | Formwork Crew (12 men) | C-3271
03.01.09.01.07 | 5 | Shear Wall Concrete | Activity | Structural | 7F | 1 | 23-Nov-2027 | 24-Nov-2027 | 03.01.09.01.06 | Concrete Crew, Pump Operator | C-3271
03.01.09.01.08 | 5 | Beam Formwork | Activity | Structural | 7F | 3 | 25-Nov-2027 | 28-Nov-2027 | 03.01.09.01.04,03.01.09.01.07 | Formwork Crew (12 men) | C-3271
03.01.09.01.09 | 5 | Slab Formwork | Activity | Structural | 7F | 3 | 27-Nov-2027 | 30-Nov-2027 | 03.01.09.01.04,03.01.09.01.07 | Formwork Crew (12 men) | C-3271
03.01.09.01.10 | 5 | Beam Reinforcement | Activity | Structural | 7F | 2 | 29-Nov-2027 | 01-Dec-2027 | 03.01.09.01.08 | Rebar Crew (10 men) | C-3271
03.01.09.01.11 | 5 | Slab Reinforcement | Activity | Structural | 7F | 2 | 01-Dec-2027 | 03-Dec-2027 | 03.01.09.01.09 | Rebar Crew (10 men) | C-3271
03.01.09.01.12 | 5 | MEP Embedded Items | Activity | Structural | 7F | 1 | 02-Dec-2027 | 03-Dec-2027 | 03.01.09.01.10,03.01.09.01.11 | MEP + Structural | C-3271
03.01.09.01.13 | 5 | Structural Inspection | Activity | Structural | 7F | 1 | 02-Dec-2027 | 03-Dec-2027 | 03.01.09.01.12 | QA/QC Inspector, Structural Engineer | C-3271
03.01.09.01.14 | 5 | Concrete Pour | Activity | Structural | 7F | 1 | 02-Dec-2027 | 03-Dec-2027 | 03.01.09.01.13 | Concrete Crew, Pump Operator | C-3271
03.01.09.01.15 | 5 | Concrete Curing | Activity | Structural | 7F | 7 | 26-Nov-2027 | 03-Dec-2027 | 03.01.09.01.14 | Concrete Crew, Pump Operator | C-3271
03.01.09.01.16 | 5 | Formwork Removal | Activity | Structural | 7F | 2 | 01-Dec-2027 | 03-Dec-2027 | 03.01.09.01.15 | Formwork Crew (12 men) | C-3271
03.01.09.02 | 4 | 02 ARCHITECTURAL WORKS | Work Package | Architectural | 7F | 2 | 26-Nov-2027 | 26-Dec-2027 | 03.01.09.01.16 | Architectural Crew | C-3271
03.01.09.02.01 | 5 | Blockwork | Activity | Architectural | 7F | 10 | 26-Nov-2027 | 06-Dec-2027 | 03.01.09.02 | Masonry / Partition Crew | C-3271
03.01.09.02.02 | 5 | Internal Partition | Activity | Architectural | 7F | 60 | 26-Nov-2027 | 25-Jan-2028 | 03.01.09.02.01 | Masonry / Partition Crew | C-3271
03.01.09.02.03 | 5 | Plastering | Activity | Architectural | 7F | 60 | 26-Nov-2027 | 25-Jan-2028 | 03.01.09.02.02 | Plaster Crew (8 men) | C-3271
03.01.09.02.04 | 5 | Waterproofing | Activity | Architectural | 7F | 60 | 26-Nov-2027 | 25-Jan-2028 | 03.01.09.02.01 | WP Crew | C-3271
03.01.09.02.05 | 5 | Screed | Activity | Architectural | 7F | 7 | 04-Dec-2027 | 11-Dec-2027 | 03.01.09.02.04 | Screed Crew | C-3271
03.01.09.02.06 | 5 | Ceiling | Activity | Architectural | 7F | 10 | 06-Dec-2027 | 16-Dec-2027 | 03.01.09.03 | Ceiling Crew | C-3271
03.01.09.02.07 | 5 | Flooring | Activity | Architectural | 7F | 5 | 08-Dec-2027 | 13-Dec-2027 | 03.01.09.02.05 | Flooring / Tiling Crew | C-3271
03.01.09.02.08 | 5 | Wall Tiling | Activity | Architectural | 7F | 2 | 10-Dec-2027 | 12-Dec-2027 | 03.01.09.02.03 | Flooring / Tiling Crew | C-3271
03.01.09.02.09 | 5 | Stone / Marble | Activity | Architectural | 7F | 2 | 12-Dec-2027 | 14-Dec-2027 | 03.01.09.02.05 | Flooring / Tiling Crew | C-3271
03.01.09.02.10 | 5 | Door Frames | Activity | Architectural | 7F | 2 | 14-Dec-2027 | 16-Dec-2027 | 03.01.09.02.01 | Joinery / Glazing Crew | C-3271
03.01.09.02.11 | 5 | Doors | Activity | Architectural | 7F | 2 | 16-Dec-2027 | 18-Dec-2027 | 03.01.09.02.10,03.01.09.02.15 | Joinery / Glazing Crew | C-3271
03.01.09.02.12 | 5 | Windows | Activity | Architectural | 7F | 2 | 18-Dec-2027 | 20-Dec-2027 | 03.01.09.01.16 | Joinery / Glazing Crew | C-3271
03.01.09.02.13 | 5 | Glass | Activity | Architectural | 7F | 2 | 20-Dec-2027 | 22-Dec-2027 | 03.01.09.02.12 | Joinery / Glazing Crew | C-3271
03.01.09.02.14 | 5 | Painting Primer | Activity | Architectural | 7F | 2 | 22-Dec-2027 | 24-Dec-2027 | 03.01.09.02.03 | Paint Crew (6 men) | C-3271
03.01.09.02.15 | 5 | Internal Painting | Activity | Architectural | 7F | 2 | 24-Dec-2027 | 26-Dec-2027 | 03.01.09.02.14 | Paint Crew (6 men) | C-3271
03.01.09.02.16 | 5 | External Finishing | Activity | Architectural | 7F | 2 | 24-Dec-2027 | 26-Dec-2027 | 03.01.09.01.16 | External Finishes Crew | C-3271
03.01.09.02.17 | 5 | Final Architectural Finishes | Activity | Architectural | 7F | 2 | 24-Dec-2027 | 26-Dec-2027 | 03.01.09.02.15 | Architectural Crew | C-3271
03.01.09.03 | 4 | 03 MEP FIRST FIX | Work Package | MEP | 7F | 2 | 21-Nov-2027 | 06-Dec-2027 | 03.01.09.01.16 | MEP First Fix Crews | C-3271
03.01.09.03.01 | 5 | Electrical Conduits | Activity | MEP | 7F | 2 | 21-Nov-2027 | 23-Nov-2027 | 03.01.09.03 | Electrical Crew (6 men) | C-3271
03.01.09.03.02 | 5 | Cable Trays | Activity | MEP | 7F | 2 | 23-Nov-2027 | 25-Nov-2027 | 03.01.09.03.01 | Electrical Crew (6 men) | C-3271
03.01.09.03.03 | 5 | Plumbing Pipes | Activity | MEP | 7F | 2 | 25-Nov-2027 | 27-Nov-2027 | 03.01.09.03.02 | Plumbing Crew (5 men) | C-3271
03.01.09.03.04 | 5 | Drainage Pipes | Activity | MEP | 7F | 2 | 27-Nov-2027 | 29-Nov-2027 | 03.01.09.03.03 | Plumbing Crew (5 men) | C-3271
03.01.09.03.05 | 5 | HVAC Ductwork | Activity | MEP | 7F | 2 | 29-Nov-2027 | 01-Dec-2027 | 03.01.09.03.04 | HVAC Crew (6 men) | C-3271
03.01.09.03.06 | 5 | HVAC Pipes | Activity | MEP | 7F | 2 | 01-Dec-2027 | 03-Dec-2027 | 03.01.09.03.05 | HVAC Crew (6 men) | C-3271
03.01.09.03.07 | 5 | Fire Fighting Pipes | Activity | MEP | 7F | 2 | 03-Dec-2027 | 05-Dec-2027 | 03.01.09.03.06 | Fire Fighting / FA Crew | C-3271
03.01.09.03.08 | 5 | Fire Alarm Conduits | Activity | MEP | 7F | 2 | 04-Dec-2027 | 06-Dec-2027 | 03.01.09.03.07 | Fire Fighting / FA Crew | C-3271
03.01.09.03.09 | 5 | ELV Conduits | Activity | MEP | 7F | 2 | 04-Dec-2027 | 06-Dec-2027 | 03.01.09.03.08 | ELV Crew | C-3271
03.01.09.04 | 4 | 04 MEP SECOND FIX | Work Package | MEP | 7F | 2 | 11-Dec-2027 | 26-Dec-2027 | 03.01.09.02.06,03.01.09.03 | MEP Second Fix Crews | C-3271
03.01.09.04.01 | 5 | Cable Pulling | Activity | MEP | 7F | 2 | 11-Dec-2027 | 13-Dec-2027 | 03.01.09.04 | Electrical Crew | C-3271
03.01.09.04.02 | 5 | DB Installation | Activity | MEP | 7F | 2 | 13-Dec-2027 | 15-Dec-2027 | 03.01.09.04.01 | Electrical Crew | C-3271
03.01.09.04.03 | 5 | Lighting | Activity | MEP | 7F | 2 | 15-Dec-2027 | 17-Dec-2027 | 03.01.09.04.02 | Electrical Crew | C-3271
03.01.09.04.04 | 5 | Switches & Sockets | Activity | MEP | 7F | 2 | 17-Dec-2027 | 19-Dec-2027 | 03.01.09.04.03 | Electrical Crew | C-3271
03.01.09.04.05 | 5 | Plumbing Fixtures | Activity | MEP | 7F | 2 | 19-Dec-2027 | 21-Dec-2027 | 03.01.09.04.04 | Plumbing Crew | C-3271
03.01.09.04.06 | 5 | HVAC Equipment | Activity | MEP | 7F | 2 | 21-Dec-2027 | 23-Dec-2027 | 03.01.09.04.05 | HVAC Crew | C-3271
03.01.09.04.07 | 5 | Fire Alarm Devices | Activity | MEP | 7F | 2 | 23-Dec-2027 | 25-Dec-2027 | 03.01.09.04.06 | Fire Fighting / FA Crew | C-3271
03.01.09.04.08 | 5 | Sprinkler Heads | Activity | MEP | 7F | 2 | 24-Dec-2027 | 26-Dec-2027 | 03.01.09.04.07 | Fire Fighting / FA Crew | C-3271
03.01.09.04.09 | 5 | Fire Fighting Equipment | Activity | MEP | 7F | 2 | 24-Dec-2027 | 26-Dec-2027 | 03.01.09.04.08 | Fire Fighting / FA Crew | C-3271
03.01.09.04.10 | 5 | ELV Devices | Activity | MEP | 7F | 2 | 24-Dec-2027 | 26-Dec-2027 | 03.01.09.04.09 | ELV Crew | C-3271
03.01.09.05 | 4 | 05 TESTING & INSPECTION | Work Package | QA/QC | 7F | 1 | 21-Dec-2027 | 29-Dec-2027 | 03.01.09.02.17,03.01.09.04 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.01 | 5 | Structural Inspection | Activity | QA/QC | 7F | 1 | 21-Dec-2027 | 22-Dec-2027 | 03.01.09.01.16 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.02 | 5 | Architectural Inspection | Activity | QA/QC | 7F | 1 | 23-Dec-2027 | 24-Dec-2027 | 03.01.09.02.17 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.03 | 5 | MEP Inspection | Activity | QA/QC | 7F | 1 | 25-Dec-2027 | 26-Dec-2027 | 03.01.09.04 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.04 | 5 | Testing | Activity | QA/QC | 7F | 2 | 27-Dec-2027 | 29-Dec-2027 | 03.01.09.05.03 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.05 | 5 | Snagging | Activity | QA/QC | 7F | 2 | 27-Dec-2027 | 29-Dec-2027 | 03.01.09.05.04 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.06 | 5 | Snag Rectification | Activity | QA/QC | 7F | 2 | 27-Dec-2027 | 29-Dec-2027 | 03.01.09.05.05 | QA/QC, Inspectors, All Trades | C-3271
03.01.09.05.07 | 5 | Floor Completion | Activity | QA/QC | 7F | 2 | 27-Dec-2027 | 29-Dec-2027 | 03.01.09.05.06 | QA/QC, Inspectors, All Trades | C-3271
03.01.10 | 3 | 03.01.10 RF – ROOF | Work Package | Construction | RF | 77 | 15-Jan-2028 | 31-Mar-2028 | 03.01.09 | Roof Crew | C-3310
03.01.10.01 | 4 | 01 STRUCTURAL WORKS | Work Package | Structural | RF | 15 | 15-Jan-2028 | 20-Feb-2028 | 03.01.10 | Rebar + Formwork + Concrete Crew | C-3310
03.01.10.01.01 | 5 | Roof Columns | Activity | Structural | RF | 7 | 15-Jan-2028 | 22-Jan-2028 | 03.01.10.01 | Rebar + Formwork + Concrete Crew | C-3310
03.01.10.01.02 | 5 | Roof Beams | Activity | Structural | RF | 10 | 18-Jan-2028 | 28-Jan-2028 | 03.01.10.01.01 | Rebar + Formwork + Concrete Crew | C-3310
03.01.10.01.03 | 5 | Roof Slab | Activity | Structural | RF | 12 | 21-Jan-2028 | 02-Feb-2028 | 03.01.10.01.02 | Rebar + Formwork + Concrete Crew | C-3310
03.01.10.01.04 | 5 | Parapet | Activity | Structural | RF | 10 | 24-Jan-2028 | 03-Feb-2028 | 03.01.10.01.03 | Rebar + Formwork + Concrete Crew | C-3310
03.01.10.01.05 | 5 | Roof Structure | Activity | Structural | RF | 10 | 27-Jan-2028 | 06-Feb-2028 | 03.01.10.01.04 | Roof Crew | C-3310
03.01.10.02 | 4 | 02 WATERPROOFING | Work Package | Architectural | RF | 15 | 10-Feb-2028 | 05-Mar-2028 | 03.01.10.01 | WP / Insulation Crew | C-3310
03.01.10.02.01 | 5 | Roof Waterproofing | Activity | Architectural | RF | 10 | 10-Feb-2028 | 20-Feb-2028 | 03.01.10.02 | WP / Insulation Crew | C-3310
03.01.10.02.02 | 5 | Insulation | Activity | Architectural | RF | 60 | 13-Feb-2028 | 05-Mar-2028 | 03.01.10.02.01 | WP / Insulation Crew | C-3310
03.01.10.02.03 | 5 | Protection | Activity | Architectural | RF | 60 | 16-Feb-2028 | 05-Mar-2028 | 03.01.10.02.02 | Roof Crew | C-3310
03.01.10.03 | 4 | 03 ARCHITECTURAL | Work Package | Architectural | RF | 15 | 20-Feb-2028 | 20-Mar-2028 | 03.01.10.02 | Roof Crew | C-3310
03.01.10.03.01 | 5 | Roof Finishes | Activity | Architectural | RF | 5 | 20-Feb-2028 | 25-Feb-2028 | 03.01.10.03 | Architectural Crew | C-3310
03.01.10.03.02 | 5 | Parapet Finishes | Activity | Architectural | RF | 8 | 23-Feb-2028 | 02-Mar-2028 | 03.01.10.03.01 | Rebar + Formwork + Concrete Crew | C-3310
03.01.10.03.03 | 5 | Roof Access | Activity | Architectural | RF | 5 | 26-Feb-2028 | 02-Mar-2028 | 03.01.10.03.02 | Architectural Crew | C-3310
03.01.10.04 | 4 | 04 MEP | Work Package | MEP | RF | 15 | 01-Feb-2028 | 25-Mar-2028 | 03.01.10.01 | Roof Crew | C-3310
03.01.10.04.01 | 5 | Roof Drainage | Activity | MEP | RF | 10 | 01-Feb-2028 | 11-Feb-2028 | 03.01.10.04 | MEP Roof Crew | C-3310
03.01.10.04.02 | 5 | HVAC Equipment | Activity | MEP | RF | 10 | 04-Feb-2028 | 14-Feb-2028 | 03.01.10.04.01 | MEP Roof Crew | C-3310
03.01.10.04.03 | 5 | Water Tank | Activity | MEP | RF | 10 | 07-Feb-2028 | 17-Feb-2028 | 03.01.10.04.02 | MEP Roof Crew | C-3310
03.01.10.04.04 | 5 | Pumps | Activity | MEP | RF | 10 | 10-Feb-2028 | 20-Feb-2028 | 03.01.10.04.03 | MEP Roof Crew | C-3310
03.01.10.04.05 | 5 | Lightning Protection | Activity | MEP | RF | 7 | 13-Feb-2028 | 20-Feb-2028 | 03.01.10.04.04 | MEP Roof Crew | C-3310
03.01.10.04.06 | 5 | Other Roof Equipment | Activity | MEP | RF | 5 | 16-Feb-2028 | 21-Feb-2028 | 03.01.10.04.05 | Roof Crew | C-3310
03.02 | 2 | 03.02 BX – EXTERNAL WORKS | Work Package | Construction | External | 488 | 01-Apr-2027 | 31-Jul-2028 | 03.01 | Construction Manager, Site Team | C-3400
03.02.01 | 3 | 01 SITE PREPARATION | Work Package | Civil | External | 45 | 01-Apr-2027 | 15-May-2027 | 03.02 | Site Crew, Surveyor | C-3410
03.02.01.01 | 4 | Site Clearance | Activity | Civil | External | 7 | 01-Apr-2027 | 08-Apr-2027 | 03.02.01 | Site Crew, Surveyor | C-3410
03.02.01.02 | 4 | Temporary Facilities | Activity | Civil | External | 10 | 05-Apr-2027 | 15-Apr-2027 | 03.02.01.01 | Site Crew, Surveyor | C-3410
03.02.01.03 | 4 | Temporary Roads | Activity | Civil | External | 12 | 09-Apr-2027 | 21-Apr-2027 | 03.02.01.02 | Site Crew, Surveyor | C-3410
03.02.01.04 | 4 | Temporary Drainage | Activity | Civil | External | 10 | 13-Apr-2027 | 23-Apr-2027 | 03.02.01.03 | Site Crew, Surveyor | C-3410
03.02.01.05 | 4 | Site Grading | Activity | Civil | External | 10 | 17-Apr-2027 | 27-Apr-2027 | 03.02.01.04 | Site Crew, Surveyor | C-3410
03.02.02 | 3 | 02 EXTERNAL CIVIL WORKS | Work Package | Civil | External | 107 | 01-May-2027 | 15-Aug-2027 | 03.02.01 | Civil Crew, Excavator | C-3420
03.02.02.01 | 4 | Excavation | Activity | Civil | External | 10 | 01-May-2027 | 11-May-2027 | 03.02.02 | Civil Crew, Excavator | C-3420
03.02.02.02 | 4 | Filling | Activity | Civil | External | 60 | 05-May-2027 | 04-Jul-2027 | 03.02.02.01 | Civil Crew, Excavator | C-3420
03.02.02.03 | 4 | Backfilling | Activity | Civil | External | 60 | 09-May-2027 | 08-Jul-2027 | 03.02.02.02 | Civil Crew, Excavator | C-3420
03.02.02.04 | 4 | Compaction | Activity | Civil | External | 60 | 13-May-2027 | 12-Jul-2027 | 03.02.02.03 | Civil Crew, Excavator | C-3420
03.02.02.05 | 4 | Concrete Works | Activity | Civil | External | 60 | 17-May-2027 | 16-Jul-2027 | 03.02.02.04 | Civil Crew, Excavator | C-3420
03.02.02.06 | 4 | Kerbs | Activity | Civil | External | 60 | 21-May-2027 | 20-Jul-2027 | 03.02.02.05 | Civil Crew, Excavator | C-3420
03.02.02.07 | 4 | External Structures | Activity | Civil | External | 60 | 25-May-2027 | 24-Jul-2027 | 03.02.02.06 | Civil Crew, Excavator | C-3420
03.02.03 | 3 | 03 EXTERNAL DRAINAGE | Work Package | Civil | External | 107 | 01-Jun-2027 | 15-Sep-2027 | 03.02.02 | Drainage Crew | C-3430
03.02.03.01 | 4 | Stormwater Drainage | Activity | Civil | External | 60 | 01-Jun-2027 | 31-Jul-2027 | 03.02.03 | Drainage Crew | C-3430
03.02.03.02 | 4 | Sewer Drainage | Activity | Civil | External | 60 | 05-Jun-2027 | 04-Aug-2027 | 03.02.03.01 | Drainage Crew | C-3430
03.02.03.03 | 4 | Manholes | Activity | Civil | External | 60 | 09-Jun-2027 | 08-Aug-2027 | 03.02.03.02 | Drainage Crew | C-3430
03.02.03.04 | 4 | Catch Pits | Activity | Civil | External | 60 | 13-Jun-2027 | 12-Aug-2027 | 03.02.03.03 | Drainage Crew | C-3430
03.02.03.05 | 4 | Inspection Chambers | Activity | Civil | External | 60 | 17-Jun-2027 | 16-Aug-2027 | 03.02.03.04 | Drainage Crew | C-3430
03.02.03.06 | 4 | Drainage Testing | Activity | Civil | External | 60 | 21-Jun-2027 | 20-Aug-2027 | 03.02.03.05 | Drainage Crew | C-3430
03.02.04 | 3 | 04 EXTERNAL UTILITIES | Work Package | MEP | External | 153 | 01-Jul-2027 | 30-Nov-2027 | 03.02.03 | Utilities Crew (MEP) | C-3440
03.02.04.01 | 4 | Water Supply | Activity | MEP | External | 60 | 01-Jul-2027 | 30-Aug-2027 | 03.02.04 | Utilities Crew (MEP) | C-3440
03.02.04.02 | 4 | Electrical | Activity | MEP | External | 60 | 05-Jul-2027 | 03-Sep-2027 | 03.02.04.01 | Utilities Crew (MEP) | C-3440
03.02.04.03 | 4 | External Lighting | Activity | MEP | External | 60 | 09-Jul-2027 | 07-Sep-2027 | 03.02.04.02 | Utilities Crew (MEP) | C-3440
03.02.04.04 | 4 | Fire Water | Activity | MEP | External | 60 | 13-Jul-2027 | 11-Sep-2027 | 03.02.04.03 | Utilities Crew (MEP) | C-3440
03.02.04.05 | 4 | Telecom | Activity | MEP | External | 60 | 17-Jul-2027 | 15-Sep-2027 | 03.02.04.04 | Utilities Crew (MEP) | C-3440
03.02.04.06 | 4 | ELV | Activity | MEP | External | 60 | 21-Jul-2027 | 19-Sep-2027 | 03.02.04.05 | Utilities Crew (MEP) | C-3440
03.02.05 | 3 | 05 ROAD & PARKING | Work Package | Civil | External | 153 | 01-Sep-2027 | 31-Jan-2028 | 03.02.04 | Road Crew, Paver | C-3450
03.02.05.01 | 4 | Subgrade | Activity | Civil | External | 7 | 01-Sep-2027 | 08-Sep-2027 | 03.02.05 | Road Crew, Paver | C-3450
03.02.05.02 | 4 | Subbase | Activity | Civil | External | 7 | 05-Sep-2027 | 12-Sep-2027 | 03.02.05.01 | Road Crew, Paver | C-3450
03.02.05.03 | 4 | Base Course | Activity | Civil | External | 7 | 09-Sep-2027 | 16-Sep-2027 | 03.02.05.02 | Road Crew, Paver | C-3450
03.02.05.04 | 4 | Kerbs | Activity | Civil | External | 7 | 13-Sep-2027 | 20-Sep-2027 | 03.02.05.03 | Road Crew, Paver | C-3450
03.02.05.05 | 4 | Pavement | Activity | Civil | External | 7 | 17-Sep-2027 | 24-Sep-2027 | 03.02.05.04 | Road Crew, Paver | C-3450
03.02.05.06 | 4 | Asphalt / Concrete | Activity | Civil | External | 7 | 21-Sep-2027 | 28-Sep-2027 | 03.02.05.05 | Road Crew, Paver | C-3450
03.02.05.07 | 4 | Parking | Activity | Civil | External | 7 | 25-Sep-2027 | 02-Oct-2027 | 03.02.05.06 | Road Crew, Paver | C-3450
03.02.05.08 | 4 | Road Marking | Activity | Civil | External | 7 | 29-Sep-2027 | 06-Oct-2027 | 03.02.05.07 | Road Crew, Paver | C-3450
03.02.05.09 | 4 | Traffic Signage | Activity | Civil | External | 7 | 03-Oct-2027 | 10-Oct-2027 | 03.02.05.08 | Road Crew, Paver | C-3450
03.02.06 | 3 | 06 LANDSCAPING | Work Package | Landscape | External | 105 | 01-Feb-2028 | 15-May-2028 | 03.02.05 | Landscape Crew | C-3460
03.02.06.01 | 4 | Topsoil | Activity | Landscape | External | 10 | 01-Feb-2028 | 11-Feb-2028 | 03.02.06 | Landscape Crew | C-3460
03.02.06.02 | 4 | Softscape | Activity | Landscape | External | 10 | 05-Feb-2028 | 15-Feb-2028 | 03.02.06.01 | Landscape Crew | C-3460
03.02.06.03 | 4 | Trees | Activity | Landscape | External | 10 | 09-Feb-2028 | 19-Feb-2028 | 03.02.06.02 | Landscape Crew | C-3460
03.02.06.04 | 4 | Shrubs | Activity | Landscape | External | 10 | 13-Feb-2028 | 23-Feb-2028 | 03.02.06.03 | Landscape Crew | C-3460
03.02.06.05 | 4 | Grass | Activity | Landscape | External | 10 | 17-Feb-2028 | 27-Feb-2028 | 03.02.06.04 | Landscape Crew | C-3460
03.02.06.06 | 4 | Hardscape | Activity | Landscape | External | 10 | 21-Feb-2028 | 02-Mar-2028 | 03.02.06.05 | Landscape Crew | C-3460
03.02.06.07 | 4 | Landscape Irrigation | Activity | Landscape | External | 10 | 25-Feb-2028 | 06-Mar-2028 | 03.02.06.06 | Landscape Crew | C-3460
03.02.07 | 3 | 07 BOUNDARY & GATE | Work Package | Architectural | External | 151 | 01-Oct-2027 | 28-Feb-2028 | 03.02.06 | Boundary / Security Crew | C-3470
03.02.07.01 | 4 | Boundary Wall | Activity | Architectural | External | 5 | 01-Oct-2027 | 06-Oct-2027 | 03.02.07 | Boundary / Security Crew | C-3470
03.02.07.02 | 4 | Gate | Activity | Architectural | External | 5 | 05-Oct-2027 | 10-Oct-2027 | 03.02.07.01 | Boundary / Security Crew | C-3470
03.02.07.03 | 4 | Guard House | Activity | Architectural | External | 5 | 09-Oct-2027 | 14-Oct-2027 | 03.02.07.02 | Boundary / Security Crew | C-3470
03.02.07.04 | 4 | Security System | Activity | Architectural | External | 5 | 13-Oct-2027 | 18-Oct-2027 | 03.02.07.03 | Boundary / Security Crew | C-3470
03.02.08 | 3 | 08 EXTERNAL FINISHES | Work Package | Architectural | External | 106 | 01-Apr-2028 | 15-Jul-2028 | 03.02.07 | External Finishes Crew, Cleaners | C-3480
03.02.08.01 | 4 | External Painting | Activity | Architectural | External | 10 | 01-Apr-2028 | 11-Apr-2028 | 03.02.08 | External Finishes Crew, Cleaners | C-3480
03.02.08.02 | 4 | Signage | Activity | Architectural | External | 10 | 05-Apr-2028 | 15-Apr-2028 | 03.02.08.01 | External Finishes Crew, Cleaners | C-3480
03.02.08.03 | 4 | External Lighting | Activity | Architectural | External | 8 | 09-Apr-2028 | 17-Apr-2028 | 03.02.08.02 | External Finishes Crew, Cleaners | C-3480
03.02.08.04 | 4 | Final Cleaning | Activity | Architectural | External | 10 | 13-Apr-2028 | 23-Apr-2028 | 03.02.08.03 | External Finishes Crew, Cleaners | C-3480
03.02.08.05 | 4 | External Snagging | Activity | Architectural | External | 10 | 17-Apr-2028 | 27-Apr-2028 | 03.02.08.04 | External Finishes Crew, Cleaners | C-3480
04 | 1 | 04 COMMISSIONING & HANDOVER | Phase | Commissioning |  | 92 | 01-Jul-2028 | 30-Sep-2028 | 03.01.10,03.02.08 | PM Team | H-4000 | Project completion and handover
04.01 | 2 | 04.01 TESTING & COMMISSIONING | Work Package | Commissioning |  | 46 | 01-Jul-2028 | 15-Aug-2028 | 04 | Commissioning Manager, QA/QC | H-4100
04.01.01 | 3 | Electrical Testing | Activity | Commissioning |  | 8 | 01-Jul-2028 | 08-Jul-2028 | 03.01.10,03.02 | Electrical Commissioning Engineer | H-4100
04.01.02 | 3 | HVAC Testing | Activity | Commissioning |  | 11 | 06-Jul-2028 | 16-Jul-2028 | 03.01.10,03.02 | HVAC Commissioning Engineer | H-4100
04.01.03 | 3 | Plumbing Testing | Activity | Commissioning |  | 13 | 11-Jul-2028 | 23-Jul-2028 | 03.01.10,03.02 | Plumbing Commissioning | H-4100
04.01.04 | 3 | Drainage Testing | Activity | Commissioning |  | 11 | 16-Jul-2028 | 26-Jul-2028 | 03.01.10,03.02 | Plumbing Commissioning | H-4100
04.01.05 | 3 | Fire Alarm Testing | Activity | Commissioning |  | 11 | 21-Jul-2028 | 31-Jul-2028 | 03.01.10,03.02 | Fire System Specialist | H-4100
04.01.06 | 3 | Fire Fighting Testing | Activity | Commissioning |  | 16 | 26-Jul-2028 | 10-Aug-2028 | 03.01.10,03.02 | Fire System Specialist | H-4100
04.01.07 | 3 | ELV Testing | Activity | Commissioning |  | 8 | 31-Jul-2028 | 07-Aug-2028 | 03.01.10,03.02 | ELV Commissioning | H-4100
04.01.08 | 3 | Integrated System Testing | Activity | Commissioning |  | 8 | 05-Aug-2028 | 12-Aug-2028 | 03.01.10,03.02 | All Systems + Commissioning Manager | H-4100
04.02 | 2 | 04.02 SNAGGING | Work Package | QA/QC |  | 48 | 15-Jul-2028 | 31-Aug-2028 | 04.01 | Commissioning Manager, QA/QC | H-4200
04.02.01 | 3 | Internal Snagging | Activity | QA/QC |  | 11 | 15-Jul-2028 | 25-Jul-2028 | 04.01 | QA/QC, Snagging Team, All Trades | H-4200
04.02.02 | 3 | External Snagging | Activity | QA/QC |  | 43 | 20-Jul-2028 | 31-Aug-2028 | 04.01 | QA/QC, Snagging Team, All Trades | H-4200
04.02.03 | 3 | MEP Snagging | Activity | QA/QC |  | 38 | 25-Jul-2028 | 31-Aug-2028 | 04.01 | QA/QC, Snagging Team, All Trades | H-4200
04.02.04 | 3 | Architectural Snagging | Activity | QA/QC |  | 33 | 30-Jul-2028 | 31-Aug-2028 | 04.01 | QA/QC, Snagging Team, All Trades | H-4200
04.02.05 | 3 | Snag Rectification | Activity | QA/QC |  | 8 | 04-Aug-2028 | 11-Aug-2028 | 04.01 | QA/QC, Snagging Team, All Trades | H-4200
04.03 | 2 | 04.03 HANDOVER DOCUMENTATION | Work Package | Documentation |  | 77 | 01-Jul-2028 | 15-Sep-2028 | 04.02 | Commissioning Manager, QA/QC | H-4300
04.03.01 | 3 | As-Built Drawings | Activity | Documentation |  | 11 | 01-Jul-2028 | 11-Jul-2028 | 04.01 | Document Controller, Engineers, Training Team | H-4300
04.03.02 | 3 | O&M Manuals | Activity | Documentation |  | 61 | 06-Jul-2028 | 04-Sep-2028 | 04.01 | External Works Team | H-4300
04.03.03 | 3 | Testing Certificates | Activity | Documentation |  | 11 | 11-Jul-2028 | 21-Jul-2028 | 04.01 | Document Controller, Engineers, Training Team | H-4300
04.03.04 | 3 | Warranty Certificates | Activity | Documentation |  | 11 | 16-Jul-2028 | 26-Jul-2028 | 04.01 | Document Controller, Engineers, Training Team | H-4300
04.03.05 | 3 | Material Certificates | Activity | Documentation |  | 11 | 21-Jul-2028 | 31-Jul-2028 | 04.01 | Document Controller, Engineers, Training Team | H-4300
04.03.06 | 3 | Training | Activity | Documentation |  | 11 | 26-Jul-2028 | 05-Aug-2028 | 04.01 | Document Controller, Engineers, Training Team | H-4300
04.03.07 | 3 | Handover Dossier | Activity | Documentation |  | 11 | 31-Jul-2028 | 10-Aug-2028 | 04.01 | Document Controller, Engineers, Training Team | H-4300
04.04 | 2 | 04.04 HANDOVER | Work Package | Handover |  | 47 | 15-Aug-2028 | 30-Sep-2028 | 04.03 | Commissioning Manager, QA/QC | H-4400
04.04.01 | 3 | Client Inspection | Activity | Handover |  | 8 | 15-Aug-2028 | 22-Aug-2028 | 04.02.05,04.03 | Commissioning Team | H-4400
04.04.02 | 3 | Final Inspection | Activity | Handover |  | 8 | 20-Aug-2028 | 27-Aug-2028 | 04.04.01 | QA/QC, Snagging Team, All Trades | H-4400
04.04.03 | 3 | Taking Over | Activity | Handover |  | 11 | 25-Aug-2028 | 04-Sep-2028 | 04.04.02 | Document Controller, Engineers, Training Team | H-4400
04.04.04 | 3 | Project Completion | Activity | Handover |  | 2 | 30-Aug-2028 | 31-Aug-2028 | 04.04.03 | PM, Client, Handover Team | H-4400

## Baseline Schedule Summary
7-FLOOR BUILDING – 24-MONTH BASELINE SCHEDULE SUMMARY
Project Start: 01-Oct-2026 ¦ Project Finish: 30-Sep-2028 ¦ Duration: 24 Months (730 calendar days)
Phase / Package | Baseline Start | Baseline Finish | Duration (Days) | Key Notes | % of Project
PROJECT – 7 FLOOR BUILDING | 01-Oct-2026 | 30-Sep-2028 | 730 | Overall contract period | 100%
01 DESIGN & ENGINEERING | 01-Oct-2026 | 31-Mar-2027 | 182 | IFC target end Mar 2027; Shop drawings continue | 25%
01.01 Design Management | 01-Oct-2026 | 31-Mar-2027 | 182 | Ongoing coordination & approvals
01.02 Architectural Design | 01-Oct-2026 | 28-Feb-2027 | 151 | Early start for spatial coordination
01.03 Structural Design | 01-Oct-2026 | 15-Feb-2027 | 138 | Foundation design priority
01.04 MEP Design | 15-Oct-2026 | 15-Mar-2027 | 152 | Parallel with structural
01.05 BIM Coordination | 01-Nov-2026 | 20-Mar-2027 | 140 | Clash detection before IFC
01.06 Shop Drawings | 15-Jan-2027 | 30-Jun-2027 | 167 | Continues into early construction
02 PROCUREMENT | 01-Nov-2026 | 30-Jun-2028 | 608 | Long-lead items early; finishes later | 83%
Structural Materials | 15-Nov-2026 | 30-Jun-2027 | 228 | Rebar, concrete, formwork
Architectural Materials | 01-Feb-2027 | 31-Mar-2028 | 425 | Finishes packages
MEP Materials / Equipment | 15-Jan-2027 | 30-Apr-2028 | 472 | Long-lead HVAC, switchgear etc.
03 CONSTRUCTION | 01-Jan-2027 | 31-Jul-2028 | 578 | Main works period | 79%
03.01 BA – MAIN BUILDING | 01-Jan-2027 | 30-Jun-2028 | 547
B1 Basement | 01-Jan-2027 | 15-May-2027 | 135 | Earthwork → Foundation → Structure → WP → Arch/MEP
GF (Ground Floor) | 01-May-2027 | 15-Jul-2027 | 76 | First typical floor cycle
1F | 28-May-2027 | 15-Aug-2027 | 80 | Staggered ~28 days after previous
2F | 25-Jun-2027 | 15-Sep-2027 | 83
3F | 22-Jul-2027 | 15-Oct-2027 | 86
4F | 19-Aug-2027 | 15-Nov-2027 | 89
5F | 16-Sep-2027 | 15-Dec-2027 | 91
6F | 14-Oct-2027 | 15-Jan-2028 | 94
7F | 11-Nov-2027 | 15-Feb-2028 | 97
RF Roof | 15-Jan-2028 | 31-Mar-2028 | 77 | Structure + waterproofing + roof equipment
03.02 BX – EXTERNAL WORKS | 01-Apr-2027 | 31-Jul-2028 | 488 | Parallel with superstructure
04 COMMISSIONING & HANDOVER | 01-Jul-2028 | 30-Sep-2028 | 92 | Final 3 months | 13%
Testing & Commissioning | 01-Jul-2028 | 15-Aug-2028 | 46 | Systems + integrated testing
Snagging | 15-Jul-2028 | 31-Aug-2028 | 48 | Internal + External + MEP
Handover Documentation | 01-Jul-2028 | 15-Sep-2028 | 77 | As-built, O&M, certificates
Handover / Taking Over | 15-Aug-2028 | 30-Sep-2028 | 47 | Client inspection → Project Completion
KEY SCHEDULE ASSUMPTIONS
1. Project Start Date: 01 October 2026 ¦ Contract Completion: 30 September 2028 (24 months / 730 calendar days).
2. Design IFC target: end of March 2027 (Month 6). Shop drawings continue into construction period.
3. B1 (Basement) construction: Jan–May 2027 (earthwork, piles, foundation, basement structure, waterproofing).
4. Typical floor cycle (structure): approximately 22–25 working days; floors staggered ~28 calendar days.
5. Architectural finishes & MEP 2nd fix follow structure with 2–4 week lag and overlap between floors.
6. External works run largely in parallel with superstructure (Apr 2027 – Jul 2028).
7. Commissioning, snagging and handover concentrated in final 3 months (Jul–Sep 2028).
8. Durations are calendar days (not pure working days). Allow for weekends, public holidays and weather in detailed planning.
9. Long-lead procurement (structural steel, façade, major MEP equipment) starts in Design phase.
10. This baseline is suitable for Level 3–4 planning. Detailed weekly work plans (Last Planner) should refine Level 5 activities.
CRITICAL PATH (indicative): Design Foundation → B1 Earthwork/Piles → B1 Structure → GF Structure → successive floors → Roof → Commissioning → Handover
COST CODE LEGEND (Mock)
D-1xxx = Design ¦ P-2xxx = Procurement ¦ C-3xxx = Construction ¦ H-4xxx = Handover/Commissioning
C-31xx = B1 Basement ¦ C-32x1 = Floor Structural ¦ C-32x2 = Floor Architectural ¦ C-32x3/4 = Floor MEP ¦ C-33xx = Roof ¦ C-34xx = External
PREDECESSORS: FS (Finish-to-Start) links shown as WBS codes. Multiple predecessors separated by comma.
RESOURCES: Typical crew / role assignment (mock). Adjust to actual organisation and subcontract packages.

## Floor Construction Template
WBS Code | Activity | Type | Discipline | Typical Duration (Days) | Predecessors | Resources | Notes
XX.01 | 01 STRUCTURAL WORKS | Work Package | Structural |  |  |  | Typical floor structural cycle
XX.01.01 | Setting Out | Activity | Structural | 1 |  | Surveyor
XX.01.02 | Column Reinforcement | Activity | Structural | 2 | XX.01.01 | Rebar Team
XX.01.03 | Column Formwork | Activity | Structural | 2 | XX.01.02 | Formwork Team
XX.01.04 | Column Concrete | Activity | Structural | 1 | XX.01.03 | Concrete Team
XX.01.05 | Shear Wall Reinforcement | Activity | Structural | 2 | XX.01.01 | Rebar Team
XX.01.06 | Shear Wall Formwork | Activity | Structural | 2 | XX.01.05 | Formwork Team
XX.01.07 | Shear Wall Concrete | Activity | Structural | 1 | XX.01.06 | Concrete Team
XX.01.08 | Beam Formwork | Activity | Structural | 3 | XX.01.04 | Formwork Team
XX.01.09 | Slab Formwork | Activity | Structural | 3 | XX.01.04 | Formwork Team
XX.01.10 | Beam Reinforcement | Activity | Structural | 2 | XX.01.08 | Rebar Team
XX.01.11 | Slab Reinforcement | Activity | Structural | 2 | XX.01.09 | Rebar Team
XX.01.12 | MEP Embedded Items | Activity | MEP | 1 | XX.01.10, XX.01.11 | MEP Team
XX.01.13 | Structural Inspection | Activity | QA/QC | 0.5 | XX.01.12 | Inspector
XX.01.14 | Concrete Pour | Activity | Structural | 1 | XX.01.13 | Concrete Team
XX.01.15 | Concrete Curing | Activity | Structural | 7 | XX.01.14 |  | Minimum curing period
XX.01.16 | Formwork Removal | Activity | Structural | 2 | XX.01.15 | Formwork Team
XX.02 | 02 ARCHITECTURAL WORKS | Work Package | Architectural
XX.02.01 | Blockwork | Activity | Architectural | 5 | XX.01.16 | Masonry Team
XX.02.02 | Internal Partition | Activity | Architectural | 4 | XX.02.01 | Partition Team
XX.02.03 | Plastering | Activity | Architectural | 6 | XX.02.02 | Plaster Team
XX.02.04 | Waterproofing | Activity | Architectural | 3 | XX.02.01 | WP Team | Wet areas
XX.02.05 | Screed | Activity | Architectural | 3 | XX.02.04 | Screed Team
XX.02.06 | Ceiling | Activity | Architectural | 4 | XX.03.01 | Ceiling Team | After first fix
XX.02.07 | Flooring | Activity | Architectural | 5 | XX.02.05 | Flooring Team
XX.02.08 | Wall Tiling | Activity | Architectural | 4 | XX.02.03 | Tiling Team
XX.02.09 | Stone / Marble | Activity | Architectural | 4 | XX.02.05 | Stone Team
XX.02.10 | Door Frames | Activity | Architectural | 2 | XX.02.01 | Joinery
XX.02.11 | Doors | Activity | Architectural | 2 | XX.02.10 | Joinery | After painting
XX.02.12 | Windows | Activity | Architectural | 3 | XX.01.16 | Window Team
XX.02.13 | Glass | Activity | Architectural | 2 | XX.02.12 | Glazing Team
XX.02.14 | Painting Primer | Activity | Architectural | 2 | XX.02.03 | Paint Team
XX.02.15 | Internal Painting | Activity | Architectural | 4 | XX.02.14 | Paint Team
XX.02.16 | External Finishing | Activity | Architectural | 5 | XX.01.16 | External Team
XX.02.17 | Final Architectural Finishes | Activity | Architectural | 3 | XX.02.15 | Finishing Team
XX.03 | 03 MEP FIRST FIX | Work Package | MEP |  |  |  | Before plastering / ceiling
XX.03.01 | Electrical Conduits | Activity | Electrical | 3 | XX.01.16 | Electrical Team
XX.03.02 | Cable Trays | Activity | Electrical | 2 | XX.01.16 | Electrical Team
XX.03.03 | Plumbing Pipes | Activity | Plumbing | 3 | XX.01.16 | Plumbing Team
XX.03.04 | Drainage Pipes | Activity | Plumbing | 3 | XX.01.16 | Plumbing Team
XX.03.05 | HVAC Ductwork | Activity | HVAC | 4 | XX.01.16 | HVAC Team
XX.03.06 | HVAC Pipes | Activity | HVAC | 3 | XX.01.16 | HVAC Team
XX.03.07 | Fire Fighting Pipes | Activity | Fire Fighting | 3 | XX.01.16 | FF Team
XX.03.08 | Fire Alarm Conduits | Activity | Fire Alarm | 2 | XX.01.16 | FA Team
XX.03.09 | ELV Conduits | Activity | ELV | 2 | XX.01.16 | ELV Team
XX.04 | 04 MEP SECOND FIX | Work Package | MEP |  |  |  | After finishes
XX.04.01 | Cable Pulling | Activity | Electrical | 3 | XX.02.06 | Electrical Team
XX.04.02 | DB Installation | Activity | Electrical | 2 | XX.04.01 | Electrical Team
XX.04.03 | Lighting | Activity | Electrical | 3 | XX.02.06 | Electrical Team
XX.04.04 | Switches & Sockets | Activity | Electrical | 2 | XX.02.15 | Electrical Team
XX.04.05 | Plumbing Fixtures | Activity | Plumbing | 3 | XX.02.08 | Plumbing Team
XX.04.06 | HVAC Equipment | Activity | HVAC | 3 | XX.03.05 | HVAC Team
XX.04.07 | Fire Alarm Devices | Activity | Fire Alarm | 2 | XX.03.08 | FA Team
XX.04.08 | Sprinkler Heads | Activity | Fire Fighting | 2 | XX.03.07 | FF Team
XX.04.09 | Fire Fighting Equipment | Activity | Fire Fighting | 2 | XX.03.07 | FF Team
XX.04.10 | ELV Devices | Activity | ELV | 2 | XX.03.09 | ELV Team
XX.05 | 05 TESTING & INSPECTION | Work Package | QA/QC
XX.05.01 | Structural Inspection | Activity | QA/QC | 1 | XX.01.16 | Inspector
XX.05.02 | Architectural Inspection | Activity | QA/QC | 1 | XX.02.17 | Inspector
XX.05.03 | MEP Inspection | Activity | QA/QC | 1 | XX.04.10 | Inspector
XX.05.04 | Testing | Activity | QA/QC | 2 | XX.05.03 | Testing Team
XX.05.05 | Snagging | Activity | QA/QC | 2 | XX.05.04 | QA Team
XX.05.06 | Snag Rectification | Activity | QA/QC | 3 | XX.05.05 | All Trades
XX.05.07 | Floor Completion | Activity | QA/QC | 1 | XX.05.06 | PM | Floor handover milestone
NOTE: Durations above are typical. In the Master WBS the Baseline Start/Finish for each floor (GF–7F) are staggered ~28 calendar days to fit the 24-month programme.

## WBS Summary Structure
Level | WBS Code | Description | Purpose / Scope
0 | 0 | PROJECT – 7 FLOOR BUILDING | Overall project
1 | 01 | DESIGN & ENGINEERING | Produce approved design information
2 | 01.01 | Design Management | Overall design control & approvals
2 | 01.02 | Architectural Design | All architectural deliverables to IFC
2 | 01.03 | Structural Design | Foundation to roof structural design
2 | 01.04 | MEP Design | Electrical, ELV, FA, HVAC, Plumbing, FF + Coordination
2 | 01.05 | BIM Coordination | Model federation, clash detection & resolution
2 | 01.06 | Shop Drawings | Contractor shop drawings & approvals
1 | 02 | PROCUREMENT | Obtain approved materials, equipment & packages
2 | 02.01 | Procurement Management | Strategy, schedule, tracking, expediting
2 | 02.02 | Structural Materials | Rebar, concrete, formwork, waterproofing, steel
2 | 02.03 | Architectural Materials | Block, finishes, doors, windows, façade, fixtures
2 | 02.04 | MEP Materials | Cables, equipment, pipes, ductwork, devices
2 | 02.05 | Procurement Process | Requisition → RFQ → Eval → PO → Approval
2 | 02.06 | Manufacturing & Expediting | Production, FAT, inspection, expediting
2 | 02.07 | Delivery & Receiving | Transport, delivery, inspection, storage
1 | 03 | CONSTRUCTION | Physically execute the works
2 | 03.01 | BA – MAIN BUILDING | Basement to Roof
3 | 03.01.01 | B1 – Basement | Earthwork, Foundation, Structure, WP, Arch, MEP
3 | 03.01.02–09 | GF to 7F | Typical floor template: Structure → Arch → MEP 1st/2nd Fix → Testing
3 | 03.01.10 | RF – Roof | Structure, Waterproofing, Finishes, Roof MEP
2 | 03.02 | BX – EXTERNAL WORKS | Site prep, civil, drainage, utilities, roads, landscape, boundary
1 | 04 | COMMISSIONING & HANDOVER | Testing, snagging, documentation & handover
2 | 04.01 | Testing & Commissioning | All systems testing + integrated testing
2 | 04.02 | Snagging | Internal / External / MEP / Architectural snagging
2 | 04.03 | Handover Documentation | As-built, O&M, certificates, training, dossier
2 | 04.04 | Handover | Client inspection, Taking Over, Project Completion

## Legend & Guidance
MASTER CONSTRUCTION WBS – 7 FLOOR BUILDING
PURPOSE OF BRANCHES
01 Design & Engineering | Produce approved design information (Brief → Design → Coordination → Approval → IFC → Shop Drawings)
02 Procurement | Obtain approved materials, equipment and subcontracted packages (Requirement → RFQ → Tech/Commercial → PO → Manufacturing → Delivery)
03 Construction | Physically execute the works (Main Building by floor + External Works)
04 Commissioning & Handover | Testing, snagging, documentation and formal handover
WBS LEVELS
Level 0 | Project
Level 1 | Phase (Design / Procurement / Construction / Commissioning)
Level 2 | Major Work Package / Discipline
Level 3 | Sub-package or Floor / Area
Level 4 | Work Group (e.g. Structural Works, Architectural Works)
Level 5 | Activity (scheduleable item with duration, predecessors, resources)
TYPE COLUMN
Project / Phase / Work Package / Summary | Not schedule activities – used for grouping and roll-up
Activity | Real schedule activity – assign Duration, Start, Finish, Predecessors, Resources, Cost
Material Package | Procurement item / package
HOW TO USE THIS WBS FOR SCHEDULING
1 | Keep only Level 4–5 (or selected Level 3) items as schedule Activities
2 | Assign realistic durations and logic links (FS, SS, FF with lag)
3 | Use the Floor Construction Template sheet as the standard cycle for GF–7F
4 | Link Procurement activities to Construction (material delivery milestones)
5 | Link Design IFC / Shop Drawing approvals as predecessors to related Construction activities
6 | Add resources, costs and baselines in your scheduling software (Primavera / MS Project)
COLOUR CODING
Dark Navy | Project level
Blue | Phase (Level 1)
Light Blue | Major Work Package (Level 2)
Pale Blue | Sub-package / Floor (Level 3)
Grey | Work Group (Level 4)
White | Activity (Level 5)

## Activity Count Summary
ACTIVITY COUNT BY PHASE & DISCIPLINE
Phase / Section | Work Packages | Activities (approx) | Remarks
01 Design & Engineering | 6 major | ~90 | Design Mgmt, Arch, Struct, MEP (7 sub), BIM, Shop Dwg
02 Procurement | 7 major | ~70 | Mgmt, 3 material groups, Process, Manufacturing, Delivery
03.01 B1 Basement | 6 groups | ~44 | Earthwork, Foundation, Structure, WP, Arch, MEP
03.01 GF–7F (8 floors) | 5 groups × 8 | ~472 | Typical floor template applied to each floor
03.01 RF Roof | 4 groups | ~17 | Structure, WP, Arch, MEP
03.02 External Works | 8 groups | ~50 | Site prep through external finishes
04 Commissioning & Handover | 4 major | ~24 | T&C, Snagging, Documentation, Handover
TOTAL (approx) |  | ~767 | Full detailed activity list ready for filtering & scheduling
Note: Activity counts are approximate based on the detailed breakdown provided. Use AutoFilter on Master WBS sheet to filter by Level, Type, Discipline or Floor.