## All Step Templates
Group | Template Name | Step No | Step Name | Weight | Discipline | Resource / Crew | Est. Duration (Days) | Inspection Hold Point | Notes
Architectural Finishes | Blockwork / Masonry – Typical Floor | 1 | Setting Out & Setting Out Marks | 10 | Architectural | Architectural Crew | 1 | No | Lines, openings, levels
Architectural Finishes | Blockwork / Masonry – Typical Floor | 2 | First Course & DPC | 15 | Architectural | Architectural Crew | 1.5 | No | Including DPC / waterproof course
Architectural Finishes | Blockwork / Masonry – Typical Floor | 3 | Block / Brick Laying | 50 | Architectural | Masonry Crew | 1.5 | No | Main wall construction
Architectural Finishes | Blockwork / Masonry – Typical Floor | 4 | Reinforcement & Ties | 10 | Architectural | Architectural Crew | 2 | No | Horizontal & vertical reinforcement
Architectural Finishes | Blockwork / Masonry – Typical Floor | 5 | Cleaning & Pointing | 10 | Architectural | Architectural Crew | 1 | No | Joint finishing
Architectural Finishes | Blockwork / Masonry – Typical Floor | 6 | Inspection & Handover | 5 | Architectural | QA/QC | 0.5 | Yes | QA check before plaster
Architectural Finishes | Internal Partition – Typical Floor | 1 | Setting Out | 10 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Internal Partition – Typical Floor | 2 | Track & Stud Installation | 30 | Architectural | Drywall Crew | 2 | No
Architectural Finishes | Internal Partition – Typical Floor | 3 | Insulation / Acoustic Fill | 15 | Architectural | Architectural Crew | 1.5 | No | If required
Architectural Finishes | Internal Partition – Typical Floor | 4 | Board Fixing (both sides) | 30 | Architectural | Drywall Crew | 1.5 | No
Architectural Finishes | Internal Partition – Typical Floor | 5 | Jointing & Skimming | 10 | Architectural | Plaster Crew | 1.5 | No
Architectural Finishes | Internal Partition – Typical Floor | 6 | Inspection | 5 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Plastering (Internal) – Typical Floor | 1 | Surface Preparation & Dubbing | 15 | Architectural | Architectural Crew | 1 | No | Cleaning, hacking, bonding agent
Architectural Finishes | Plastering (Internal) – Typical Floor | 2 | Corner Beads & Stop Beads | 10 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Plastering (Internal) – Typical Floor | 3 | Scratch / Base Coat | 30 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Plastering (Internal) – Typical Floor | 4 | Finish Coat | 30 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Plastering (Internal) – Typical Floor | 5 | Curing & Cleaning | 10 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Plastering (Internal) – Typical Floor | 6 | Inspection | 5 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 1 | Surface Preparation | 15 | Architectural | Waterproofing Crew | 1 | No
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 2 | Primer Application | 15 | Architectural | Waterproofing Crew | 1.5 | No
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 3 | First Coat Waterproofing | 25 | Architectural | Waterproofing Crew | 1.5 | No
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 4 | Second Coat + Reinforcement | 25 | Architectural | Waterproofing Crew | 2 | No | Mesh / membrane at corners
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 5 | Protection Layer | 15 | Architectural | Waterproofing Crew | 1.5 | No
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 6 | Flood Test / Inspection | 5 | Architectural | Waterproofing Crew | 0.5 | Yes
Architectural Finishes | Screed – Typical Floor | 1 | Surface Preparation & Cleaning | 15 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Screed – Typical Floor | 2 | Level Marks & Datum | 15 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Screed – Typical Floor | 3 | Screed Laying | 40 | Architectural | Screed Crew | 1.5 | No
Architectural Finishes | Screed – Typical Floor | 4 | Levelling & Finishing | 20 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Screed – Typical Floor | 5 | Curing | 5 | Architectural | Architectural Crew | 3 | No
Architectural Finishes | Screed – Typical Floor | 6 | Inspection | 5 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Ceiling – Typical Floor | 1 | Ceiling Frame / Suspension | 25 | Architectural | Ceiling Crew | 1.5 | No | Main & cross runners, hangers
Architectural Finishes | Ceiling – Typical Floor | 2 | Ceiling Board / Panel Fixing | 35 | Architectural | Ceiling Crew | 1.5 | No
Architectural Finishes | Ceiling – Typical Floor | 3 | Jointing & Skim Coat | 20 | Architectural | Plaster Crew | 1.5 | No
Architectural Finishes | Ceiling – Typical Floor | 4 | Final Paint / Finish | 15 | Architectural | Ceiling Crew | 1.5 | No
Architectural Finishes | Ceiling – Typical Floor | 5 | Inspection & Handover | 5 | Architectural | Ceiling Crew | 0.5 | Yes
Architectural Finishes | Flooring – Typical Floor | 1 | Substrate Preparation | 15 | Architectural | Architectural Crew | 1 | No | Cleaning, priming
Architectural Finishes | Flooring – Typical Floor | 2 | Waterproofing (if wet area) | 10 | Architectural | Waterproofing Crew | 1.5 | No | Optional – set to 0 if not needed
Architectural Finishes | Flooring – Typical Floor | 3 | Setting Out & Layout | 10 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Flooring – Typical Floor | 4 | Tile / Stone / Vinyl Laying | 40 | Architectural | Tiling / Flooring Crew | 1.5 | No
Architectural Finishes | Flooring – Typical Floor | 5 | Grouting & Cleaning | 15 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Flooring – Typical Floor | 6 | Final Inspection | 10 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Wall Tiling – Typical Floor | 1 | Surface Preparation | 15 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Wall Tiling – Typical Floor | 2 | Waterproofing (wet areas) | 15 | Architectural | Waterproofing Crew | 1.5 | No
Architectural Finishes | Wall Tiling – Typical Floor | 3 | Setting Out & Guides | 10 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Wall Tiling – Typical Floor | 4 | Tile Installation | 40 | Architectural | Tiling / Flooring Crew | 2 | No
Architectural Finishes | Wall Tiling – Typical Floor | 5 | Grouting & Sealing | 15 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Wall Tiling – Typical Floor | 6 | Cleaning & Inspection | 5 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Stone / Marble – Typical Floor | 1 | Surface Preparation | 15 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Stone / Marble – Typical Floor | 2 | Setting Out & Template | 15 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Stone / Marble – Typical Floor | 3 | Stone Fixing / Laying | 40 | Architectural | Tiling / Flooring Crew | 1.5 | No
Architectural Finishes | Stone / Marble – Typical Floor | 4 | Joint Filling / Grouting | 15 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Stone / Marble – Typical Floor | 5 | Polishing & Protection | 10 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Stone / Marble – Typical Floor | 6 | Inspection | 5 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Internal Painting – Typical Floor | 1 | Surface Preparation & Sanding | 20 | Architectural | Paint Crew | 1 | No
Architectural Finishes | Internal Painting – Typical Floor | 2 | Primer / Sealer | 20 | Architectural | Paint Crew | 1.5 | No
Architectural Finishes | Internal Painting – Typical Floor | 3 | First Coat | 25 | Architectural | Paint Crew | 1.5 | No
Architectural Finishes | Internal Painting – Typical Floor | 4 | Second / Final Coat | 25 | Architectural | Paint Crew | 1.5 | No
Architectural Finishes | Internal Painting – Typical Floor | 5 | Touch-up & Cleaning | 5 | Architectural | Paint Crew | 1 | No
Architectural Finishes | Internal Painting – Typical Floor | 6 | Inspection | 5 | Architectural | Paint Crew | 0.5 | Yes
Architectural Finishes | Door Frames – Typical Floor | 1 | Setting Out & Opening Check | 20 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Door Frames – Typical Floor | 2 | Frame Installation & Fixing | 50 | Architectural | Joinery / Glazing Crew | 2 | No
Architectural Finishes | Door Frames – Typical Floor | 3 | Plumb, Level & Temporary Brace | 20 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Door Frames – Typical Floor | 4 | Inspection | 10 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Doors (Leaf + Ironmongery) – Typical Floor | 1 | Door Leaf Installation | 40 | Architectural | Joinery / Glazing Crew | 2 | No
Architectural Finishes | Doors (Leaf + Ironmongery) – Typical Floor | 2 | Hinges & Alignment | 20 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Doors (Leaf + Ironmongery) – Typical Floor | 3 | Lockset / Handle / Ironmongery | 25 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Doors (Leaf + Ironmongery) – Typical Floor | 4 | Adjustment & Operation Test | 10 | Architectural | Architectural Crew | 1.5 | Yes
Architectural Finishes | Doors (Leaf + Ironmongery) – Typical Floor | 5 | Inspection | 5 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Windows / Glazing – Typical Floor | 1 | Frame Installation | 30 | Architectural | Joinery / Glazing Crew | 2 | No
Architectural Finishes | Windows / Glazing – Typical Floor | 2 | Alignment & Fixing | 20 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Windows / Glazing – Typical Floor | 3 | Glass / Panel Installation | 30 | Architectural | Joinery / Glazing Crew | 2 | No
Architectural Finishes | Windows / Glazing – Typical Floor | 4 | Sealing & Weatherproofing | 15 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Windows / Glazing – Typical Floor | 5 | Inspection & Operation Test | 5 | Architectural | QA/QC | 0.5 | Yes
MEP First Fix | Electrical Conduits – Typical Floor | 1 | Setting Out & Marking | 15 | Electrical / ELV | Electrical Crew | 1 | No | Routes, boxes, levels
MEP First Fix | Electrical Conduits – Typical Floor | 2 | Conduit Installation (concealed) | 45 | Electrical / ELV | Electrical Crew | 2 | No
MEP First Fix | Electrical Conduits – Typical Floor | 3 | Junction / Draw Boxes Installation | 15 | Electrical / ELV | Electrical Crew | 2 | No
MEP First Fix | Electrical Conduits – Typical Floor | 4 | Pull Wire / Fish Wire | 10 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | Electrical Conduits – Typical Floor | 5 | Continuity Check & Cleaning | 10 | Electrical / ELV | Electrical Crew | 1 | No
MEP First Fix | Electrical Conduits – Typical Floor | 6 | Inspection | 5 | Electrical / ELV | QA/QC + Electrical Engineer | 0.5 | Yes
MEP First Fix | Cable Trays – Typical Floor | 1 | Setting Out & Support Fixing | 20 | Electrical / ELV | Electrical Crew | 1 | No | Hangers, brackets
MEP First Fix | Cable Trays – Typical Floor | 2 | Tray / Ladder Installation | 40 | Electrical / ELV | Electrical Crew | 2 | No
MEP First Fix | Cable Trays – Typical Floor | 3 | Jointing & Earthing | 15 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | Cable Trays – Typical Floor | 4 | Cover / Lid Installation | 10 | Electrical / ELV | Electrical Crew | 2 | No | If applicable
MEP First Fix | Cable Trays – Typical Floor | 5 | Alignment & Level Check | 10 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | Cable Trays – Typical Floor | 6 | Inspection | 5 | Electrical / ELV | QA/QC + Electrical Engineer | 0.5 | Yes
MEP First Fix | Plumbing Pipes – Typical Floor | 1 | Setting Out & Marking | 15 | Plumbing | Plumbing Crew | 1 | No
MEP First Fix | Plumbing Pipes – Typical Floor | 2 | Pipe Installation & Fixing | 40 | Plumbing | Plumbing Crew | 2 | No
MEP First Fix | Plumbing Pipes – Typical Floor | 3 | Fittings & Joints | 20 | Plumbing | Plumbing Crew | 1.5 | No
MEP First Fix | Plumbing Pipes – Typical Floor | 4 | Pressure Test | 15 | Plumbing | QA/QC + Plumbing Engineer | 1 | Yes
MEP First Fix | Plumbing Pipes – Typical Floor | 5 | Insulation (if required) | 5 | Plumbing | Plumbing Crew | 1.5 | No
MEP First Fix | Plumbing Pipes – Typical Floor | 6 | Inspection | 5 | Plumbing | QA/QC + Plumbing Engineer | 0.5 | Yes
MEP First Fix | Drainage Pipes – Typical Floor | 1 | Setting Out & Gradient Check | 15 | Plumbing | Plumbing Crew | 1 | No
MEP First Fix | Drainage Pipes – Typical Floor | 2 | Pipe Installation & Supports | 40 | Plumbing | Plumbing Crew | 2 | No
MEP First Fix | Drainage Pipes – Typical Floor | 3 | Fittings & Joints | 20 | Plumbing | Plumbing Crew | 1.5 | No
MEP First Fix | Drainage Pipes – Typical Floor | 4 | Slope / Gradient Verification | 10 | Plumbing | Plumbing Crew | 1.5 | No
MEP First Fix | Drainage Pipes – Typical Floor | 5 | Leak / Water Test | 10 | Plumbing | QA/QC + Plumbing Engineer | 1.5 | Yes
MEP First Fix | Drainage Pipes – Typical Floor | 6 | Inspection | 5 | Plumbing | QA/QC + Plumbing Engineer | 0.5 | Yes
MEP First Fix | HVAC Ductwork – Typical Floor | 1 | Setting Out & Support Installation | 15 | HVAC | HVAC Crew | 1 | No
MEP First Fix | HVAC Ductwork – Typical Floor | 2 | Duct Installation | 40 | HVAC | HVAC Crew | 2 | No | Straight ducts + fittings
MEP First Fix | HVAC Ductwork – Typical Floor | 3 | Joint Sealing & Gaskets | 15 | HVAC | HVAC Crew | 1.5 | No
MEP First Fix | HVAC Ductwork – Typical Floor | 4 | Flexible Connections | 10 | HVAC | HVAC Crew | 1.5 | No
MEP First Fix | HVAC Ductwork – Typical Floor | 5 | Insulation | 15 | HVAC | HVAC Crew | 1.5 | No
MEP First Fix | HVAC Ductwork – Typical Floor | 6 | Inspection & Cleaning | 5 | HVAC | QA/QC + HVAC Engineer | 0.5 | Yes
MEP First Fix | HVAC Pipes – Typical Floor | 1 | Setting Out & Support Fixing | 15 | HVAC | HVAC Crew | 1 | No
MEP First Fix | HVAC Pipes – Typical Floor | 2 | Pipe Installation | 35 | HVAC | HVAC Crew | 2 | No
MEP First Fix | HVAC Pipes – Typical Floor | 3 | Fittings, Valves & Joints | 20 | HVAC | HVAC Crew | 1.5 | No
MEP First Fix | HVAC Pipes – Typical Floor | 4 | Pressure Test | 15 | HVAC | QA/QC + HVAC Engineer | 1 | Yes
MEP First Fix | HVAC Pipes – Typical Floor | 5 | Insulation & Cladding | 10 | HVAC | HVAC Crew | 1.5 | No
MEP First Fix | HVAC Pipes – Typical Floor | 6 | Inspection | 5 | HVAC | QA/QC + HVAC Engineer | 0.5 | Yes
MEP First Fix | Fire Fighting Pipes – Typical Floor | 1 | Setting Out & Support Installation | 15 | Fire Fighting | Fire Fighting Crew | 1 | No
MEP First Fix | Fire Fighting Pipes – Typical Floor | 2 | Pipe Installation | 40 | Fire Fighting | Fire Fighting Crew | 2 | No
MEP First Fix | Fire Fighting Pipes – Typical Floor | 3 | Fittings, Valves & Joints | 20 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP First Fix | Fire Fighting Pipes – Typical Floor | 4 | Pressure / Hydrostatic Test | 15 | Fire Fighting | QA/QC + FF Engineer | 1.5 | Yes
MEP First Fix | Fire Fighting Pipes – Typical Floor | 5 | Painting / Identification | 5 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP First Fix | Fire Fighting Pipes – Typical Floor | 6 | Inspection | 5 | Fire Fighting | QA/QC + FF Engineer | 0.5 | Yes
MEP First Fix | Fire Alarm Conduits – Typical Floor | 1 | Setting Out & Marking | 15 | Electrical / ELV | Electrical Crew | 1 | No
MEP First Fix | Fire Alarm Conduits – Typical Floor | 2 | Conduit Installation | 45 | Electrical / ELV | Electrical Crew | 2 | No
MEP First Fix | Fire Alarm Conduits – Typical Floor | 3 | Junction Boxes & Accessories | 15 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | Fire Alarm Conduits – Typical Floor | 4 | Pull Wire Installation | 10 | Electrical / ELV | Electrical Crew | 2 | No
MEP First Fix | Fire Alarm Conduits – Typical Floor | 5 | Continuity Check | 10 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | Fire Alarm Conduits – Typical Floor | 6 | Inspection | 5 | Electrical / ELV | QA/QC + Electrical Engineer | 0.5 | Yes
MEP First Fix | ELV Conduits – Typical Floor | 1 | Setting Out & Marking | 15 | Electrical / ELV | Electrical Crew | 1 | No
MEP First Fix | ELV Conduits – Typical Floor | 2 | Conduit / Trunking Installation | 45 | Electrical / ELV | Electrical Crew | 2 | No
MEP First Fix | ELV Conduits – Typical Floor | 3 | Boxes & Accessories | 15 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | ELV Conduits – Typical Floor | 4 | Pull Wire / Draw Rope | 10 | Electrical / ELV | Electrical Crew | 1.5 | No
MEP First Fix | ELV Conduits – Typical Floor | 5 | Continuity & Cleaning | 10 | Electrical / ELV | Electrical Crew | 1 | No
MEP First Fix | ELV Conduits – Typical Floor | 6 | Inspection | 5 | Electrical / ELV | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Second Fix | Cable Pulling – Typical Floor | 1 | Cable Preparation & Labeling | 15 | Electrical | Electrical Crew | 1 | No | Cutting, tagging, checking
MEP Second Fix | Cable Pulling – Typical Floor | 2 | Cable Pulling | 50 | Electrical | Electrical Crew | 1.5 | No | Main pulling work
MEP Second Fix | Cable Pulling – Typical Floor | 3 | Termination at both ends | 20 | Electrical | Electrical Crew | 1.5 | No | Glanding, lug, connection
MEP Second Fix | Cable Pulling – Typical Floor | 4 | Continuity & Insulation Test | 10 | Electrical | QA/QC + Electrical Engineer | 1.5 | Yes | Megger / continuity
MEP Second Fix | Cable Pulling – Typical Floor | 5 | Inspection & Documentation | 5 | Electrical | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Second Fix | DB Installation – Typical Floor | 1 | DB Positioning & Fixing | 25 | Electrical | Electrical Crew | 1.5 | No | Wall / floor mounting
MEP Second Fix | DB Installation – Typical Floor | 2 | Incoming Cable Termination | 20 | Electrical | Electrical Crew | 1.5 | No
MEP Second Fix | DB Installation – Typical Floor | 3 | Outgoing Circuit Termination | 30 | Electrical | Electrical Crew | 1.5 | No
MEP Second Fix | DB Installation – Typical Floor | 4 | Internal Wiring & Labelling | 15 | Electrical | Electrical Crew | 1 | No
MEP Second Fix | DB Installation – Typical Floor | 5 | Testing & Inspection | 10 | Electrical | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Second Fix | Lighting Installation – Typical Floor | 1 | Fixture Positioning & Fixing | 30 | Electrical | Electrical Crew | 1.5 | No
MEP Second Fix | Lighting Installation – Typical Floor | 2 | Wiring & Connection | 30 | Electrical | Electrical Crew | 1.5 | No
MEP Second Fix | Lighting Installation – Typical Floor | 3 | Lamp / Driver Installation | 20 | Electrical | Electrical Crew | 2 | No
MEP Second Fix | Lighting Installation – Typical Floor | 4 | Testing & Alignment | 15 | Electrical | QA/QC + Electrical Engineer | 1 | Yes
MEP Second Fix | Lighting Installation – Typical Floor | 5 | Final Cleaning & Inspection | 5 | Electrical | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Second Fix | Switches & Sockets – Typical Floor | 1 | Back Box Preparation | 15 | Electrical | Electrical Crew | 1 | No
MEP Second Fix | Switches & Sockets – Typical Floor | 2 | Wiring & Connection | 40 | Electrical | Electrical Crew | 1.5 | No
MEP Second Fix | Switches & Sockets – Typical Floor | 3 | Device Fixing & Faceplate | 30 | Electrical | Electrical Crew | 1.5 | No
MEP Second Fix | Switches & Sockets – Typical Floor | 4 | Function Test | 10 | Electrical | QA/QC + Electrical Engineer | 1 | Yes
MEP Second Fix | Switches & Sockets – Typical Floor | 5 | Inspection | 5 | Electrical | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Second Fix | Plumbing Fixtures – Typical Floor | 1 | Fixture Positioning & Setting Out | 15 | Plumbing | Plumbing Crew | 1 | No
MEP Second Fix | Plumbing Fixtures – Typical Floor | 2 | Connection to Supply & Waste | 40 | Plumbing | Plumbing Crew | 1.5 | No
MEP Second Fix | Plumbing Fixtures – Typical Floor | 3 | Fixing & Sealing | 25 | Plumbing | Plumbing Crew | 1.5 | No
MEP Second Fix | Plumbing Fixtures – Typical Floor | 4 | Testing (flow & leakage) | 15 | Plumbing | QA/QC + Plumbing Engineer | 1 | Yes
MEP Second Fix | Plumbing Fixtures – Typical Floor | 5 | Cleaning & Inspection | 5 | Plumbing | QA/QC + Plumbing Engineer | 0.5 | Yes
MEP Second Fix | HVAC Equipment – Typical Floor | 1 | Equipment Positioning & Fixing | 25 | HVAC | HVAC Crew | 1.5 | No
MEP Second Fix | HVAC Equipment – Typical Floor | 2 | Duct / Pipe Connection | 30 | HVAC | HVAC Crew | 1.5 | No
MEP Second Fix | HVAC Equipment – Typical Floor | 3 | Electrical & Control Connection | 20 | HVAC | HVAC Crew | 1.5 | No
MEP Second Fix | HVAC Equipment – Typical Floor | 4 | Insulation & Cladding | 15 | HVAC | HVAC Crew | 1.5 | No
MEP Second Fix | HVAC Equipment – Typical Floor | 5 | Testing & Commissioning Check | 10 | HVAC | QA/QC + HVAC Engineer | 1 | Yes
MEP Second Fix | Fire Alarm Devices – Typical Floor | 1 | Device Positioning & Fixing | 25 | Fire Fighting | Fire Fighting Crew | 1.5 | No | Detectors, MCPs, sounders
MEP Second Fix | Fire Alarm Devices – Typical Floor | 2 | Wiring & Termination | 35 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Second Fix | Fire Alarm Devices – Typical Floor | 3 | Addressing / Programming | 20 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Second Fix | Fire Alarm Devices – Typical Floor | 4 | Function Test | 15 | Fire Fighting | QA/QC + FF Engineer | 1 | Yes
MEP Second Fix | Fire Alarm Devices – Typical Floor | 5 | Inspection & Documentation | 5 | Fire Fighting | QA/QC + FF Engineer | 0.5 | Yes
MEP Second Fix | Sprinkler Heads – Typical Floor | 1 | Head Positioning & Alignment | 20 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Second Fix | Sprinkler Heads – Typical Floor | 2 | Installation & Tightening | 40 | Fire Fighting | Fire Fighting Crew | 2 | No
MEP Second Fix | Sprinkler Heads – Typical Floor | 3 | Escutcheon / Cover Plate | 15 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Second Fix | Sprinkler Heads – Typical Floor | 4 | Pressure / Leak Test | 20 | Fire Fighting | QA/QC + FF Engineer | 1.5 | Yes
MEP Second Fix | Sprinkler Heads – Typical Floor | 5 | Inspection | 5 | Fire Fighting | QA/QC + FF Engineer | 0.5 | Yes
MEP Second Fix | Fire Fighting Equipment – Typical Floor | 1 | Equipment Positioning & Fixing | 30 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Second Fix | Fire Fighting Equipment – Typical Floor | 2 | Pipe / Hose Connection | 30 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Second Fix | Fire Fighting Equipment – Typical Floor | 3 | Valve / Accessory Installation | 20 | Fire Fighting | Fire Fighting Crew | 2 | No
MEP Second Fix | Fire Fighting Equipment – Typical Floor | 4 | Pressure Test & Function Check | 15 | Fire Fighting | QA/QC + FF Engineer | 1 | Yes
MEP Second Fix | Fire Fighting Equipment – Typical Floor | 5 | Inspection & Signage | 5 | Fire Fighting | QA/QC + FF Engineer | 0.5 | Yes
MEP Second Fix | ELV Devices – Typical Floor | 1 | Device Positioning & Fixing | 25 | ELV | Electrical Crew | 1.5 | No
MEP Second Fix | ELV Devices – Typical Floor | 2 | Cable Termination | 30 | ELV | Electrical Crew | 1.5 | No
MEP Second Fix | ELV Devices – Typical Floor | 3 | Power & Network Connection | 20 | ELV | Electrical Crew | 1.5 | No
MEP Second Fix | ELV Devices – Typical Floor | 4 | Configuration / Programming | 15 | ELV | Electrical Crew | 1.5 | No
MEP Second Fix | ELV Devices – Typical Floor | 5 | Testing & Inspection | 10 | ELV | QA/QC + Electrical Engineer | 0.5 | Yes
Structure & Early Works | Site Preparation | 1 | Site Clearance & Demolition | 20 | Structural | Structural Crew | 1.5 | No | Clear vegetation, debris, existing structures
Structure & Early Works | Site Preparation | 2 | Temporary Fencing & Access | 15 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Site Preparation | 3 | Temporary Facilities Setup | 20 | Structural | Structural Crew | 1.5 | No | Site office, stores, welfare
Structure & Early Works | Site Preparation | 4 | Temporary Roads & Drainage | 20 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Site Preparation | 5 | Site Grading & Levelling | 15 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Site Preparation | 6 | Inspection & Handover to Survey | 10 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Anti-Termite Treatment | 1 | Surface Preparation & Cleaning | 15 | Structural | Structural Crew | 1 | No
Structure & Early Works | Anti-Termite Treatment | 2 | Trench / Hole Preparation | 15 | Structural | Structural Crew | 1 | No
Structure & Early Works | Anti-Termite Treatment | 3 | Chemical Application (Horizontal) | 25 | Structural | Structural Crew | 1.5 | No | Under slab / foundation
Structure & Early Works | Anti-Termite Treatment | 4 | Chemical Application (Vertical) | 25 | Structural | Structural Crew | 1.5 | No | Perimeter / walls
Structure & Early Works | Anti-Termite Treatment | 5 | Protection & Backfill | 10 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Anti-Termite Treatment | 6 | Certificate & Inspection | 10 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Piling Works | 1 | Setting Out & Pile Points | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Piling Works | 2 | Pile Installation / Driving | 40 | Structural | Structural Crew | 2 | No
Structure & Early Works | Piling Works | 3 | Pile Head Breaking / Cut-off | 15 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Piling Works | 4 | Pile Testing (Working Load / Integrity) | 20 | Structural | Structural Crew | 1 | Yes
Structure & Early Works | Piling Works | 5 | Pile Rectification (if any) | 10 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Piling Works | 6 | As-built & Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Substructure Works | 1 | Excavation to Formation | 15 | Structural | Civil / Survey Crew | 1.5 | No
Structure & Early Works | Substructure Works | 2 | Blinding / Lean Concrete | 10 | Structural | Concrete Crew | 1.5 | No
Structure & Early Works | Substructure Works | 3 | Pile Cap / Raft Reinforcement | 20 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Substructure Works | 4 | Pile Cap / Raft Formwork & Concrete | 25 | Structural | Formwork Crew | 1.5 | No
Structure & Early Works | Substructure Works | 5 | Ground Beam / Slab on Grade | 20 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Substructure Works | 6 | Inspection & Backfill Preparation | 10 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Underground MEP / Embedded Services | 1 | Setting Out & Coordination | 15 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Underground MEP / Embedded Services | 2 | Trenching / Sleeve Installation | 25 | Structural | Structural Crew | 2 | No
Structure & Early Works | Underground MEP / Embedded Services | 3 | Pipe / Conduit / Duct Installation | 30 | Structural | Structural Crew | 2 | No
Structure & Early Works | Underground MEP / Embedded Services | 4 | Testing & Protection | 15 | Structural | Structural Crew | 1 | Yes
Structure & Early Works | Underground MEP / Embedded Services | 5 | Backfill & Compaction | 10 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Underground MEP / Embedded Services | 6 | As-built & Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Temporary Works | Tower Crane Installation | 1 | Foundation / Base Preparation | 20 | Temporary Works | Temporary Works / Crane Crew | 1 | No
Temporary Works | Tower Crane Installation | 2 | Crane Erection & Assembly | 35 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | Tower Crane Installation | 3 | Electrical Connection & Testing | 20 | Temporary Works | Temporary Works / Crane Crew | 1 | Yes
Temporary Works | Tower Crane Installation | 4 | Load Testing & Certification | 15 | Temporary Works | Temporary Works / Crane Crew | 1 | Yes
Temporary Works | Tower Crane Installation | 5 | Inspection & Handover | 10 | Temporary Works | Temporary Works / Crane Crew | 0.5 | Yes
Temporary Works | External Scaffolding | 1 | Foundation / Base Plates | 15 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | External Scaffolding | 2 | Scaffold Erection (Main Structure) | 40 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | External Scaffolding | 3 | Platforms, Guardrails & Access | 20 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | External Scaffolding | 4 | Ties, Bracing & Safety Netting | 15 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | External Scaffolding | 5 | Inspection & Tagging | 10 | Temporary Works | Temporary Works / Crane Crew | 0.5 | Yes
Temporary Works | Material Hoist / Loading Platform | 1 | Support Structure / Frame Installation | 25 | Temporary Works | Temporary Works / Crane Crew | 2 | No
Temporary Works | Material Hoist / Loading Platform | 2 | Hoist / Platform Assembly | 30 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | Material Hoist / Loading Platform | 3 | Electrical & Safety Devices | 20 | Temporary Works | Temporary Works / Crane Crew | 1.5 | No
Temporary Works | Material Hoist / Loading Platform | 4 | Load Test & Certification | 15 | Temporary Works | Temporary Works / Crane Crew | 1 | Yes
Temporary Works | Material Hoist / Loading Platform | 5 | Inspection & Handover | 10 | Temporary Works | Temporary Works / Crane Crew | 0.5 | Yes
Drywall & Special Partitions | Dry Wall Installation | 1 | Setting Out & Marking | 10 | Architectural | Drywall Crew | 1 | No
Drywall & Special Partitions | Dry Wall Installation | 2 | Track & Stud Framing | 25 | Architectural | Drywall Crew | 1.5 | No
Drywall & Special Partitions | Dry Wall Installation | 3 | Insulation / Acoustic Fill | 15 | Architectural | Drywall Crew | 1.5 | No
Drywall & Special Partitions | Dry Wall Installation | 4 | Board Fixing (both sides) | 25 | Architectural | Drywall Crew | 1.5 | No
Drywall & Special Partitions | Dry Wall Installation | 5 | Jointing, Taping & Skimming | 15 | Architectural | Plaster Crew | 1.5 | No
Drywall & Special Partitions | Dry Wall Installation | 6 | Inspection & Handover | 10 | Architectural | Drywall Crew | 0.5 | Yes
Drywall & Special Partitions | Toilet Cubicle / Partition | 1 | Setting Out & Floor Fixings | 15 | Architectural | Architectural Crew | 1 | No
Drywall & Special Partitions | Toilet Cubicle / Partition | 2 | Panel & Door Installation | 40 | Architectural | Joinery / Glazing Crew | 2 | No
Drywall & Special Partitions | Toilet Cubicle / Partition | 3 | Headrail, Fittings & Hardware | 25 | Architectural | Architectural Crew | 1.5 | No
Drywall & Special Partitions | Toilet Cubicle / Partition | 4 | Adjustment & Operation Test | 10 | Architectural | Architectural Crew | 1.5 | Yes
Drywall & Special Partitions | Toilet Cubicle / Partition | 5 | Inspection & Cleaning | 10 | Architectural | QA/QC | 0.5 | Yes
Drywall & Special Partitions | Fabric Wall / Acoustic Panel | 1 | Substrate Preparation | 15 | Architectural | Architectural Crew | 1 | No
Drywall & Special Partitions | Fabric Wall / Acoustic Panel | 2 | Frame / Batten Installation | 25 | Architectural | Joinery / Glazing Crew | 2 | No
Drywall & Special Partitions | Fabric Wall / Acoustic Panel | 3 | Acoustic Fill / Backing | 20 | Architectural | Architectural Crew | 1.5 | No
Drywall & Special Partitions | Fabric Wall / Acoustic Panel | 4 | Fabric / Panel Fixing | 30 | Architectural | Architectural Crew | 1.5 | No
Drywall & Special Partitions | Fabric Wall / Acoustic Panel | 5 | Inspection & Cleaning | 10 | Architectural | QA/QC | 0.5 | Yes
MEP Final Fix / Plant | AHU Installation | 1 | Positioning & Base Frame | 20 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | AHU Installation | 2 | Duct & Pipe Connections | 25 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | AHU Installation | 3 | Electrical & Control Wiring | 20 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | AHU Installation | 4 | Insulation & Cladding | 15 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | AHU Installation | 5 | Testing & Commissioning Checks | 15 | HVAC | QA/QC + HVAC Engineer | 1 | Yes
MEP Final Fix / Plant | AHU Installation | 6 | Inspection & Handover | 5 | HVAC | QA/QC + HVAC Engineer | 0.5 | Yes
MEP Final Fix / Plant | Busduct Works | 1 | Support & Hanger Installation | 15 | Electrical | Electrical Crew | 2 | No
MEP Final Fix / Plant | Busduct Works | 2 | Busduct Section Installation | 35 | Electrical | Electrical Crew | 2 | No
MEP Final Fix / Plant | Busduct Works | 3 | Jointing & Torqueing | 20 | Electrical | Electrical Crew | 1.5 | No
MEP Final Fix / Plant | Busduct Works | 4 | Earthing & Bonding | 10 | Electrical | Electrical Crew | 1.5 | No
MEP Final Fix / Plant | Busduct Works | 5 | Insulation Resistance Test | 15 | Electrical | QA/QC + Electrical Engineer | 1.5 | Yes
MEP Final Fix / Plant | Busduct Works | 6 | Inspection & Documentation | 5 | Electrical | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Final Fix / Plant | Fire Hose Reel Installation | 1 | Cabinet / Frame Positioning | 20 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Final Fix / Plant | Fire Hose Reel Installation | 2 | Hose Reel & Pipe Connection | 35 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Final Fix / Plant | Fire Hose Reel Installation | 3 | Valve, Nozzle & Accessories | 20 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Final Fix / Plant | Fire Hose Reel Installation | 4 | Pressure Test & Function Check | 15 | Fire Fighting | QA/QC + FF Engineer | 1 | Yes
MEP Final Fix / Plant | Fire Hose Reel Installation | 5 | Signage & Inspection | 10 | Fire Fighting | QA/QC + FF Engineer | 0.5 | Yes
MEP Final Fix / Plant | Fire Hydrant Installation | 1 | Hydrant Body Positioning | 20 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Final Fix / Plant | Fire Hydrant Installation | 2 | Pipe Connection & Valves | 30 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Final Fix / Plant | Fire Hydrant Installation | 3 | Backfill & Protection | 15 | Fire Fighting | Fire Fighting Crew | 1.5 | No
MEP Final Fix / Plant | Fire Hydrant Installation | 4 | Pressure Test & Flushing | 20 | Fire Fighting | QA/QC + FF Engineer | 1 | Yes
MEP Final Fix / Plant | Fire Hydrant Installation | 5 | Painting, Signage & Inspection | 15 | Fire Fighting | QA/QC + FF Engineer | 0.5 | Yes
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 1 | Foundation / Base Preparation | 15 | MEP Plant | MEP Plant Crew + Specialist | 1 | No
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 2 | Equipment Positioning & Alignment | 25 | MEP Plant | MEP Plant Crew + Specialist | 1.5 | No
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 3 | Pipe / Duct / Exhaust Connections | 20 | MEP Plant | MEP Plant Crew + Specialist | 1.5 | No
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 4 | Electrical & Control Connections | 20 | MEP Plant | MEP Plant Crew + Specialist | 1.5 | No
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 5 | Testing, Start-up & Commissioning | 15 | MEP Plant | MEP Plant Crew + Specialist | 1 | Yes
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 6 | Inspection & Handover | 5 | MEP Plant | MEP Plant Crew + Specialist | 0.5 | Yes
MEP Final Fix / Plant | Pumps & Tanks Installation | 1 | Base / Foundation Preparation | 15 | MEP Plant | MEP Plant Crew + Specialist | 1 | No
MEP Final Fix / Plant | Pumps & Tanks Installation | 2 | Equipment Positioning & Fixing | 25 | MEP Plant | MEP Plant Crew + Specialist | 1.5 | No
MEP Final Fix / Plant | Pumps & Tanks Installation | 3 | Pipework & Valve Connections | 25 | MEP Plant | MEP Plant Crew + Specialist | 1.5 | No
MEP Final Fix / Plant | Pumps & Tanks Installation | 4 | Electrical & Control Wiring | 15 | MEP Plant | MEP Plant Crew + Specialist | 1.5 | No
MEP Final Fix / Plant | Pumps & Tanks Installation | 5 | Testing & Commissioning | 15 | MEP Plant | MEP Plant Crew + Specialist | 1 | Yes
MEP Final Fix / Plant | Pumps & Tanks Installation | 6 | Inspection & Handover | 5 | MEP Plant | MEP Plant Crew + Specialist | 0.5 | Yes
MEP Final Fix / Plant | LV-MSB / Switchgear Installation | 1 | Positioning & Fixing | 20 | Electrical | Electrical Crew | 1.5 | No
MEP Final Fix / Plant | LV-MSB / Switchgear Installation | 2 | Busbar / Cable Termination | 30 | Electrical | Electrical Crew | 1.5 | No
MEP Final Fix / Plant | LV-MSB / Switchgear Installation | 3 | Internal Wiring & Labelling | 20 | Electrical | Electrical Crew | 1 | No
MEP Final Fix / Plant | LV-MSB / Switchgear Installation | 4 | Testing (IR, Continuity, Function) | 20 | Electrical | QA/QC + Electrical Engineer | 1 | Yes
MEP Final Fix / Plant | LV-MSB / Switchgear Installation | 5 | Inspection & Energisation Ready | 10 | Electrical | QA/QC + Electrical Engineer | 0.5 | Yes
MEP Final Fix / Plant | Diffuser / Grille / Louver Installation | 1 | Opening Preparation & Frame | 20 | HVAC | HVAC Crew | 1 | No
MEP Final Fix / Plant | Diffuser / Grille / Louver Installation | 2 | Device Fixing & Alignment | 40 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | Diffuser / Grille / Louver Installation | 3 | Connection to Duct / Flexible | 20 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | Diffuser / Grille / Louver Installation | 4 | Adjustment & Balancing Check | 10 | HVAC | HVAC Crew | 1.5 | No
MEP Final Fix / Plant | Diffuser / Grille / Louver Installation | 5 | Inspection & Cleaning | 10 | HVAC | QA/QC + HVAC Engineer | 0.5 | Yes
Architectural Finishes | Balustrade & Railings | 1 | Setting Out & Fixing Points | 15 | Architectural | Metalworks Crew | 1 | No
Architectural Finishes | Balustrade & Railings | 2 | Post / Frame Installation | 30 | Architectural | Joinery / Glazing Crew | 2 | No
Architectural Finishes | Balustrade & Railings | 3 | Handrail / Infill Installation | 30 | Architectural | Metalworks Crew | 2 | No
Architectural Finishes | Balustrade & Railings | 4 | Alignment, Welding / Fixing | 15 | Architectural | Metalworks Crew | 1.5 | No
Architectural Finishes | Balustrade & Railings | 5 | Finishing, Cleaning & Inspection | 10 | Architectural | Metalworks Crew | 0.5 | Yes
Architectural Finishes | Timber Floor / Carpet Installation | 1 | Substrate Preparation & Levelling | 20 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Timber Floor / Carpet Installation | 2 | Underlay / Moisture Barrier | 15 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Timber Floor / Carpet Installation | 3 | Flooring Installation | 40 | Architectural | Tiling / Flooring Crew | 2 | No
Architectural Finishes | Timber Floor / Carpet Installation | 4 | Finishing / Skirting / Edges | 15 | Architectural | Architectural Crew | 1.5 | No
Architectural Finishes | Timber Floor / Carpet Installation | 5 | Cleaning & Inspection | 10 | Architectural | QA/QC | 0.5 | Yes
Architectural Finishes | Wall & Soffit Skim Coat | 1 | Surface Preparation | 20 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Wall & Soffit Skim Coat | 2 | First Skim Coat Application | 30 | Architectural | Plaster Crew | 1.5 | No
Architectural Finishes | Wall & Soffit Skim Coat | 3 | Second Skim Coat & Sanding | 30 | Architectural | Plaster Crew | 1.5 | No
Architectural Finishes | Wall & Soffit Skim Coat | 4 | Final Touch-up & Cleaning | 10 | Architectural | Architectural Crew | 1 | No
Architectural Finishes | Wall & Soffit Skim Coat | 5 | Inspection | 10 | Architectural | QA/QC | 0.5 | Yes
External Works & Handover | Landscaping | 1 | Soil Preparation & Grading | 15 | External / Handover | Landscape Crew | 1 | No
External Works & Handover | Landscaping | 2 | Softscape (Trees, Shrubs, Grass) | 35 | External / Handover | Landscape Crew | 1.5 | No
External Works & Handover | Landscaping | 3 | Hardscape (Paving, Edging) | 25 | External / Handover | Landscape Crew | 1.5 | No
External Works & Handover | Landscaping | 4 | Irrigation System | 15 | External / Handover | Landscape Crew | 1.5 | No
External Works & Handover | Landscaping | 5 | Final Cleaning & Inspection | 10 | External / Handover | Landscape Crew | 0.5 | Yes
External Works & Handover | External Drainage | 1 | Setting Out & Excavation | 15 | External / Handover | External Works Crew | 1 | No
External Works & Handover | External Drainage | 2 | Pipe / Channel Installation | 30 | External / Handover | External Works Crew | 2 | No
External Works & Handover | External Drainage | 3 | Manholes / Catch Pits | 20 | External / Handover | External Works Crew | 1.5 | No
External Works & Handover | External Drainage | 4 | Backfill, Testing & Connection | 20 | External / Handover | External Works Crew | 1 | Yes
External Works & Handover | External Drainage | 5 | Cover, Surfacing & Inspection | 15 | External / Handover | QA/QC + PM Team | 0.5 | Yes
External Works & Handover | Permanent Fence / Boundary | 1 | Setting Out & Foundation | 20 | External / Handover | External Works Crew | 1 | No
External Works & Handover | Permanent Fence / Boundary | 2 | Post / Panel Installation | 35 | External / Handover | External Works Crew | 2 | No
External Works & Handover | Permanent Fence / Boundary | 3 | Gate Installation | 20 | External / Handover | External Works Crew | 2 | No
External Works & Handover | Permanent Fence / Boundary | 4 | Finishing & Hardware | 15 | External / Handover | External Works Crew | 1.5 | No
External Works & Handover | Permanent Fence / Boundary | 5 | Inspection & Handover | 10 | External / Handover | QA/QC + PM Team | 0.5 | Yes
External Works & Handover | Client Inspection & Taking Over | 1 | Internal Snagging & Rectification | 25 | External / Handover | QA/QC + PM Team | 1.5 | No
External Works & Handover | Client Inspection & Taking Over | 2 | External Snagging & Rectification | 20 | External / Handover | QA/QC + PM Team | 1.5 | No
External Works & Handover | Client Inspection & Taking Over | 3 | Client Inspection Walkthrough | 20 | External / Handover | QA/QC + PM Team | 0.5 | Yes
External Works & Handover | Client Inspection & Taking Over | 4 | Touch-up & Final Cleaning | 15 | External / Handover | QA/QC + PM Team | 1 | No
External Works & Handover | Client Inspection & Taking Over | 5 | Documentation & Taking Over Certificate | 20 | External / Handover | QA/QC + PM Team | 0.5 | Yes
Structure & Early Works | Pile Cap | 1 | Setting Out & Excavation | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Pile Cap | 2 | Blinding Concrete | 10 | Structural | Concrete Crew | 1.5 | No
Structure & Early Works | Pile Cap | 3 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Pile Cap | 4 | Formwork Installation | 20 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Pile Cap | 5 | Concrete Pouring | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Pile Cap | 6 | Curing & Formwork Removal | 10 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Pile Cap | 7 | Inspection & Handover | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Ground Beam | 1 | Setting Out & Excavation | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Ground Beam | 2 | Blinding (if required) | 5 | Structural | Civil / Survey Crew | 1.5 | No
Structure & Early Works | Ground Beam | 3 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Ground Beam | 4 | Formwork Installation | 20 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Ground Beam | 5 | Concrete Pouring | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Ground Beam | 6 | Curing & Formwork Removal | 15 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Ground Beam | 7 | Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Columns | 1 | Setting Out & Starter Bars Check | 10 | Structural | Rebar Crew | 1 | No
Structure & Early Works | Columns | 2 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Columns | 3 | Formwork Installation | 25 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Columns | 4 | Concrete Pouring | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Columns | 5 | Curing | 10 | Structural | Concrete Crew | 3 | No
Structure & Early Works | Columns | 6 | Formwork Removal & Inspection | 10 | Structural | Formwork Crew | 0.5 | Yes
Structure & Early Works | Shear Wall / Core Wall | 1 | Setting Out & Starter Bars | 10 | Structural | Rebar Crew | 1 | No
Structure & Early Works | Shear Wall / Core Wall | 2 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Shear Wall / Core Wall | 3 | Formwork / Jump Form Installation | 25 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Shear Wall / Core Wall | 4 | Concrete Pouring | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Shear Wall / Core Wall | 5 | Curing | 10 | Structural | Concrete Crew | 3 | No
Structure & Early Works | Shear Wall / Core Wall | 6 | Formwork Removal & Inspection | 10 | Structural | Formwork Crew | 0.5 | Yes
Structure & Early Works | Beams | 1 | Setting Out & Level Check | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Beams | 2 | Formwork Installation | 25 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Beams | 3 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Beams | 4 | MEP Embedded Items / Sleeves | 10 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Beams | 5 | Concrete Pouring | 15 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Beams | 6 | Curing & Formwork Removal | 10 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Beams | 7 | Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Slab | 1 | Setting Out & Level Check | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Slab | 2 | Formwork / Table Form Installation | 20 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Slab | 3 | Bottom Reinforcement | 15 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Slab | 4 | MEP Embedded Items / Sleeves / Conduits | 15 | Structural | Structural Crew | 1.5 | No
Structure & Early Works | Slab | 5 | Top Reinforcement | 15 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Slab | 6 | Concrete Pouring | 15 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Slab | 7 | Curing & Formwork Removal | 10 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Staircase | 1 | Setting Out & Level Check | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Staircase | 2 | Formwork Installation | 25 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Staircase | 3 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Staircase | 4 | Concrete Pouring | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Staircase | 5 | Curing & Formwork Removal | 15 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Staircase | 6 | Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Ramp | 1 | Setting Out & Gradient Check | 15 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Ramp | 2 | Formwork Installation | 20 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Ramp | 3 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Ramp | 4 | Concrete Pouring | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Ramp | 5 | Curing, Surface Finish & Formwork Removal | 15 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Ramp | 6 | Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Retaining Wall | 1 | Setting Out & Excavation | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Retaining Wall | 2 | Blinding / Base Preparation | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | Retaining Wall | 3 | Reinforcement Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Retaining Wall | 4 | Formwork Installation | 20 | Structural | Formwork Crew | 2 | No
Structure & Early Works | Retaining Wall | 5 | Concrete Pouring (in lifts if high) | 20 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Retaining Wall | 6 | Curing, Formwork Removal & Backfill Prep | 10 | Structural | Formwork Crew | 3 | No
Structure & Early Works | Retaining Wall | 7 | Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Diaphragm Wall | 1 | Guide Wall Construction | 15 | Structural | Piling Crew | 1.5 | No
Structure & Early Works | Diaphragm Wall | 2 | Trench Excavation under Bentonite | 25 | Structural | Civil / Survey Crew | 1.5 | No
Structure & Early Works | Diaphragm Wall | 3 | Reinforcement Cage Installation | 20 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Diaphragm Wall | 4 | Concrete Pouring (Tremie) | 25 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Diaphragm Wall | 5 | Panel Joint Cleaning & Inspection | 10 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Diaphragm Wall | 6 | As-built & Integrity Check | 5 | Structural | Piling Crew | 0.5 | Yes
Structure & Early Works | CBP / Secant Pile Wall | 1 | Setting Out & Guide Wall (if any) | 10 | Structural | Civil / Survey Crew | 1 | No
Structure & Early Works | CBP / Secant Pile Wall | 2 | Bored Pile Installation (Primary) | 30 | Structural | Piling Crew | 2 | No
Structure & Early Works | CBP / Secant Pile Wall | 3 | Bored Pile Installation (Secondary / Secant) | 25 | Structural | Piling Crew | 2 | No
Structure & Early Works | CBP / Secant Pile Wall | 4 | Pile Head Breaking & Capping Beam | 20 | Structural | Piling Crew | 1.5 | No
Structure & Early Works | CBP / Secant Pile Wall | 5 | Testing & Integrity Check | 10 | Structural | Piling Crew | 1 | Yes
Structure & Early Works | CBP / Secant Pile Wall | 6 | Inspection & Handover | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes
Structure & Early Works | Slab on Grade / Ground Slab | 1 | Subgrade Preparation & Compaction | 15 | Structural | Structural Crew | 1 | No
Structure & Early Works | Slab on Grade / Ground Slab | 2 | Blinding / Vapour Barrier | 10 | Structural | Civil / Survey Crew | 1.5 | No
Structure & Early Works | Slab on Grade / Ground Slab | 3 | Reinforcement / Mesh Fixing | 25 | Structural | Rebar Crew | 2 | No
Structure & Early Works | Slab on Grade / Ground Slab | 4 | Formwork / Edge Form | 10 | Structural | Formwork Crew | 1.5 | No
Structure & Early Works | Slab on Grade / Ground Slab | 5 | Concrete Pouring & Finishing | 25 | Structural | Concrete Crew | 1 | Yes
Structure & Early Works | Slab on Grade / Ground Slab | 6 | Curing & Joint Cutting | 10 | Structural | Concrete Crew | 3 | No
Structure & Early Works | Slab on Grade / Ground Slab | 7 | Inspection | 5 | Structural | QA/QC + Structural Engineer | 0.5 | Yes

## Template Index
Group | Template Name | No. of Steps | Total Weight | Recommended Use
Architectural Finishes | Blockwork / Masonry – Typical Floor | 6 | 100 | GF–7F Blockwork activity
Architectural Finishes | Internal Partition – Typical Floor | 6 | 100 | GF–7F Internal Partition
Architectural Finishes | Plastering (Internal) – Typical Floor | 6 | 100 | GF–7F Plastering
Architectural Finishes | Waterproofing (Wet Areas) – Typical Floor | 6 | 100 | Wet areas only
Architectural Finishes | Screed – Typical Floor | 6 | 100 | GF–7F Screed
Architectural Finishes | Ceiling – Typical Floor | 5 | 100 | GF–7F Ceiling
Architectural Finishes | Flooring – Typical Floor | 6 | 100 | GF–7F Flooring
Architectural Finishes | Wall Tiling – Typical Floor | 6 | 100 | GF–7F Wall Tiling
Architectural Finishes | Stone / Marble – Typical Floor | 6 | 100 | Stone / Marble areas
Architectural Finishes | Internal Painting – Typical Floor | 6 | 100 | GF–7F Internal Painting
Architectural Finishes | Door Frames – Typical Floor | 4 | 100 | GF–7F Door Frames
Architectural Finishes | Doors (Leaf + Ironmongery) – Typical Floor | 5 | 100 | GF–7F Doors
Architectural Finishes | Windows / Glazing – Typical Floor | 5 | 100 | GF–7F Windows / Glass
MEP First Fix | Electrical Conduits – Typical Floor | 6 | 100 | GF–7F Electrical Conduits
MEP First Fix | Cable Trays – Typical Floor | 6 | 100 | GF–7F Cable Trays
MEP First Fix | Plumbing Pipes – Typical Floor | 6 | 100 | GF–7F Plumbing Pipes
MEP First Fix | Drainage Pipes – Typical Floor | 6 | 100 | GF–7F Drainage Pipes
MEP First Fix | HVAC Ductwork – Typical Floor | 6 | 100 | GF–7F HVAC Ductwork
MEP First Fix | HVAC Pipes – Typical Floor | 6 | 100 | GF–7F HVAC Pipes
MEP First Fix | Fire Fighting Pipes – Typical Floor | 6 | 100 | GF–7F Fire Fighting Pipes
MEP First Fix | Fire Alarm Conduits – Typical Floor | 6 | 100 | GF–7F Fire Alarm Conduits
MEP First Fix | ELV Conduits – Typical Floor | 6 | 100 | GF–7F ELV Conduits
MEP Second Fix | Cable Pulling – Typical Floor | 5 | 100 | GF–7F Cable Pulling
MEP Second Fix | DB Installation – Typical Floor | 5 | 100 | GF–7F DB Installation
MEP Second Fix | Lighting Installation – Typical Floor | 5 | 100 | GF–7F Lighting
MEP Second Fix | Switches & Sockets – Typical Floor | 5 | 100 | GF–7F Switches & Sockets
MEP Second Fix | Plumbing Fixtures – Typical Floor | 5 | 100 | GF–7F Plumbing Fixtures
MEP Second Fix | HVAC Equipment – Typical Floor | 5 | 100 | GF–7F HVAC Equipment
MEP Second Fix | Fire Alarm Devices – Typical Floor | 5 | 100 | GF–7F Fire Alarm Devices
MEP Second Fix | Sprinkler Heads – Typical Floor | 5 | 100 | GF–7F Sprinkler Heads
MEP Second Fix | Fire Fighting Equipment – Typical Floor | 5 | 100 | GF–7F Fire Fighting Equipment
MEP Second Fix | ELV Devices – Typical Floor | 5 | 100 | GF–7F ELV Devices
Structure & Early Works | Site Preparation | 6 | 100 | Early works – site establishment
Structure & Early Works | Anti-Termite Treatment | 6 | 100 | Before / during foundation
Structure & Early Works | Piling Works | 6 | 100 | Piling + testing + rectification
Structure & Early Works | Substructure Works | 6 | 100 | Pile cap, raft, ground beam, SOG
Structure & Early Works | Underground MEP / Embedded Services | 6 | 100 | Below ground MEP & services
Temporary Works | Tower Crane Installation | 5 | 100 | Temporary crane setup
Temporary Works | External Scaffolding | 5 | 100 | External access scaffolding
Temporary Works | Material Hoist / Loading Platform | 5 | 100 | Vertical material handling
Drywall & Special Partitions | Dry Wall Installation | 6 | 100 | Gypsum / drywall partitions
Drywall & Special Partitions | Toilet Cubicle / Partition | 5 | 100 | Toilet cubicles
Drywall & Special Partitions | Fabric Wall / Acoustic Panel | 5 | 100 | Acoustic fabric walls
MEP Final Fix / Plant | AHU Installation | 6 | 100 | Air Handling Units
MEP Final Fix / Plant | Busduct Works | 6 | 100 | Busduct installation
MEP Final Fix / Plant | Fire Hose Reel Installation | 5 | 100 | Fire hose reels
MEP Final Fix / Plant | Fire Hydrant Installation | 5 | 100 | External / internal hydrants
MEP Final Fix / Plant | Major Plant Equipment (Chiller / Cooling Tower / Genset) | 6 | 100 | Chiller, CT, Genset etc.
MEP Final Fix / Plant | Pumps & Tanks Installation | 6 | 100 | Transfer, booster, submersible, tanks
MEP Final Fix / Plant | LV-MSB / Switchgear Installation | 5 | 100 | Main switchboards
MEP Final Fix / Plant | Diffuser / Grille / Louver Installation | 5 | 100 | Air terminals & louvers
Architectural Finishes | Balustrade & Railings | 5 | 100 | Stair / balcony balustrades
Architectural Finishes | Timber Floor / Carpet Installation | 5 | 100 | Timber or carpet flooring
Architectural Finishes | Wall & Soffit Skim Coat | 5 | 100 | Skim coat before paint
External Works & Handover | Landscaping | 5 | 100 | Soft & hard landscape
External Works & Handover | External Drainage | 5 | 100 | Stormwater / external drainage
External Works & Handover | Permanent Fence / Boundary | 5 | 100 | Boundary wall / fence / gate
External Works & Handover | Client Inspection & Taking Over | 5 | 100 | Final inspection & handover
Structure & Early Works | Pile Cap | 7 | 100 | Pile cap construction
Structure & Early Works | Ground Beam | 7 | 100 | Ground beam
Structure & Early Works | Columns | 6 | 100 | Typical floor / basement columns
Structure & Early Works | Shear Wall / Core Wall | 6 | 100 | Shear walls & core walls
Structure & Early Works | Beams | 7 | 100 | Beam formwork + rebar + concrete
Structure & Early Works | Slab | 7 | 100 | Typical floor slab cycle
Structure & Early Works | Staircase | 6 | 100 | Structural staircase
Structure & Early Works | Ramp | 6 | 100 | Vehicle / access ramp
Structure & Early Works | Retaining Wall | 7 | 100 | Basement / site retaining wall
Structure & Early Works | Diaphragm Wall | 6 | 100 | Diaphragm wall panels
Structure & Early Works | CBP / Secant Pile Wall | 6 | 100 | Contiguous / secant bored pile wall
Structure & Early Works | Slab on Grade / Ground Slab | 7 | 100 | Ground floor slab on grade

## How to Use in P6
HOW TO USE THESE ACTIVITY STEP TEMPLATES IN PRIMAVERA P6
1. Create Templates | Enterprise → Activity Step Templates → Add
Create one template for each name listed in the 'Template Index' sheet.
Copy the Step Name and Weight exactly from the 'All Step Templates' sheet.
2. Assign to Activities | Open the activity (e.g. Ceiling – GF) → Steps tab → Assign
Select the matching template and click Assign.
Repeat for every floor (GF to 7F).
3. Progress Update | When updating progress, open the activity → Steps tab.
Mark completed steps (or enter Step % Complete).
P6 automatically calculates Physical % Complete of the activity.
4. Best Practice | Keep the Master Schedule Activity as the single bar on the Gantt chart.
Use Steps only for progress measurement and detailed control.
For daily/weekly field control, still use Last Planner / Weekly Work Plans.
Notes | All weights total 100 for easy percentage reading.
You can adjust weights later if your actual work proportions differ.
Templates can be assigned to multiple activities (all floors).
New Groups Added (from site activity lists):
Structure & Early Works, Temporary Works, Drywall & Special Partitions, MEP Final Fix / Plant, External Works & Handover
Existing templates (Architectural, MEP First Fix, MEP Second Fix) were kept unchanged.
ENHANCED FIELDS (added):
Discipline ¦ Resource / Crew ¦ Est. Duration (Days) ¦ Inspection Hold Point
These fields support better progress control, look-ahead planning and QA hold-point tracking.
In Primavera: map Weight + Step Name to native Steps. Map Discipline, Resource, Duration, Hold Point to User Defined Fields (UDFs) if required.