DIGITAL CONSTRUCTION OPERATING SYSTEM

DCOS

STANDARD OPERATING PROCEDURE

Work Breakdown Structure (WBS)

Management, Governance & Control

| Document Control |  |
| --- | --- |
| Document No. | DCOS-SOP-WBS-001 |
| Version | 2.0 — Comprehensive Issue |
| Status | Approved |
| Document Owner | PMO Manager |
| Classification | Internal — Controlled Document |
| Applies To | All DCOS Projects & Disciplines |
| Supersedes | DCOS-SOP-WBS-001 R1.0 |
| Effective Date | On approval (see Revision History) |

About this procedure This SOP defines how the Work Breakdown Structure (WBS) — the structural spine of DCOS — is created, coded, approved, maintained, secured, and retired across the full project lifecycle. Every operational record in the platform (task, document, cost, material, inspection, incident) must resolve to a controlled WBS location. This document is the single authority for WBS practice and overrides any local or module-specific convention.

# Revision History

| Ver. | Date | Author | Summary of Change | Approved By |
| --- | --- | --- | --- | --- |
| 1.0 | — | PMO | Initial approved baseline SOP for WBS management. | PMO Manager |
| 2.0 | May 2026 | System Architect / PMO | Comprehensive rewrite: added definitions, RACI, coding standard, state model, change control, integration rules, worked roll-up examples, security matrix, data model and API alignment, governance and non-conformance register. | PMO Manager |

## Approval

| Role | Name | Responsibility | Signature / Date |
| --- | --- | --- | --- |
| Prepared By | System Architect | Authored procedure content |  |
| Reviewed By | Project Director | Technical & governance review |  |
| Approved By | PMO Manager | Document owner — final approval |  |

# Table of Contents

Revision History	2

Table of Contents	3

1.  Purpose	4

2.  Scope	4

3.  Definitions & Terminology	4

4.  References & Related Documents	5

5.  Roles & Responsibilities	5

6.  WBS Philosophy & Governing Principles	6

7.  WBS Hierarchy & Standard Structure	7

8.  WBS Coding Standard & Numbering Convention	8

9.  WBS Node Attributes & Assignment	9

10.  WBS Creation Workflow	10

11.  WBS Template Management	11

12.  WBS Status Lifecycle	12

13.  WBS Activation Rules	12

14.  WBS Modification & Change Control	13

15.  WBS Closure Procedure	13

16.  WBS Archiving & Retention	14

17.  Cross-Module Dependency & Integration Rules	14

18.  Progress Measurement & Roll-Up	15

19.  WBS Security & Access Control	16

20.  WBS Notifications	16

21.  WBS Audit Requirements	16

22.  WBS Dashboard & KPIs	17

23.  Data Model	18

24.  API Endpoints	18

25.  Definition of Done	19

26.  Common Mistakes & Non-Conformances	19

27.  Governance Rules	20

28.  Future Enhancements	20

Appendix A — End-to-End Worked Example	21

29.  Final Statement	21

# 1. Purpose

This procedure establishes the standard, mandatory process for creating, coding, approving, maintaining, governing, and retiring the Work Breakdown Structure (WBS) within the Digital Construction Operating System (DCOS).

In DCOS, the WBS is not a planning artefact that lives only in the scheduling module — it is the primary location and control structure of the entire platform. Every task, document, cost record, material movement, inspection, and safety event is anchored to a WBS node. A disciplined WBS is therefore the precondition for reliable progress measurement, cost control, traceability, and reporting.

## 1.1 Objectives of this Procedure

- Standardize how projects are decomposed into controllable, reportable parts.

- Guarantee that every operational record carries a valid, unique WBS reference.

- Define unambiguous ownership, approval, and change-control for the structure.

- Enable consistent progress and cost roll-up from task level to project level.

- Provide an auditable, append-only history of every structural change.

- Protect data integrity by preventing deletion or re-coding of nodes that carry live records.

# 2. Scope

This SOP applies to all projects managed in DCOS, across all project types and all disciplines, and to all users who create, approve, consume, or report against WBS data.

## 2.1 Project Types in Scope

| Project Type | Typical WBS Emphasis |
| --- | --- |
| Building Projects (towers, offices, residential) | Building → Level → Zone → Room → Element |
| Infrastructure Projects (roads, bridges, utilities) | Section / Chainage → Structure → Element |
| Industrial / Factory Projects | Area → System → Equipment → Element |
| Design-Only / Consultancy Projects | Discipline → Deliverable Package → Drawing Set |
| Maintenance Projects | Asset → System → Component → Work Order |
| Internal / Company Projects | Phase → Workstream → Deliverable |

Mandatory linkage rule All operational records must be linked to a WBS node. No task, document, cost, material, inspection, or incident may exist in DCOS without a valid WBS reference. This rule is enforced by the platform and is non-negotiable.

# 3. Definitions & Terminology

The following terms are used consistently throughout DCOS documentation and this procedure.

| Term | Definition |
| --- | --- |
| WBS | Work Breakdown Structure — the hierarchical, location-based decomposition of a project into controllable nodes. |
| WBS Node | A single element in the hierarchy (e.g. a Building, Level, Zone, Room, or Element). |
| Node Type | The classification of a node — Project, Building, Level, Zone, Room, Element, or Task group. |
| Parent / Child | The hierarchical relationship between a node and the nodes immediately above (parent) or below (children) it. |
| WBS Code | The human-readable identifier assigned to a node, unique within its project. |
| Full Path | The concatenated chain of codes from project root to the node (the breadcrumb). |
| Roll-Up | The automatic aggregation of progress (and cost) from child nodes up to parent nodes. |
| Leaf Node | A node with no children — typically the level at which tasks attach. |
| Dynamic Depth | The principle that the hierarchy may have more or fewer levels per project, as the work requires. |
| Active Node | A node in a state that permits new operational records to be created against it. |
| Controlled Document | A version-managed document governed under DCOS document control. |

# 4. References & Related Documents

This SOP should be read together with the following DCOS architecture and governance documents.

| Reference | Document | Relevance |
| --- | --- | --- |
| DCOS-ARCH-001 | System Architecture & Module Design | Defines WBS as the system spine and the modular platform design. |
| DCOS-ARCH-GAP-001 | Architecture Gap Analysis & Improvement Report | Confirms preservation of the WBS philosophy and roll-up direction. |
| DCOS-SOP-DOC-001 | Document Control SOP | Governs document numbering that embeds WBS codes. |
| DCOS-SOP-TASK-001 | Task Management SOP | Defines task lifecycle attached to leaf WBS nodes. |
| DCOS Audit & Notification Engines | Core platform engines | Provide audit logging and notification used by this SOP. |

# 5. Roles & Responsibilities

WBS governance is shared across defined roles. Each role has a specific accountability boundary; no single user both designs and unilaterally approves a structure.

## 5.1 Role Definitions

| Role | WBS Responsibility |
| --- | --- |
| PMO Manager | Owns the WBS standard and templates. Governs naming, coding, depth rules, and cross-project consistency. Custodian of this SOP. |
| Project Manager | Approves and activates the project WBS. Authorizes restricted structural changes during execution. |
| Discipline / Department Managers | Review the structure for their discipline. Confirm node ownership and discipline tagging are correct. |
| WBS Coordinator | Performs day-to-day WBS maintenance: creating approved nodes, updating descriptions, applying approved changes. |
| Engineers / Site Staff | Consume the WBS — they attach tasks, documents, and records to nodes but cannot alter the structure. |
| Administrator | Holds the technical delete permission, used only via the controlled deletion path with audit and approval. |

## 5.2 RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity | PMO | PM | Disc. Mgr | WBS Coord. | Admin |
| --- | --- | --- | --- | --- | --- |
| Define WBS standard & templates | A/R | C | C | I | I |
| Create project WBS structure | C | A | C | R | I |
| Review structure before approval | C | A | R | C | I |
| Approve & activate WBS | I | A/R | C | I | I |
| Routine maintenance (descriptions, add nodes) | I | A | C | R | I |
| Restricted change (move / recode active node) | C | A/R | C | R | C |
| Close WBS node | I | A | C | R | I |
| Delete node (controlled path only) | C | A | I | C | R |
| Archive WBS at project closure | A | R | I | C | C |

# 6. WBS Philosophy & Governing Principles

## 6.1 Core Principle — Everything Belongs to a Location

The founding principle of DCOS is simple: every operational record belongs to a location in the WBS. Before any record is created, it must be able to answer the five control questions.

| # | Control Question | Resolved By |
| --- | --- | --- |
| 1 | Which project? | Project node |
| 2 | Which WBS location? | Building / Level / Zone / Room / Element node |
| 3 | Which discipline? | Discipline tag on the node or record |
| 4 | Which responsible party? | Node owner / assignment |
| 5 | What status? | Node and record status |

## 6.2 Governing Principles

- Single spine. The WBS is the one structure all modules consume. Modules must never create independent, parallel location structures.

- Dynamic depth. The hierarchy adapts to the project. A factory, a tower, a road, and a hospital will not share the same shape — the structure must flex without breaking the rules.

- Roll-up upward only. Progress and cost aggregate from child to parent. A parent's value is always derived, never entered directly.

- Uniqueness within project. Every WBS code is unique inside its project, which protects document numbering and reporting integrity.

- Integrity over convenience. A node that carries live records is protected — it cannot be deleted or silently re-coded.

- Auditability. Every structural action is logged in an append-only audit trail.

Preserve these decisions (per Architecture Gap Analysis) WBS as the single spine connecting all modules — do not change this. Dynamic hierarchy depth (not fixed levels) — essential for mixed project types. Progress and cost roll-up from child to parent — correct calculation direction. WBS code uniqueness within project — critical for document numbering integrity.

# 7. WBS Hierarchy & Standard Structure

## 7.1 DCOS Standard Hierarchy

The standard DCOS building-project hierarchy is seven primary levels. Optional Phase and Discipline nodes may be inserted on complex programmes where dynamic depth is required (see 7.3).

Project (Level 0) e.g. GDT Office Tower └─ Building (Level 1) e.g. Tower A, Podium, Basement └─ Level (Level 2) e.g. B2, B1, L01 … L29, RF └─ Zone (Level 3) e.g. ZA, ZB, ZC, ZD └─ Room (Level 4) e.g. Lobby, Office, MEP Room └─ Element (Level 5) e.g. Column, Wall, Slab └─ Task (Level 6) e.g. Install Rebar, Cast Concrete

## 7.2 Level Reference

| Level | Node Type | Purpose | Examples |
| --- | --- | --- | --- |
| 0 | Project | Top-level container; the contract / job | GDT Office Tower |
| 1 | Building / Area | Major physical or contractual division | Tower A, Podium, Basement, External Works |
| 2 | Level | Floor or vertical division | B2, B1, L01, L02, L29, RF |
| 3 | Zone | Horizontal sub-division of a level | ZA, ZB, ZC, ZD |
| 4 | Room / Space | Functional space within a zone | Meeting Room, Office, Lobby, Toilet, MEP Room |
| 5 | Element | Physical work element within a space | Column, Wall, Beam, Slab, Door, Ceiling |
| 6 | Task | Executable unit of work on an element | Install Rebar, Review Shop Drawing, Cast Concrete |

## 7.3 Dynamic Depth & Optional Nodes

Not every project uses every level, and some require additional intermediate levels. The hierarchy supports this through dynamic depth.

- Skip levels where they do not apply. A small fit-out may go Project → Building → Room → Element, with no Zone.

- Insert Phase and Discipline nodes. Large programmes may use Project → Phase → Discipline → Building … to separate design, construction, and commissioning, or to ring-fence disciplines.

- Never skip a level merely for speed. Skipping Zone on a multi-zone floor is a common, reportable mistake (see Section 25).

Rule: discipline is a tag, not a level (default) By default, discipline is recorded as an attribute on the node and on the element code (STR/ARC/MEP), not as a structural level. A dedicated Discipline level is permitted only on large programmes where the PMO has approved it in the project template. Do not mix disciplines into the physical hierarchy ad hoc.

# 8. WBS Coding Standard & Numbering Convention

Consistent coding is what makes WBS data sortable, searchable, and reliable for document numbering. The following formats are mandatory.

## 8.1 Node Code Formats

| Level | Format | Examples | Notes |
| --- | --- | --- | --- |
| Project | PRJ-YYYY-NNN | PRJ-2026-001 | Year + sequence; assigned at project creation |
| Building | BLD-XX | BLD-TA, BLD-PD, BLD-BSM | Short building mnemonic |
| Level | Lnn / Bn / RF | L01, L05, B1, RF | L = above ground, B = basement, RF = roof |
| Zone | ZX | ZA, ZB, ZC, ZD | Single zone letter |
| Room | RM-XXXX | RM-MEETING01, RM-LOBBY01 | Functional name + sequence |
| Element | DSC-NNN | STR-001, ARC-001, MEP-001 | Discipline prefix + sequence |

## 8.2 Full Path / Numbering Example

The full path concatenates each level's code, providing a unique breadcrumb and the basis for document numbers.

PRJ-2026-001 │ └─ BLD-TA │ └─ L05 │ └─ ZA │ └─ RM-MEETING01 │ └─ STR-004

Resolved full path:

PRJ-2026-001 · BLD-TA · L05 · ZA · RM-MEETING01 · STR-004

## 8.3 Coding Rules

- WBS codes must be unique within a project. The platform rejects duplicates.

- Codes use uppercase letters, digits, and hyphens only — no spaces or special characters.

- Manual code entry is the standard; auto-generation may be enabled later via configuration.

- Element codes always carry a discipline prefix (STR / ARC / MEP / CIV …).

- Once a node is Active and carries records, its code is locked (see Change Control).

# 9. WBS Node Attributes & Assignment

## 9.1 Core Node Attributes

| Attribute | Description |
| --- | --- |
| wbs_code | Unique code within the project |
| wbs_name | Human-readable node name |
| wbs_type / node_type | Building, Level, Zone, Room, Element, Task group |
| parent_id | Reference to the parent node (null for project root) |
| full_path | Concatenated breadcrumb path |
| discipline | STR / ARC / MEP / CIV / multi (tag) |
| owner | Responsible team or individual |
| status | Draft, Active, On Hold, Closed, Archived |
| sort_order | Display order among siblings |
| progress_percent | Rolled-up progress (derived for parents) |

## 9.2 Assignment Rules

Every node may carry an owner, discipline, department, and manager. Assignment drives accountability, notification routing, and security filtering.

Node: L05 Owner: Structural Team Discipline: STR Manager: Discipline Manager (Structures)

Assignment cascades, but can be overridden A child node inherits the owner and discipline of its parent unless explicitly overridden. This keeps setup fast while allowing a single room or element to be reassigned to another team without breaking the parent's defaults.

# 10. WBS Creation Workflow

A new WBS is built top-down, reviewed, approved, and then activated. Records cannot be attached until the structure is Active.

Create Project ↓ Create Building(s) ↓ Create Level(s) ↓ Create Zone(s) ↓ Create Room(s) ↓ Create Element(s) ↓ Review (Discipline Managers) ↓ Approve (Project Manager) ↓ Activate → structure open for operations

## 10.1 Step Detail

| Step | Performed By | Outcome |
| --- | --- | --- |
| Create structure (top-down) | WBS Coordinator | Draft nodes with codes, names, owners |
| Verify codes & depth | WBS Coordinator | No duplicates; correct level usage |
| Discipline review | Discipline Managers | Confirm discipline tagging & ownership |
| Approval | Project Manager | Structure approved for activation |
| Activation | Project Manager | Status → Active; records may be attached |

# 11. WBS Template Management

To avoid rebuilding common structures repeatedly, DCOS maintains standard WBS templates governed by the PMO.

## 11.1 Standard Templates

| Template | Typical Use |
| --- | --- |
| High-Rise Building | Multi-level towers with repeating floors and zones |
| Residential Tower | Residential units with standardized room layouts |
| Factory / Industrial | Area- and system-based decomposition |
| Hospital | Department-driven layout with strict MEP zoning |
| Infrastructure | Chainage / section-based decomposition |

## 11.2 Clone Workflow

Select Template ↓ Select Target Project ↓ Clone Structure ↓ Adjust (rename, add/remove nodes) ↓ Review & Approve ↓ Activate

Template governance Templates are PMO-controlled master data. Project teams may clone and adjust a template for their project but may not edit the master template. Proposed template improvements are routed to the PMO Manager.

# 12. WBS Status Lifecycle

Each WBS node moves through a defined set of states. State controls whether records can be created against the node.

| Status | Meaning | Records Allowed? |
| --- | --- | --- |
| Draft | Node is being set up; not yet approved | No |
| Active | Approved and open for operations | Yes |
| On Hold | Temporarily suspended (e.g. design freeze) | Restricted |
| Closed | Work complete; no new records permitted | No |
| Archived | Historical reference only | No (read-only) |

## 12.1 State Transition Diagram

Draft ──approve & activate──▶ Active Active ──suspend──▶ On Hold ──resume──▶ Active Active ──complete & approve──▶ Closed Closed ──reopen (PM approval)──▶ Active Closed ──project closure──▶ Archived

Transition control Only the Project Manager may approve Active → Closed and Closed → Active (reopen). Reopening a Closed node always generates a high-severity audit entry and a notification to the PMO.

# 13. WBS Activation Rules

A WBS may only be activated when the following preconditions are satisfied. Activation is approved by the Project Manager.

| # | Activation Precondition | Verified By |
| --- | --- | --- |
| 1 | Parent project is Active | WBS Coordinator |
| 2 | Stakeholders assigned to the project | Project Manager |
| 3 | Project team assigned | Project Manager |
| 4 | Structure reviewed and verified (no duplicate codes, correct depth) | Discipline Managers |
| 5 | Owners assigned to nodes | WBS Coordinator |

# 14. WBS Modification & Change Control

Once a WBS is Active, structural changes are controlled. The platform distinguishes between freely allowed changes and restricted changes that require approval.

## 14.1 Allowed vs Restricted Changes

| Change | Classification | Approval |
| --- | --- | --- |
| Edit node description / name | Allowed | None (logged) |
| Change node owner / assignment | Allowed | None (logged + notify) |
| Add new child nodes | Allowed | None (logged) |
| Move a historical node (with records) | Restricted | Project Manager |
| Change an active WBS code | Restricted | Project Manager |
| Delete an existing node | Restricted | Administrator + PM |

## 14.2 Change Control Workflow (Restricted Changes)

Raise change request (reason mandatory) ↓ Impact check (linked records?) ↓ Project Manager review & approval ↓ Apply change ↓ Audit log (before/after) + notify affected owners

Integrity guard A node that has linked records (tasks, documents, costs, inspections) must not be deleted. If the work is genuinely cancelled, the node is Closed or Cancelled, never deleted — this preserves history and the audit trail.

# 15. WBS Closure Procedure

A WBS node may be closed only when all work and records under it are complete.

## 15.1 Closure Preconditions

- All tasks under the node are Closed.

- All inspections are closed/passed.

- All documents under the node are complete and issued.

- Rolled-up progress is 100%.

## 15.2 Closure Workflow

Review (WBS Coordinator) ↓ Approval (Project Manager) ↓ Close → node read-only, no new records

# 16. WBS Archiving & Retention

At project closure, the WBS and its linked records are archived. Archived structures remain available for historical reporting, claims, and lessons-learned but accept no new records.

| Data | Active Retention | Archive |
| --- | --- | --- |
| Active project WBS | Project duration + 2 years | Hot storage |
| Completed project WBS | 2 years post-completion | Warm storage, 10 years |
| WBS audit logs | Active | 7 years minimum |
| WBS-linked drawing references | Project + 5 years | Cold storage, 15 years |

Archiving rule Archiving never deletes audit history. Deleting a business record does not delete its audit entries, and a node snapshot is retained even where a controlled deletion has occurred.

# 17. Cross-Module Dependency & Integration Rules

Every module consumes the WBS from the central WBS Engine. Modules must not build their own location structures. The relationship is always module-record → WBS node.

| Module | Record Linked to WBS | Why |
| --- | --- | --- |
| Task Management | Task → WBS node | Location and progress source of truth |
| Document Control | Document → WBS node | Drives document numbering & filtering |
| Procurement | Material / PR / PO → WBS node | Budget commitment per location |
| Inventory / Stock | Material issue → WBS node | Consumption allocated to location |
| QA/QC | Inspection → WBS node | Quality records traceable to location |
| HSE | Incident → WBS node | Safety events located precisely |
| Cost Control | Cost → WBS node | Cost roll-up per location |
| Planning | Schedule activity → WBS node | Schedule-to-location alignment |

Governance: one structure only No module may create an independent location or area structure. All modules consume WBS from the centralized WBS Engine. This is the rule that makes DCOS an operating system rather than a collection of disconnected tools.

# 18. Progress Measurement & Roll-Up

Progress is entered only at the leaf (task) level. The system aggregates upward automatically; parent nodes never accept directly entered progress.

## 18.1 Roll-Up Direction

Task → Element → Room → Zone → Level → Building → Project

## 18.2 Worked Example — Simple Average

With equal weighting, an element's progress is the average of its tasks:

| Task | Progress |
| --- | --- |
| Task A | 100% |
| Task B | 50% |
| Task C | 0% |
| Element progress = (100 + 50 + 0) / 3 | 50% |

## 18.3 Weighted Roll-Up (Recommended for Cost-Loaded WBS)

Simple averaging treats a large structural slab and a single door as equal. Where nodes carry value or quantity weight, DCOS uses weighted roll-up so a parent reflects true physical progress.

| Task | Weight | Progress | Weighted |
| --- | --- | --- | --- |
| Slab pour | 70 | 100% | 70.0 |
| Door install | 10 | 0% | 0.0 |
| Wall finish | 20 | 50% | 10.0 |
| Weighted progress = (70 + 0 + 10) / 100 | 100 |  | 80% |

Roll-up rules Progress is entered at leaf level only; parents are always derived. Default method is simple average; weighted roll-up applies where nodes carry weight or value. Roll-up recalculates automatically whenever a child task progress changes.

# 19. WBS Security & Access Control

WBS access follows role-based permissions combined with project assignment. The effective permission is the intersection of role, project access, and discipline scope.

## 19.1 Permission Matrix

| Action | Permitted Role |
| --- | --- |
| View | All assigned project users |
| Create | WBS Manager / WBS Coordinator |
| Edit | WBS Manager / WBS Coordinator |
| Approve | Project Manager |
| Delete | Administrator (controlled path only) |

## 19.2 Effective Permission Formula

Effective access = Role permission ∩ Project access ∩ Discipline scope

Multi-tenant isolation All WBS data is tenant-scoped. Row-level security ensures a user from one company can never view another company's WBS, even accidentally. Tenant identity is taken from the authenticated session, never from request input.

# 20. WBS Notifications

The Notification Engine alerts the right people when significant WBS events occur. Notifications are routed by recipient strategy (owner, project role, discipline).

| Event | Notify | Channel | Priority |
| --- | --- | --- | --- |
| WBS activated | Project team, Discipline Managers | In-App, Email | Normal |
| WBS closed | Owner, Project Manager | In-App | Normal |
| Progress delayed | Owner, Discipline Manager, PM | In-App, Telegram | High |
| Owner changed | Old owner, new owner, PM | In-App, Email | Normal |
| Active code / structure changed | PM, PMO | In-App, Email | High |

# 21. WBS Audit Requirements

Every structural action is recorded in the append-only Audit Trail Engine. Audit logs cannot be edited or deleted by any user, including administrators.

## 21.1 Logged Actions

- Create WBS node

- Edit WBS node (description, owner, attributes)

- Activate WBS node

- Close / reopen WBS node

- Assign or change owner

- Change structure (move / recode / controlled delete)

## 21.2 Audit Record Fields

| Field | Description |
| --- | --- |
| user_id / user_name_snapshot | Who performed the action (and their name at the time) |
| action_type | CREATE, UPDATE, ACTIVATE, CLOSE, REOPEN, DELETE, ASSIGN |
| entity_id | Affected WBS node |
| old_values / new_values | Before/after state for changes |
| status_from / status_to | State transition, where applicable |
| comment / reason_code | Mandatory for restricted changes |
| severity | LOW / MEDIUM / HIGH / CRITICAL |
| created_at | Timestamp of the event |

Append-only Audit logs are append-only. Normal users cannot edit them; administrators cannot modify history (only archive/export per permission). Deleting a WBS node never deletes its audit entries.

# 22. WBS Dashboard & KPIs

## 22.1 Dashboard Views

| Audience | Dashboard Content |
| --- | --- |
| Project Manager | Building progress, level progress, delayed areas, critical areas |
| Executive / Director | Project completion, portfolio progress, project health score |
| Discipline Manager | Discipline workload by node, deliverable status |

## 22.2 WBS KPIs

| KPI | What It Measures |
| --- | --- |
| Active WBS count | Nodes currently open for operations |
| Closed WBS count | Completed nodes |
| Delayed WBS count | Nodes behind planned progress |
| Progress % | Rolled-up completion per node / project |
| Open tasks per node | Outstanding work at each location |

# 23. Data Model

The WBS Engine is backed by the following core tables. Field lists are indicative and align with the DCOS database design.

## 23.1 wbs_nodes

| Field | Type | Description |
| --- | --- | --- |
| id | uuid | Unique node ID |
| tenant_id | uuid | Company / tenant scope |
| project_id | uuid | Owning project |
| parent_id | uuid (nullable) | Parent node (null = project root) |
| wbs_code | text | Unique code within project |
| wbs_name | text | Node name |
| wbs_type | text | Building, Level, Zone, Room, Element, Task group |
| full_path | text | Concatenated breadcrumb |
| status | text | Draft / Active / On Hold / Closed / Archived |
| sort_order | int | Display order among siblings |

## 23.2 wbs_assignments

| Field | Type | Description |
| --- | --- | --- |
| id | uuid | Assignment ID |
| wbs_id | uuid | Linked node |
| owner_id | uuid | Responsible user / team |
| discipline | text | STR / ARC / MEP / CIV / multi |

## 23.3 wbs_progress

| Field | Type | Description |
| --- | --- | --- |
| id | uuid | Progress record ID |
| wbs_id | uuid | Linked node |
| planned_progress | numeric | Planned % at the reporting date |
| actual_progress | numeric | Rolled-up actual % |

# 24. API Endpoints

The WBS Engine exposes the following endpoints. All endpoints are tenant-scoped and enforce the permission matrix in Section 19.

| Method | Endpoint | Purpose | Permission |
| --- | --- | --- | --- |
| GET | /wbs | List / tree of nodes | View |
| POST | /wbs | Create node | WBS Manager |
| PUT | /wbs/{id} | Update node | WBS Manager |
| DELETE | /wbs/{id} | Controlled delete | Administrator |
| POST | /wbs/clone | Clone template to project | WBS Manager |
| GET | /wbs/progress | Rolled-up progress | View |

# 25. Definition of Done

A project WBS is considered complete and production-ready only when all of the following are satisfied.

| # | Criterion | Status |
| --- | --- | --- |
| 1 | Buildings created | ✓ |
| 2 | Levels created | ✓ |
| 3 | Zones created | ✓ |
| 4 | Rooms created | ✓ |
| 5 | Elements created | ✓ |
| 6 | Owners assigned | ✓ |
| 7 | Reviewed by discipline managers | ✓ |
| 8 | Approved by Project Manager | ✓ |
| 9 | Activated | ✓ |
| 10 | Progress roll-up enabled | ✓ |
| 11 | Reporting enabled | ✓ |

# 26. Common Mistakes & Non-Conformances

The following practices are non-conformances. Where the platform cannot prevent them outright, they are flagged for correction.

| Non-Conformance | Why It Is Wrong | Correct Practice |
| --- | --- | --- |
| Creating tasks without a WBS link | Breaks traceability and roll-up | Always attach tasks to a leaf node |
| Duplicate WBS codes | Corrupts numbering & reporting | Enforce uniqueness within project |
| Skipping the Zone level on a multi-zone floor | Loses location granularity | Use every applicable level |
| Mixing disciplines into the physical hierarchy | Confuses structure with discipline | Tag discipline; keep hierarchy physical |
| Using the WBS as a cost code | Conflates location with accounting | Link cost codes to WBS; keep them separate |
| Entering progress at a parent node | Bypasses roll-up integrity | Enter progress only at leaf level |
| Deleting a node that has records | Destroys history | Close or cancel the node instead |

# 27. Governance Rules

- The WBS is mandatory for every project — there are no exceptions.

- No operational record may exist without a WBS linkage.

- All modules must consume WBS from the centralized WBS Engine.

- Modules must not create independent location structures.

- Active codes and historical nodes are protected; structural changes follow change control.

- Audit logs for WBS actions are append-only and cannot be deleted.

Why this matters Tasks execute work. Documents store information. Costs track money. Inspections verify quality. But the WBS provides the structure that connects them all. Without WBS, there is no project control — every project, every location, every task, and every document must belong to a controlled WBS structure.

# 28. Future Enhancements

The following capabilities are planned to extend the WBS Engine. They build on, but do not change, the principles in this SOP.

| Enhancement | Benefit |
| --- | --- |
| BIM integration | Link WBS nodes to model objects for 3D location |
| 4D planning | Tie schedule activities to WBS for time-based visualization |
| AI progress forecast | Predict completion and flag at-risk nodes early |
| Digital twin | Live operational mirror of the built asset by WBS location |
| Location-based reporting | Heat-mapped progress and issues across the WBS |
| Auto WBS code generation | Rule-based code assignment to reduce manual entry |

# Appendix A — End-to-End Worked Example

A single rebar installation task, fully resolved through the structure, illustrates how every control question is answered by the WBS.

| Control Question | Resolved Value |
| --- | --- |
| Project | PRJ-2026-001 — GDT Office Tower |
| Building | BLD-TA — Tower A |
| Level | L05 — Level 5 |
| Zone | ZA — Zone A |
| Room | RM-MEETING01 — Meeting Room 01 |
| Element | STR-004 — Slab |
| Task | Install Rebar |
| Discipline | STR (Structures) |
| Owner | Structural Team |
| Status | In Progress (task) / Active (node) |

Resulting document number for a related shop-drawing under this node:

PRJ-2026-001-STR-DWG-BLD-TA-L05-001-R02

# 29. Final Statement

The WBS is the backbone of DCOS.

Tasks execute work. Documents store information. Costs track money. Inspections verify quality. But the WBS provides the structure that connects them all. Without WBS, there is no project control.

Every project. Every location. Every task. Every document.

Must belong to a controlled WBS structure.

— End of Procedure —