## 00 Overview
STANDARD WBS STRUCTURE – PLANNING MODULE & QS MODULE
Purpose: Standardise both structures and define the bridge so duration can be calculated from quantity.
MODULE | PRIMARY DRIVER | STANDARD CODE STYLE | SHEET IN THIS WORKBOOK
Planning WBS | Location + Sequence (When / Where) | PRJ / PH / BA / BX / BA-nF-ST… | 01 Planning WBS Standard
QS WBS | Product + Element (What / How much) | QS-1 … QS-7 with Bridge Codes | 02 QS WBS Standard
Bridge Mapping | Connection key for duration & cost | Type Code ↔ QS Bridge Code | 03 Bridge Mapping Standard
Productivity Library | Qty → Duration conversion rates | Trade + UoM + Daily output | 04 Productivity Library
Integration Rules | Governance & calculation rules | — | 05 Integration Rules
CORE FORMULA
Duration (days) = Quantity (from QS, by floor/zone) ÷ Daily Productivity (from Library) × Adjustment factors
MINIMUM CONNECTION FIELDS
Planning side: Type Code + Floor/Area + Cost Code
QS side: QS Code + Bridge Code + Unit + Quantity (preferably by location)
Shared: Bridge Mapping table + Productivity Library
RECOMMENDED USE
1. Adopt these two standard structures on every new building project.
2. Freeze Type Codes and Bridge Codes early (design stage).
3. Require QS to provide location-allocated quantities for duration-driver items.
4. Calculate durations for structural, architectural and MEP first-fix key trades and reconcile with the baseline schedule.
5. Keep both WBS living documents under Project Controls coordination.

## 01 Planning WBS Standard
Level | WBS Code | Type Code | Description | Type | Purpose / Notes
0 | 0 | PRJ-XXXX-XXX | PROJECT – [Building Name] | Project | Overall project container
1 | 01 | PH01 | 01 DESIGN & ENGINEERING | Phase | Produce approved design information
2 | 01.01 | PH01-DM | Design Management | Work Package | Brief, criteria, reviews, IFC, change control
2 | 01.02 | PH01-AR | Architectural Design | Work Package | Plans, elevations, schedules, IFC Arch
2 | 01.03 | PH01-ST | Structural Design | Work Package | Foundation to roof, analysis, IFC Struct
2 | 01.04 | PH01-ME | MEP Design | Work Package | All MEP disciplines + coordination
3 | 01.04.01 | PH01-EL | Electrical | Work Package | Power, lighting, earthing, lightning
3 | 01.04.02 | PH01-EV | ELV | Work Package | Data, CCTV, access, PA
3 | 01.04.03 | PH01-FA | Fire Alarm | Work Package | Detection & alarm
3 | 01.04.04 | PH01-HV | HVAC | Work Package | Cooling, duct, pipe
3 | 01.04.05 | PH01-PL | Plumbing | Work Package | Water supply, sanitary, drainage
3 | 01.04.06 | PH01-FF | Fire Fighting | Work Package | Sprinkler, hydrant, hydraulic
3 | 01.04.07 | PH01-MC | MEP Coordination | Work Package | Clash, builder work, IFC package
2 | 01.05 | PH01-BM | BIM Coordination | Work Package | Models, clash detection, federated model
2 | 01.06 | PH01-SD | Shop Drawings | Work Package | Struct, Arch, MEP shop drawings & approval
1 | 02 | PH02 | 02 PROCUREMENT | Phase | Obtain materials, equipment & packages
2 | 02.01 | PH02-PM | Procurement Management | Work Package | Strategy, schedule, tracking, expediting
2 | 02.02 | PH02-SM | Structural Materials | Work Package | Rebar, concrete, formwork, steel, WP materials
2 | 02.03 | PH02-AM | Architectural Materials | Work Package | Block, finishes, doors, windows, façade
2 | 02.04 | PH02-MM | MEP Materials | Work Package | Cables, pipes, equipment, devices
2 | 02.05 | PH02-PP | Procurement Process | Work Package | Requisition → RFQ → Eval → PO → Approval
2 | 02.06 | PH02-MF | Manufacturing & Expediting | Work Package | Production, FAT, inspection, expediting
2 | 02.07 | PH02-DL | Delivery & Receiving | Work Package | Transport, delivery, inspection, storage
1 | 03 | PH03 | 03 CONSTRUCTION | Phase | Physically execute the works
2 | 03.01 | BA | BA – MAIN BUILDING | Building | Primary building asset
3 | 03.01.01 | BA-B1 | B1 – Basement / Underground | Floor / Area | Earthwork, foundation, basement structure
4 | 03.01.01.01 | BA-B1-EW | Earthwork | Work Group | Excavation, support, dewatering, formation
4 | 03.01.01.02 | BA-B1-FD | Foundation | Work Group | Piles, pile caps, ground beams
4 | 03.01.01.03 | BA-B1-ST | Structural | Work Group | Columns, walls, beams, slab, stairs
4 | 03.01.01.04 | BA-B1-WP | Waterproofing | Work Group | Foundation, retaining, slab WP
4 | 03.01.01.05 | BA-B1-AR | Architectural | Work Group | Blockwork, plaster, finishes, doors
4 | 03.01.01.06 | BA-B1-ME | MEP | Work Group | First fix + testing
3 | 03.01.02 | BA-GF | GF – Ground Floor | Floor / Area | Typical floor cycle applies
4 | 03.01.02.01 | BA-GF-ST | Structural Works | Work Group | Setting out → columns → walls → beams/slab → pour → curing → strip
4 | 03.01.02.02 | BA-GF-AR | Architectural Works | Work Group | Blockwork → plaster → finishes → doors/windows → paint
4 | 03.01.02.03 | BA-GF-M1 | MEP First Fix | Work Group | Conduits, trays, pipes, ducts
4 | 03.01.02.04 | BA-GF-M2 | MEP Second Fix | Work Group | Cables, fixtures, equipment, devices
4 | 03.01.02.05 | BA-GF-QA | Testing & Inspection | Work Group | Inspection, testing, snag, floor completion
3 | 03.01.0X | BA-nF | nF – Typical Floor (1F to Top) | Floor / Area | Repeat BA-GF structure for each floor; change Type Code to BA-1F, BA-2F…
3 | 03.01.10 | BA-RF | RF – Roof | Floor / Area | Structure, waterproofing, finishes, roof MEP
4 | 03.01.10.01 | BA-RF-ST | Structural Works | Work Group | Roof structure, parapet
4 | 03.01.10.02 | BA-RF-WP | Waterproofing | Work Group | Membrane, insulation, protection
4 | 03.01.10.03 | BA-RF-AR | Architectural | Work Group | Finishes, access
4 | 03.01.10.04 | BA-RF-ME | MEP | Work Group | Drainage, HVAC, tanks, lightning
2 | 03.02 | BX | BX – EXTERNAL WORKS | Building / Zone | Site & external packages
3 | 03.02.01 | BX-SP | Site Preparation | Work Group | Clearance, temporary facilities, grading
3 | 03.02.02 | BX-CV | External Civil Works | Work Group | Excavation, fill, concrete, kerbs
3 | 03.02.03 | BX-DR | External Drainage | Work Group | Stormwater, sewer, manholes
3 | 03.02.04 | BX-UT | External Utilities | Work Group | Water, power, lighting, fire, telecom
3 | 03.02.05 | BX-RD | Road & Parking | Work Group | Subgrade to pavement, marking
3 | 03.02.06 | BX-LS | Landscaping | Work Group | Softscape, hardscape, irrigation
3 | 03.02.07 | BX-BG | Boundary & Gate | Work Group | Wall, gate, guard house, security
3 | 03.02.08 | BX-FN | External Finishes | Work Group | Painting, signage, cleaning, snagging
1 | 04 | PH04 | 04 COMMISSIONING & HANDOVER | Phase | Testing, snagging, documentation, taking over
2 | 04.01 | PH04-TC | Testing & Commissioning | Work Package | All systems + integrated testing
2 | 04.02 | PH04-SN | Snagging | Work Package | Internal, external, MEP, arch + rectification
2 | 04.03 | PH04-DO | Handover Documentation | Work Package | As-built, O&M, certificates, training, dossier
2 | 04.04 | PH04-HO | Handover | Work Package | Client inspection, taking over, completion
RULES
1. Level 0–2 = Summary only (no duration). Level 3–4 = Work packages / groups. Level 5 = Schedule activities (add under each Work Group).
2. Type Code is the primary bridge key to QS module (together with Cost Code).
3. For multi-floor buildings: duplicate BA-GF structure for each floor and change Type Code (BA-1F, BA-2F…).

## 02 QS WBS Standard
Level | QS Code | Bridge Code | Description | Unit | Typical Qty Basis | Notes
1 | 1 | QS-1 | PRELIMINARIES & GENERAL | Item / sum | Project | Site establishment, management, temp works
2 | 1.1 | QS-1.1 | Site Establishment & Temporary Works | sum | Project | Offices, hoarding, access, temporary roads
2 | 1.2 | QS-1.2 | Project Management & Supervision | sum / month | Project | Staff, insurances, bonds
1 | 2 | QS-2 | SUBSTRUCTURE | — | Location | All work below ground floor level
2 | 2.1 | QS-2.1 | Earthworks | m³ / m² | BA-B1-EW | Excavation, fill, disposal, formation
3 | 2.1.1 | QS-2.1.1 | Bulk excavation | m³ | BA-B1-EW | Connect to Planning BA-B1-EW activities
3 | 2.1.2 | QS-2.1.2 | Disposal of excavated material | m³ | BA-B1-EW
3 | 2.1.3 | QS-2.1.3 | Filling & compaction | m³ | BA-B1-EW
3 | 2.1.4 | QS-2.1.4 | Dewatering | sum / week | BA-B1-EW | Duration-sensitive
2 | 2.2 | QS-2.2 | Piling & Foundation | — | BA-B1-FD
3 | 2.2.1 | QS-2.2.1 | Piles (bored / driven) | m / no | BA-B1-FD | By pile type
3 | 2.2.2 | QS-2.2.2 | Pile testing | no | BA-B1-FD
3 | 2.2.3 | QS-2.2.3 | Pile caps | m³ | BA-B1-FD | Concrete + rebar often separate
3 | 2.2.4 | QS-2.2.4 | Ground beams | m³ | BA-B1-FD
3 | 2.2.5 | QS-2.2.5 | Foundation reinforcement | tonne | BA-B1-FD | Key duration driver
2 | 2.3 | QS-2.3 | Basement Structure | — | BA-B1-ST
3 | 2.3.1 | QS-2.3.1 | Basement columns | m³ | BA-B1-ST
3 | 2.3.2 | QS-2.3.2 | Retaining / shear walls | m³ / m² | BA-B1-ST
3 | 2.3.3 | QS-2.3.3 | Basement beams & slab | m³ | BA-B1-ST
3 | 2.3.4 | QS-2.3.4 | Basement reinforcement | tonne | BA-B1-ST
2 | 2.4 | QS-2.4 | Waterproofing (substructure) | m² | BA-B1-WP | Membrane, protection board
1 | 3 | QS-3 | SUPERSTRUCTURE | — | Location by floor | Frame, upper floors, roof, stairs
2 | 3.1 | QS-3.1 | Concrete Frame | — | BA-nF-ST | Allocate by floor
3 | 3.1.1 | QS-3.1.1 | Columns | m³ | BA-nF-ST | Per floor quantity
3 | 3.1.2 | QS-3.1.2 | Shear walls / core walls | m³ / m² | BA-nF-ST
3 | 3.1.3 | QS-3.1.3 | Beams | m³ | BA-nF-ST
3 | 3.1.4 | QS-3.1.4 | Slabs | m³ / m² | BA-nF-ST
3 | 3.1.5 | QS-3.1.5 | Stairs & landings | m³ / m² | BA-nF-ST
3 | 3.1.6 | QS-3.1.6 | Reinforcement (superstructure) | tonne | BA-nF-ST | Major duration driver – split beams/slab/walls if needed
3 | 3.1.7 | QS-3.1.7 | Formwork | m² | BA-nF-ST | Major duration driver
3 | 3.1.8 | QS-3.1.8 | Concrete (structural) | m³ | BA-nF-ST
2 | 3.2 | QS-3.2 | Structural Steel (if any) | tonne | BA-nF-ST | Optional
2 | 3.3 | QS-3.3 | Roof Structure | — | BA-RF-ST
3 | 3.3.1 | QS-3.3.1 | Roof slab / structure | m³ / m² | BA-RF-ST
3 | 3.3.2 | QS-3.3.2 | Parapet | m / m³ | BA-RF-ST
2 | 3.4 | QS-3.4 | Roof Waterproofing & Insulation | m² | BA-RF-WP
1 | 4 | QS-4 | ARCHITECTURE & FINISHES | — | Location by floor
2 | 4.1 | QS-4.1 | Blockwork / Masonry | m² | BA-nF-AR | Key duration driver
2 | 4.2 | QS-4.2 | Internal Partitions | m² | BA-nF-AR
2 | 4.3 | QS-4.3 | Plastering / Rendering | m² | BA-nF-AR | Key duration driver
2 | 4.4 | QS-4.4 | Screeds | m² | BA-nF-AR
2 | 4.5 | QS-4.5 | Floor Finishes | m² | BA-nF-AR | Tiles, stone, vinyl, etc.
2 | 4.6 | QS-4.6 | Wall Finishes / Tiling | m² | BA-nF-AR
2 | 4.7 | QS-4.7 | Ceiling Finishes | m² | BA-nF-AR
2 | 4.8 | QS-4.8 | Painting & Decorating | m² | BA-nF-AR
2 | 4.9 | QS-4.9 | Doors, Frames & Hardware | no | BA-nF-AR
2 | 4.10 | QS-4.10 | Windows & Glazing | m² / no | BA-nF-AR
2 | 4.11 | QS-4.11 | Façade / Curtain Wall | m² | BA / External | May be package
2 | 4.12 | QS-4.12 | Waterproofing (wet areas) | m² | BA-nF-AR
2 | 4.13 | QS-4.13 | Sanitary Fixtures | no | BA-nF-AR / MEP
1 | 5 | QS-5 | MEP SERVICES | — | Location + system
2 | 5.1 | QS-5.1 | Electrical | — | BA-nF-M1 / M2
3 | 5.1.1 | QS-5.1.1 | Conduits & cable trays | m | BA-nF-M1 | First fix
3 | 5.1.2 | QS-5.1.2 | Cables | m | BA-nF-M2 | Second fix
3 | 5.1.3 | QS-5.1.3 | DB / Switchgear | no | BA-nF-M2
3 | 5.1.4 | QS-5.1.4 | Lighting fixtures | no | BA-nF-M2
3 | 5.1.5 | QS-5.1.5 | Small power / accessories | no | BA-nF-M2
2 | 5.2 | QS-5.2 | ELV Systems | — | BA-nF-M1 / M2 | Data, CCTV, access, PA
2 | 5.3 | QS-5.3 | Fire Alarm | — | BA-nF-M1 / M2
2 | 5.4 | QS-5.4 | HVAC | — | BA-nF-M1 / M2
3 | 5.4.1 | QS-5.4.1 | Ductwork | m² / m | BA-nF-M1 | First fix
3 | 5.4.2 | QS-5.4.2 | HVAC pipework | m | BA-nF-M1
3 | 5.4.3 | QS-5.4.3 | HVAC equipment | no | BA-nF-M2 / BA-RF-ME
2 | 5.5 | QS-5.5 | Plumbing & Drainage | — | BA-nF-M1 / M2
3 | 5.5.1 | QS-5.5.1 | Water supply pipes | m | BA-nF-M1
3 | 5.5.2 | QS-5.5.2 | Drainage pipes | m | BA-nF-M1
3 | 5.5.3 | QS-5.5.3 | Plumbing fixtures | no | BA-nF-M2
2 | 5.6 | QS-5.6 | Fire Fighting | — | BA-nF-M1 / M2
3 | 5.6.1 | QS-5.6.1 | Fire fighting pipes | m | BA-nF-M1
3 | 5.6.2 | QS-5.6.2 | Sprinklers & equipment | no | BA-nF-M2
1 | 6 | QS-6 | EXTERNAL WORKS | — | BX-*
2 | 6.1 | QS-6.1 | Site preparation & earthworks | m³ / m² | BX-SP / BX-CV
2 | 6.2 | QS-6.2 | External drainage | m / no | BX-DR
2 | 6.3 | QS-6.3 | External utilities | m / no | BX-UT
2 | 6.4 | QS-6.4 | Roads & paving | m² | BX-RD
2 | 6.5 | QS-6.5 | Landscaping | m² / no | BX-LS
2 | 6.6 | QS-6.6 | Boundary walls, gates & security | m / no | BX-BG
1 | 7 | QS-7 | DAYWORKS / PROVISIONAL / CONTINGENCY | — | Project | As required by contract
RULES
1. QS WBS is product/element based. Use Bridge Code to link to Planning Type Code (BA-nF-ST, BA-nF-AR, etc.).
2. Wherever possible, allocate quantities by location (floor / zone) so duration can be calculated per Planning activity.
3. Key duration drivers (rebar, formwork, concrete, blockwork, plaster, major MEP first fix) should always have floor-level quantities.

## 03 Bridge Mapping Standard
Planning Type Code | Planning Description | QS Bridge Code | QS Description | UoM | Mapping Rule | Duration Driver?
BA-B1-EW | B1 Earthwork | QS-2.1 | Earthworks | m³ | 1 Planning group ← 1 or more QS items; sum qty by location | Yes
BA-B1-FD | B1 Foundation | QS-2.2 | Piling & Foundation | m³ / t / no | Map pile, pile cap, ground beam, foundation rebar separately if needed | Yes
BA-B1-ST | B1 Structural | QS-2.3 | Basement Structure | m³ / t | Columns, walls, beams, slab, rebar | Yes
BA-B1-WP | B1 Waterproofing | QS-2.4 | Waterproofing (substructure) | m² | Direct | Medium
BA-B1-AR | B1 Architectural | QS-4.x | Blockwork, plaster, finishes… | m² / no | Multiple QS items → one Planning group | Medium
BA-B1-ME | B1 MEP | QS-5.x | MEP first fix items | m / no | Conduits, pipes, trays by system | Medium
BA-nF-ST | Typical Floor Structural | QS-3.1 | Concrete Frame (by floor) | m³ / t / m² | MUST have floor-allocated qty for rebar, formwork, concrete | Yes – Critical
BA-nF-AR | Typical Floor Architectural | QS-4.1–4.12 | Blockwork to painting (by floor) | m² / no | Blockwork & plaster are main duration drivers | Yes
BA-nF-M1 | Typical Floor MEP 1st Fix | QS-5.x.1 | Conduits, trays, pipes, ducts (by floor) | m / m² | First fix before plaster/ceiling | Yes
BA-nF-M2 | Typical Floor MEP 2nd Fix | QS-5.x.2+ | Cables, fixtures, equipment (by floor) | m / no | After finishes | Medium
BA-nF-QA | Typical Floor Testing | — | Not quantity-driven | — | Duration from experience / inspection schedule | No
BA-RF-ST | Roof Structural | QS-3.3 | Roof Structure | m³ / m² | Direct | Yes
BA-RF-WP | Roof Waterproofing | QS-3.4 | Roof WP & Insulation | m² | Direct | Medium
BA-RF-AR | Roof Architectural | QS-4.x | Roof finishes | m² | Direct | Low
BA-RF-ME | Roof MEP | QS-5.4.3 / 5.x | Roof equipment, drainage, tanks | no / m | Equipment installation | Medium
BX-SP | Site Preparation | QS-6.1 | Site prep & earthworks | m³ / m² | Direct | Medium
BX-CV | External Civil | QS-6.1 | External civil | m³ / m² | Direct | Medium
BX-DR | External Drainage | QS-6.2 | External drainage | m / no | Direct | Medium
BX-UT | External Utilities | QS-6.3 | External utilities | m / no | Direct | Medium
BX-RD | Road & Parking | QS-6.4 | Roads & paving | m² | Direct | Yes
BX-LS | Landscaping | QS-6.5 | Landscaping | m² / no | Direct | Low
BX-BG | Boundary & Gate | QS-6.6 | Boundary, gates, security | m / no | Direct | Medium
PH01-* | Design packages | — | Not quantity-driven for duration | — | Duration from design programme / resources | No
PH02-* | Procurement packages | — | Lead time from supplier, not BOQ qty | — | Use long-lead register + procurement schedule | No
PH04-* | Commissioning & Handover | — | Not quantity-driven | — | Duration from testing plan & snag allowance | No
DURATION CALCULATION RULE
Duration (days) = Quantity (from QS, by location) ÷ Daily Productivity (from Productivity Library) × Factors (crew, shift, complexity).
Only rows marked 'Yes' under Duration Driver should be used for quantity-based duration. Others use experience / programme logic.

## 04 Productivity Library
ID | Trade / Item | UoM | Daily Output (1 crew) | Typical Crew Size | Man-days per Unit | Planning Type Code | Notes
P01 | Bulk excavation (machine) | m³ | 150 | 1 excavator + 2 men | 0.02 | BA-B1-EW | Adjust for soil type & disposal distance
P02 | Pile installation (bored) | m | 20 | 1 rig + 4 men | 0.25 | BA-B1-FD | Per rig
P03 | Pile cap concrete | m³ | 40 | 8 men + pump | 0.2 | BA-B1-FD
P04 | Foundation rebar | tonne | 1.2 | 8–10 men | 7.5 | BA-B1-FD | Key driver
P05 | Column rebar | tonne | 1 | 8 men | 8 | BA-nF-ST | Key driver
P06 | Beam rebar | tonne | 1.2 | 8–10 men | 7.5 | BA-nF-ST | Key driver
P07 | Slab rebar | tonne | 2.5 | 10–12 men | 4 | BA-nF-ST | Key driver
P08 | Column formwork | m² | 40 | 6 men | 0.15 | BA-nF-ST
P09 | Beam & slab formwork | m² | 80 | 10–12 men | 0.13 | BA-nF-ST | Key driver
P10 | Structural concrete pour | m³ | 80 | Pump + 10 men | 0.12 | BA-nF-ST | Limited by pump / batching
P11 | Blockwork (150–200mm) | m² | 30 | 6–8 men | 0.23 | BA-nF-AR | Key driver
P12 | Internal plaster | m² | 50 | 6 men | 0.12 | BA-nF-AR | Key driver
P13 | Floor screed | m² | 80 | 6 men | 0.08 | BA-nF-AR
P14 | Floor tiling | m² | 35 | 4–6 men | 0.14 | BA-nF-AR
P15 | Wall tiling | m² | 25 | 4 men | 0.16 | BA-nF-AR
P16 | Painting (internal, 2 coats) | m² | 80 | 4–6 men | 0.06 | BA-nF-AR
P17 | Electrical conduits (1st fix) | m | 120 | 4–6 men | 0.04 | BA-nF-M1
P18 | Cable tray | m | 40 | 4 men | 0.1 | BA-nF-M1
P19 | Plumbing pipes (1st fix) | m | 60 | 4 men | 0.07 | BA-nF-M1
P20 | HVAC ductwork | m² | 50 | 4–6 men | 0.1 | BA-nF-M1
P21 | Fire fighting pipes | m | 50 | 4 men | 0.08 | BA-nF-M1
P22 | Cable pulling | m | 200 | 4 men | 0.02 | BA-nF-M2 | Varies by cable size
P23 | Lighting installation | no | 30 | 4 men | 0.13 | BA-nF-M2
P24 | Roof waterproofing membrane | m² | 100 | 6 men | 0.06 | BA-RF-WP
P25 | Asphalt / road paving | m² | 200 | Paver + crew | 0.03 | BX-RD | Machine output
NOTE: Productivity rates are indicative starting values. Calibrate with project historical data or early site records. Man-days per Unit ≈ Crew size ÷ Daily Output.

## 05 Integration Rules
STANDARD INTEGRATION RULES – PLANNING WBS ↔ QS WBS
1. PURPOSE OF EACH WBS
Planning WBS | Answers WHEN and WHERE work happens. Location + sequence driven. Used for schedule, resources, progress.
QS WBS | Answers WHAT and HOW MUCH. Product / element driven. Used for quantities, cost, BOQ, valuation.
2. DO NOT FORCE THEM TO BE IDENTICAL
Rule | Keep Planning location-based and QS product-based. Connect them through Bridge Codes, do not merge into one tree.
3. BRIDGE KEYS (mandatory)
Primary key | Planning Type Code (e.g. BA-3F-ST) ↔ QS Bridge Code (e.g. QS-3.1)
Secondary key | Cost Code (shared in both systems for cost reporting)
Location key | Floor / Area (BA-B1, BA-GF, BA-1F… BA-RF, BX-*) – QS quantities should be allocated by location for duration drivers
4. DURATION FROM QUANTITY
Formula | Duration (days) = Quantity (location-specific) ÷ Daily Productivity × Adjustment factors
Where applied | Only for Duration Drivers (see Bridge Mapping sheet – marked Yes)
Where NOT applied | Design, Procurement lead times, Testing, Snagging, Handover – use programme logic / experience
5. MAPPING CARDINALITY
One-to-Many | One Planning activity/group can receive quantity from several QS items (e.g. BA-3F-ST ← columns + beams + slab + rebar)
Many-to-One | One QS item can feed several Planning activities when quantity is split by floor
6. MINIMUM DATA QS MUST PROVIDE FOR INTEGRATION
Required | QS Code, Description, Unit, Total Quantity, Quantity by Location (for duration drivers), Unit Rate (optional for cost)
7. GOVERNANCE
Ownership | Planning Manager owns Planning WBS & Type Codes. QS Manager owns QS WBS & quantities. Project Controls owns the Mapping table.
Change control | Any change to Type Code or Bridge Code must update the Mapping sheet and be version-controlled.
Calibration | Productivity Library must be reviewed after first 1–2 floors and updated from actual site output.
8. IMPLEMENTATION SEQUENCE
Step 1 | Adopt both standard WBS structures (this workbook)
Step 2 | Agree Bridge Codes and freeze the Mapping sheet
Step 3 | QS produces quantities with location allocation for duration drivers
Step 4 | Calculate durations for key trades and compare with baseline
Step 5 | Load agreed durations into Planning schedule; use variance for improvement
Step 6 | Feed Level 4–5 packages to Last Planner for weekly work plans